| 3 | Engineering and Construction |
| --- | --- |
| Short Contract |
| A contract between | Westcountry Rivers Trust |
|  | Rain-Charm House, Kyl Cober Parc, Stoke Climsland, Cornwall, PL17 8PH |
| and | TBC |
| for | Fish Passage Improvement – Trewen Bridge Weir |
|  | Contents | Page |
|  | Contract Forms |  |
|  | Contract Data | 2 |
|  | The Contractor’s Offer | 5 |
|  | The Employer’s Acceptance | 5 |
|  | Price List | 6 |
|  | Works Information | 8 |
|  | Site Information | 12 |
|  | Conditions of Contract | CC1 |
| 1 |

| Contract Data |
| --- |
|  | The Employer is |
| Name | Westcountry Rivers Trust |
| Address | Rain-Charm House, Kyl Cober Parc, Stoke Climsland, Cornwall, PL17 8PH |
| Telephone | 01579 372140 |
| E-mail address | david@wrt.org.uk |
| The works are | The structural design and construction of a new glacis downstream of the existing bridge foundation slab. The placement of 200mm high baffles down the face of the new glacis to provide passage for salmonids and the formation of an eel pass on the left-hand bank formed from proprietary eel tiles. Making good of the adjoining wingwalls downstream of the bridge. The formation of an eel passage formed from proprietary eel tiles. Protection of the left-hand bank downstream of the weir with appropriately sized riprap stone. The higher sections of bank will be dressed with topsoil and seeded with an appropriate grass/wildflower seed mix. Eel Pass at Camelford Weir, River Camel, Cornwall |
| The site is | Trewen Bridge Weir, SX09268 83439, refer to location plan 01 and Detailed Site Location & Block Plan 02. |
| The starting date is | 28 August 2019 |
| The completion date is | 30 September 2019 |
| The period for reply is | One | week. |
| The defects date is | One | year after Completion. |
| The defect correction period is | Four | weeks. |
| The delay damages are | £750 | per week. |
| The assessment day is the | last Thursday | of each month. |
| The retention is | Five | %. |
| Does the United Kingdom Housing Grants, Construction and Regeneration Act (1996) apply? | No |
|  | The Adjudicator is |
| Name | Construction Industry Council (CIC) |
| Address | Construction Industry Council (CIC) The Building Centre 26 Store Street London WC1E 7BT |
| Telephone | 020 7399 7400 |
| E-mail address | enquiries@cic.org.uk |
| 2 |

| Contract Data |
| --- |
| The interest rate on late payment is 0.15 % per complete week of delay. |
| The Contractor is not liable to the Employer for loss of or damage to the Employer’s |
| property in excess of | £5,000,000 for any one event. |
| The Employer provides this insurance | None |
| The minimum amount of cover for the third insurance (Public Liability) stated in the |
| Insurance Table is | £5,000,000 |
| The minimum amount of cover for the fourth insurance (Employers Liability) stated in the |
| Insurance Table is | £5,000,000 |
| The Adjudicator nominating body is | Construction Industry Council (CIC) |
| The adjudication procedure is | The current CIC Model Adjudication Procedure |
| The conditions of contract are the NEC3 Engineering and Construction Short Contract (June 2005 with amendments September 2011) and the following additional conditions |
| Security | Z1 Z1.1 | Site admittance The Contractor submits to the Employer details of people who are to be employed by him and his Subcontractors in connection with the works. The details include a list of names and addresses, the capacities in which they are employed, and other information required by the Employer. |
|  | Z1.2 | Photographs The Contractor does not take photographs of the site or the works or any part of them unless he has obtained the acceptance of the Employer. |
|  | Z1.3 | The Contractor takes the measures needed to prevent his and his subcontractors’ people taking, publishing or otherwise circulating such photographs. |
| Parent Company Guarantee | Z2 Z2.1 | It is a condition precedent to the obligation of the Employer to pay any sums under this contract that if the Contractor is a subsidiary within the meaning of the Companies Act 2006 the Contractor has provided to the Employer a parent company guarantee in the form set out in this contract duly executed as a deed by the Contractor’s ultimate parent. |
| Principal Designer & Contractor | Z3 Z3.1 Z3.2 | The Contractor is the Principal Contractor in terms of The Construction (Design and Management) Regulations 2015. The Employer is the Principal Designer in terms of The Construction (Design and Management) Regulations 2015. |
|  |  | 3 |
| The Contracts (Rights of Third Parties) Act 1999 | Z4 Z4.1 | For the purposes of the Contracts (Rights of Third Parties) Act 1999, nothing in this contract confers or purports to confer on a third party any benefit or any right to enforce a term of this contract. |
| Sub-contracting | Z5 Z5.1 | The Contractor submits the name of each proposed Subcontractor to the Employer for acceptance. A reason for not accepting the Subcontractor is that his appointment will not allow the Contractor to provide the works. The Contractor does not appoint a proposed Subcontractor until the Employer has accepted him. |
| Dispute Resolution | Z6 Z6.1 | Disputes between Employer and Contractor are to be resolved in the first instance by the Project Managers for the Employer and Contractor. Where a resolution between these two designated individuals is not possible, the dispute should be escalated to the Chief Executive of the parties for resolution. Should the Chief Executives fail to reach agreement the dispute is to be referred to a neutral third party for mediation. Only when these steps fail should the dispute be resolved in line with the Contract Data as set out on page 2 of this contract. |
| Contractor’s Design | Z7 Z7.1 | Details of the Contractor’s Design element include concrete specification, reinforcement details and structural calculations. Details of proposed baffle fixing technique will also be required. |
| Biosecurity | Z8 |  |
|  | Z8.1 | The WRT Biosecurity Protocol must always be adhered to. |
| 4 |

| Contract Data |
| --- |
| The Contractor’s Offer |
| The Contractor is |
| Name | TBC |
| Address |  |
| Telephone |  |
| E-mail address |  |
| The percentage for overheads and profit added to the Defined Cost for people is %. The percentage for overheads and profit added to other Defined Cost is %. |
| The Contractor offers to Provide the Works in accordance with the conditions of contract for an amount to be determined in accordance with the conditions of contract. |
| The offered total of the Prices is |  |
|  | Enter the total of the Prices from the Price List. |  |
| Signed on behalf of the Contractor |  |
| Name |  |
| Position |  |
| Signature |  | Date |
| The Employer’s Acceptance |
| The Employer accepts the Contractor’s Offer to Provide the Works Signed on behalf of the Employer |
| Name |  |
| Position |  |
| Signature |  | Date |
| 5 |

| Contract Data |
| --- |
| Price List |
| PREAMBLE TO THE PRICE LIST The Prices entered against each item in the Price List shall allow for all costs of performing or procuring all activities and obligations required and described in, or that can be reasonable inferred from, the contract, other than any which are specifically described in the contract as costs to be borne by the Employer. The Price List forms the basis for payment. The amount entered against an item shall be the sum due to the Contractor on completion of the item. The Employer will not make any payment for work other than against completed items in the Price List. Completion of an item is deemed to include supplying the Employer with any relevant certificates relating to Plant, Materials and tests applicable to the works contained in the item. The costs of any activities which have not been included within the Price List shall be deemed to have been included within the prices for the other items within the Price List. Items in the Price List must be for discrete, clearly identifiable sections of work. Because payment depends on the satisfactory completion of items it is necessary to define tangible completion for items where completion is not physically obvious. Every item in the Price List upon which the quotation has been based and for which the contractor would expect to be paid under any ensuing contract shall be legibly priced in ink. Each item must be given a unique and logical reference number. It must be possible to identify items in the Price List with work items shown on the programme required by the contract. The contractor may add additional items to the Price List to ensure that he can be paid for fulfilling his obligations under the contract, particularly the requirements and conditions described in the Works Information. The contractor may expand each item into as many sub-items as he wishes, bearing in mind that one aim of using a Price List is to simplify the assessment of payments due to the Contractor. Separate sub-total sums of the Prices for all the sub-items within each item must be shown, and these item sub-totals must be added together to form the total amount of the Quotation. Sub-items need not be site construction activities. The various elements of contractor’s design, preparation of the CDM Construction Phase Health and Safety Plan or making a down payment for materials or off-site works may be legitimate sub-items, but it must be possible to identify tangible completion for items where completion is not physically obvious. The contractor shall note that the Employer retains the right to omit any of the items as required to conform to the allowable budget for the project. Where items listed by the contractor in the Price List are to be omitted, notification will be given to the contractor by the Employer. |
| 6 |
| Entries in the first four columns in this Price List are made either by the Employer or the contractor. If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the contractor enters the amount in the Price column only; the Unit, Quantity and Rate columns being left blank. If the Contractor is to be paid an amount for the item of work which is the rate for the work multiplied by the quantity completed, the contractor enters the rate which is then multiplied by the expected quantity to produce the Price, which is also entered. |
| Item number | Description | Unit | Quantity | Rate | Price |
|  | The total of the Prices, excluding VAT | £ |  |
|  | 7 |

Contract Data

Works Information

1 Description of the works

The works seek to improve upstream fish passage for salmonids and eel at Trewen Bridge Weir. The weir is located downstream of the bridge and is formed of the bridge’s concrete slab foundation. Fish passage is compromised by the head difference over the weir of some 450mm and also the relatively shallow and fast flowing river section beneath the bridge over the bridge apron. In outline, the proposed works comprise; the construction of a new glacis downstream of the existing bridge foundation slab, the placement of 200mm high baffles down the face of the new glacis to provide passage for salmonids, the formation of an eel pass on the left-hand bank formed from proprietary eel tiles and the making good of the adjoining wingwalls downstream of the bridge. An element of Contractor’s Design is also required for structural elements of proposed new glacis including concrete type and dimensions, steel reinforcement and cover requirements. The construction drawings provide details of the works proposed. The Construction Method Statement provided is a starting point to planning the works, the Contractor is to prepare their own Method Statement for the undertaking of the works, including all temporary works required; a construction phase Health and Safety Plan is also required. A programme must also be prepared demonstrating completion of the works by 30 September 2019 (subject to all consents being in place and favourable weather/river conditions). Once consents are in place (to be sought by the employer) and in times of suitable river and weather conditions, the Contractor is to undertake the works as agreed and in full compliance with this contract. Should this not be possible prior to 30 September 2019, it is anticipated that they will be undertaken in a suitable weather window during the 2020 in-river work window. All works must comply with current industry standard best practice appropriate for the operations required, all latest editions of relevant British and European Standards, the Civil Engineering Specification for the Water Industry and PPG5 - Pollution Prevention Guidelines Works and maintenance in or near water.

8

| 2 Drawings |
| --- |
|  | Drawing number | Revision | Title |  |
|  | 01 | 0 | Site Location Plan |  |
|  | 02 | 0 | Detailed Site Location and Block Plan |  |
|  | 03 | 0 | Existing Layout Plan |  |
|  | 04 | A | Proposed Layout Plan |  |
|  | 05 | A | Sections – Existing and Proposed |  |
|  | 06 | 0 | Proposed Temporary Works |  |
|  | 9 |

| Contract Data |
| --- |
| Works Information |
| 3 Specifications |
|  | Title | Date or revision | Tick if publicly available |  |
|  | Pollution Prevention Guidelines 5 (PPG5) Working In or Near a Watercourse | October 2007 |  |  |
|  | Civil Engineering Specification for the Water Industry 7th Edition | 7th Edition |  |  |
|  | The works are to be carried out in a manner that is sympathetic to the surrounding environment. Anti-pollution measures must be in place to prevent water pollution and all work and machinery must conform to Pollution Prevention Guidelines 5 (PPG5) Working In or Near a Watercourse. All proposed works must conform to all relevant British and European Standards and current Best Practice Guidelines. |  |
| 4 Constraints on how the Contractor Provides the Works |
|  | All works must be undertaken in accordance with the drawings and documents provided. All ‘in-river’ works must be complete by 30 September 2019. If this is not possible, it is anticipated that the works will be completed in the 2020 in-river works window at a time to be agreed. The works can only be undertaken at times of suitably dry and calm weather conditions when river levels are suitably low. The nearest Environment Agency river levels gauge is approximately 7km downstream at Penvose. All ‘in river’ work areas must be suitably bunded to form secure, fully enclosed, dry working areas. The site is located adjacent to a public highway and dwellings exist nearby. Due care and attention must be paid to ensure all impacts on highway users and nearby residents are minimised. Should it be necessary to park vehicles on the public highway, appropriate traffic control measures will be required. The site and surroundings must be maintained in a clean, tidy and workmanlike condition at all times. All existing surfaces, structures and other items must be left in an ‘as found’ condition as far as practical on the completion of the works. Services Information; The Contractor is to satisfy themselves that services do not exist and to ensure no services are damaged in anyway in the undertaking of the works. |  |
|  | 10 |

| Contract Data |
| --- |
| Works Information |
| 5 Requirements for the programme |
| The Contractor is to provide an estimated duration for the undertaking of the works, subject to weather and river conditions, and an indication of when they propose to commence the work. |
| The Contractor must be out of the river and the fish pass operational from the 30 September 2019, the recognised period for salmonid migration. |
| 6 Services and other things provided by the Employer |
|  | Item | Date by which it will be provided |  |
| It is not anticipated that any other services are located within or around the bridge and weir, but this may not be the case. The Contractor is to satisfy themselves that other services do not exist and to ensure no services are damaged in anyway in the undertaking of the works. | n. a |
|  | 11 |

| Contract Data |
| --- |
| Site Information |
| Site Location – drawings 01 and 02 indicate the location of the weir which is on the River Allen approximately one mile to the west of Camelford. |
| Access Routes and Site Boundaries – please refer to 02, Detailed Site Location and Block Plan. |
| Utility Information – please refer to 6 Services, above. The Contractor is to satisfy themselves that services do not exist and to ensure no services are damaged in anyway in the undertaking of the works |
| Other Site Considerations - please refer to 4 Constraints, above. It is essential that the site is managed in a workmanlike and considerate manner at all times. Vehicle movements and noise are to be kept to a minimum and the adjoining public highway is not blocked at any time unless appropriate traffic management systems are in place. Invasive species of flora, including Himalayan Balsam, exist nearby to the site. These will either have been treated by others prior to the works being undertaken or their locations indicated to the contractor prior to the commencement of works. Great care must be taken to ensure invasive species of flora and fauna are not spread/released to the wider environment during the undertaking of the works. The WRT Biosecurity Protocol must always be adhered to. |
|  | 12 |