## Sheet1
CLARIFICATION LOG
Tender: | Exhibition Design Tender - Mineral Gallery - Royal Institution of Cornwall
Tender Reference: | 09/2023_(02)
Published Date: | 2023-10-06
Version number: | 10
Number | Clarification | Response | Reply date
1 | Could you please confirm if the tender for RIC Museum Mineral gallery requires architectural services? | We do not envisage that this work will require architectural services. | 2023-09-14
2 | We note that the contract is a design build one with the scope of work running up to RIBA stage 6 (completion and handover). Would it therefore be acceptable for the team to be led by the fit out company with the design team employed as sub-consultants? | Yes. The RIC would only contract with the fit out company. | 2023-09-14
3 | Given that the tender is for a design build “turn key” solution how much detail of the design of the gallery are you expecting in the tender return? In order to price the fit out stage some level of detail will be needed and some flexibility developing a viable cost plan, within the budget envelope, will be needed during the contract. | We’re not expecting vast detail/ finished design as appreciate that for you to produce the detail you need input from our interpretation design and brand work as well as public consultation. During the evaluation, we will be looking at other schemes you have been involved with. There is a budget limit for the fitout. It will be your responsibility to ensure that your design comes within the proposed budget so will be looking at the team to project manage this accordingly. | 2023-09-14
4 | Is it possible for the RIC to provide more photographs of the gallery, collections and showcases, also plans of the building and/or a virtual tour to help us better understand the gallery and its relationship to the site? | Please find attached an extract of the Masterplan which details the current layout and relationship with the rest of the site. Additional photos also supplied of the current gallery. | 2023-09-14
5 | Could you kindly share CAD drawings and photos of the gallery please? | Additional photos supplied with this clarification. No CAD drawings are available. | 2023-09-14
6 | Please could you also advise whether there have been any discussions about what the Client would like to keep from the existing gallery, and what goes? | The client would like to retain as many of the minerals currently on display as possible. The mining material can be refreshed with other artefacts. They would like to retain the Edwardian dark wood, central cabinets, but replace the lightwood cabinets. | 2023-09-14
7 | Would you have a list of objects / artefacts available that must form part of the redeveloped gallery please? | A list of minerals is supplied with this clarification. We do not expect object mounts to be made for many/any of these. | 2023-09-14
8 | Please could you advise with reference to AV and interactive content, is the Client responsible for content / film production or would this fall within the responsibility and fee of the appointed design team please? If the latter, please could you advise whether any existing footage / content is available in the Museum’s collection that could be made available to the exhibition designer? | This would fall into the responsibility and budget of the project. There is no existing content. However, there are partners willing to support content development. | 2023-09-14
9 | Please could you confirm that building, structural and civil works would fall within the responsibility of the Client? I.e. the Exhibition Designer will be handed the gallery with finished floors, finished walls, HVAC, heating and insulation, emergency lighting, other non-show lighting (house, back of house, external, etc), fire alarm points and other safety requirements in place, internet access, telephone system in place, services (water, electricity, other power, cableways, trunking, conduit, AV cabling), electrical works to include distribution boards, contactors and power points, acoustic treatments completed etc? | There is no additional building works as part of this project. The gallery has existing LED track lighting, emergency lighting, heating and fire alarm points, wifi and electricity. This contract will need to include any changes to the existing parquet floor (polishing), painting and decorating, trunking etc. | 2023-09-14
10 | Please could you confirm whether internal walls / partitions and any windows block off/curtains (if applicable) would fall within the budget of the exhibition designer? | Not applicable | 2023-09-14
11 | Please could you share brand guidelines, if available? | These are currently being updated and will be available to the successful tenderer. | 2023-09-14
12 | The tender is for design and build. Can you confirm that you are only interested in design and build or would you consider a design and manage approach, where the designer is contracted and the fabricator appointed following a tender? | We are happy to consider alternative proposals so long as the project meets the deadline and budget constraints. In this scenario, The RIC will contract only with the designer as lead. For the purposes of evaluation we would however seek costs for the total works | 2023-09-14
13 | The brief doesn’t mention an interpretation plan. Can I assume that you do not require a plan and that all text and other content will be supplied by yourselves? | An interpretation plan is in development and will be available at a later stage. | 2023-09-14
14 | You plan to open the gallery by June 2024. This is a very tight programme for a project of this size. Is the date correct? If so are you able to consider extending the programme? | We can consider extending the deadline slightly . We are committed to our funding agteement which states open for Summer 2024. | 2023-09-14
15 | The brief refers to the re-use of the existing mineral gallery showcases and we would like to know what the status of these cases is, i.e. would it be acceptable to modify them to make them more accessible and/or improve conservation, safety and display standards? | We would like to retain the Edwardian dark wood, central cabinets, but replace the lightwood cabinets. The central cabinets are to be modified to make them more accessible and are to meet safety and display standards. This also meets with our environmental objectives to reuse and recycle. | 16/09/023
16 | Can you clarify whether a speculative creative response to the Design Brief is required at tender stage? | We are not looking for a draft design at tender stage. We will be looking for a methodology and examples of how you would approach the design element. | 2023-09-16
17 | We are asked to provide a breakdown of costs for Manufacturing and Construction. As the scheme will have not yet been designed, can we assume that the distribution of costs between manufacturing elements can be varied within the agreed overall cost as the design develops? | There is a budget breakdown for design and build within the tender pack. Returns should identify costs within these 2 budget allocations. | 16/09/024
18 | Tender Vol 1 identifies a maximum budget of £400,000 including VAT. For the avoidance of doubt can you confirm then that the maximum available budget is therefore £333,333.33 + VAT @ 20%? | Yes. Confirm that this is the case. | 2023-09-16
19 | Our usual approach is to design and deliver a project within the defined budget to provide best value for the client. Here we are being asked to propose a cost against which we would design and deliver the project. Clearly there is a direct relationship between the available funds and what can be delivered, so any tender price will have to be based on assumptions. Is it the RIC's intention to spend all of the available budget on this redevelopment or to look for a substantial reduction on that figure? | We have detailed the maximum budget available for the project. If you are able to design and deliver the project to the scale and quality detailed for less, then this should be detailed within your cost return. | 16/09/025
20 | Please can you provide a plan for the gallery space? | No - this is what we are looking for Consultants to produce. We have architectural plans within the masterplan. | 2023-09-20
21 | Please can you advise/share any interpretation plans that have been developed to date on the project? | An interpretation plan is in development and will be available at a later stage. | 2023-09-20
22 | Please can you advise if there is any further information on the content requirements e.g., are there certain objects that need to be displayed together? | We are looking to keep the current curation as much as possible, so minerals in the same groups as they are at the moment, displayed together. We aren’t looking for mounts or any additional display. | 2023-09-20
23 | Content / Script writing / research requirements. Should we allow for any script writing or will the client team be providing all written content? | You should allow for script writing | 2023-09-20
24 | We understand that we can submit the tender return in our own document format as long as we cross reference to questions within 'Tender-Vol 1-Instructions_Final’ | That is correct. | 2023-09-20
25 | Is it possible to further define the scope of work for the Mechanical and Electrical Services (including lighting) ? Our understanding is as follow: a. Focus of existing lights on track, is it possible to identify a quantity and type of fitting? | We are currently upgrading some of the M&E fittings in the museum. The lighting system is remaining but the control of the track circuits are replaced by a control system rather than the current manual switches. The luminaires on the tracks are the Concord Sylvania LED Muse fittings which we believe some of them have inbuilt dimming control and all have adjustable beam angles and focus. The newer version of the same fitting will, so we believe, fit the current track if there are insufficient fittings. | 2023-09-20
26 | Is it possible to further define the scope of work for the Mechanical and Electrical Services (including lighting) ? Our understanding is as follow: b. Specify and install new lights to existing timber showcases. Is it know if the existing power supply to each showcase can be re-used or is it expected to be replaced? | Existing power supply can be reused | 2023-09-20
27 | Is it possible to further define the scope of work for the Mechanical and Electrical Services (including lighting) ? Our understanding is as follow: c. Provide new power and data for the digital lab within the existing Mineral Gallery. Is it imagined that this will re-use existing supplies or will new connections need to be made from locations outside of the gallery. | Unknown until we know the design detail | 2023-09-20
28 | We applaud the intention to reuse and recycle the Edwardian cases, and wondered to what extent they can be modified to meet modern museum standards. Have the cases been accessioned or are they subject to the Grade 2 listing? | They are not accessioned or subject to the building's listing and can be modified. We would like to see them lowered, and better use of the cupboards and drawers for display. | 2023-09-20
29 | The Schedule 1 Price asks for a breakdown of cost per RIBA stage. At RIBA 2 - Concept Design (to include feasibility report / Business Plan). Can you please clarify what is required in addition to the RIBA Concept Stage Design Report? Are bidders required to include the services of a Business Planner on their team. | Just a stage design report is required (with cost plan) | 2023-09-20
30 | Is the RIC open to some progress meetings being conducted virtually? | Yes absolutely. | 2023-09-20
31 | Thank you for clarifying the status of the Edwardian cases. Clearly they will need a substantial amount of work to make them more suitable for use. Can we assume that the cases can be removed to our joinery workshop for modification? | Yes of course | 2023-09-25
32 | As we pull together our team of museum specialists, we are keen to include contractors who may be able to contribute to the museum's local economy. Can you define 'local' as it is referred to in the Method Statement Social Value Considerations, i.e. is this Truro City, Carrick District or Cornwall? | Cornwall | 2023-09-25
33 | Please could we request a one-week extension to enable bidders to compile information effectively for the full project team. | Unfortunately, due to the tight timescales to deliver this project, we cannot offer an extension. | 2023-09-27
34 | It is unusual for contract/project administration to be in the requirements of the design team as usually this would be an external function. Could you clarify this please. | We are expecting the design team to ensure that the design and build proposed is delivered within the specified budget. Any variations from this MUST be agreed with the client. | 2023-09-27
35 | Is the design element separate to the construction or the tenderer has to provide both as a package | We are looking for a design and build team. | 2023-09-29
36 | Essentially, we were wondering if there would be any value in us submitting a tender that concentrates solely on the front end of the project and handover to any exhibition build and manufacturers contractors that may be on your books already. Looking at the diagram attached provided in the tender pack, we would cover areas of strategic definition, preparation and briefing and concept design. We would then effectively then handover to an exhibition build contractor. | We are looking for a design and build team. | 2023-09-29
37 | We note that interviews for shortlisted bidders are proposed to be in person in Truro. While travel to Truro is an accepted aspect of delivering the contract, we would request that interviews can be conducted virtually to minimise the cost and time of travel when the outcome is uncertain. Please advise. | Yes, online would be acceptable | 2023-09-29
38 | We are concerned that it may not be feasible to modify the central desktop showcases sufficiently to make them fully accessible. Are you able to tell us whether the glass showcase element can be removed from the specimen drawers below? If not, is it acceptable to the RIC to replace some of these with new showcases that can be designed to meet the necessary access and conservation standards? | The showcase tops could be removed with some carpentry work, and new bases created. These are the cases that we are particularly keen to retain, so we would rather see them modified than lost altogether. | 2023-09-29
39 | Is it in order to respond to relevant questions on a separate document rather than within the Selection Questionnaire? In particular Section 3 provided these are cross referenced in the Selection Questionnaire along with the appropriate reference header on the document itself. | We would ask bidders to provide their substantive responses within the Volume 2 – Applicants Offer document. If relevant information is to be provided in addition, please ensure this is clearly cross referenced | 2023-10-04
40 | We understand that work will only progress to the next work stage following client instruction and that the contract will initially be for RIBA stages 1 and 2. Please can you explain the costs you wish to see in respect of RIBA stages 5-6. Are you expecting to see the supplier fees for each of the services listed? Or are you expecting to see a figure for the total cost for that particular service? If the latter, providing a figure at this stage of the tender process is virtually impossible as it is not until the job progresses through the initial RIBA stages that the detail of the scheme becomes known. For example it is not known at this stage what AV Services will be required/applicable so it is not possible to allocate a cost at this stage. Would an acceptable solution be to enter costs for each service as a percentage of the overall budget available based on our experience of how a similar exhibition design project would typically break down? | Noting the challenge presented by detail of the proposal shaping the full costs for the later stages, e.g. Stages 5, 6, we would ask applicants to work on the basis of the total overall maximum budget for the tender is £400k (including VAT). We have as a guide indicated a range of estimated costs relate to the key elements of the work: Design: £48,000 - £78,000 Build: £328,000 – 352,000. Lowering the overall design costs will see more budget being available for build element. For example, a bid of design costs of £120k would leave £280k for build versus a bid design cost of £80k would leave a higher proportion of the total budget of £320k for build. Accordingly, we would propose to see a percentage cost related to the consultancy costs for the design element against each RIBA stage as set out in the Price Schedule. The Price Schedule has been updated to reflect the update removing specific reference to the build element line items. For avoidance of doubt the price element of the evaluation will therefore be based on the consultancy / design costs. | 2023-10-04
41 | In Schedule 1 - Price_Final Note N refers to the cost of services additional to those detailed in Appendix A. We cannot find Appendix A - does this refer to Appendix 1 the Design Brief? | Apologies, this should read “These rates will be used to establish the cost of services which are deemed to be additional to those quoted for in the tender response” not as within the document, e.g. “These rates will be used to establish the cost of services which are deemed to be additional to those detailed in Appendix A. | 2023-10-04
42 | In the Q&A - you have said that the central ‘dark wood Edwardian’ are to be adapted and the ‘light wooden’ cases to the walls are to be replaced. Is it possible to share the decision making / thinking behind this approach? | Our audience like the look and feel of the Edwardian cases but are not currently fully accessible. These can be updated with regards to different varnishes etc as required. Retaining these also meets with our environmental objectives to reuse and recycle. If you feel that the light wooden cases can be reused/ recycled then please include these in your proposal. | 2023-10-04
43 | Also, is there an ‘in house electrical contractor’ with whom we would interface to agree the adaptions to the existing electrical installation? | We do not have an ‘in-house’ electrical contractor but we are working with external contractors on the upgrade of existing M&E systems, and, within agreed levels, can be available for project advice. Something like that? | 2023-10-04
44 | Do we need a Graphic Designer as part of our team or is 2D design covered entirely by the Brand Design Team. | Ultimately its up to you to decide who's required on your team, but we would envisage that a graphic design is included. | 2023-10-04
45 | What are your internal resources for the project? For instance, are you expecting to make external appointments for graphic artworking, mounts etc? | We do not have any internal resources for the design and fabrication of this project. We are expecting a complete solution from this commission. Mounts are not required. | 2023-10-05
46 | Does the anticipated fee budget include VAT? | Yes, the maximum budget including VAT is £400k. This is to cover the design services and the work itself around the build. | 2023-10-05
47 | Should the build budget cover AV hardware? | Yes, Audio Visual should form part of the build element. | 2023-10-05
48 | Are the existing cases in the gallery compatible with conservation and security requirements? | We would like to retain the Edwardian dark wood, central cabinets, but replace the lightwood cabinets. The central cabinets are to be modified to make them more accessible and currently have adequate safety and display standards. | 2023-10-05
49 | Could we have a definitive list of the disciplines expected to come under the design fee budget? | Please refer to Appendix 2 - Core Team and Volume 1 (Section 2). | 2023-10-05
50 | Are there 2D brand guidelines in place for the overall museum interpretation strategy, and to what extent would these interact with the 2D exhibition design in the gallery? | These are currently being updated and will be available to the successful tenderer. | 2023-10-06
51 | What extent of participation would the 2D designer be expected to have in the branding workshops? | There are no expectations at present, but we would welcome collaboration between the designers. | 2023-10-06
52 | We noticed that Schedule 1 – Price refers to ‘Concept Design (to include feasibility report / Business Plan)’. Could you please provide clarification on whether you require Feasibility and Business Planning services, and if so, specify the expected deliverables? It's worth noting that these services are not mentioned in either Appendix 1 - Design Brief or Appendix 2 - Core Team. | We do not required feasibility and business planning services | 2023-10-06
53 | We're just looking at the timetable and wondered whether the contract end date should include the completion of the reinstallation of the mineral collection in their cases, could you clarify? Should we assume that the museum staff team will install the objects or do we need to allow for our objects display specialist to do that? | Yes the timescale should include the installation of minerals in the cases, and yes the museum team will install the objects. | 2023-10-06
PLEASE NOTE: DEADLINE FOR CLARIFICATIONS IS 6 OCTOBER 2023
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: jackie@jackiegeorge.co.uk