[image: image2.jpg]Department
for Environment
Food & Rural Affairs



www.gov.uk/defra
Invitation to Tender 

Major Waste Reform Consultation Analysis
A Tender to Commission an Analysis of the Responses from the Consultation.
Tender Reference: 31246
November 2020 
Important Notice

All references in this ITT to the Authority include, where appropriate and unless the context otherwise requires, references to the Authority’s predecessors and successor(s).

The Information has been prepared to assist interested parties in deciding whether or not to submit a Response in relation to the procurement. It does not purport to be all-inclusive or to contain all of the information that a Tenderer may require. Any descriptions of existing and proposed contractual arrangements are of a general nature only. Where the Information describes any contractual arrangements which are not yet in force, those arrangements are subject to change. Any reference to a contract or other document is qualified in full by reference to the entire terms of the contract or document to which reference is made.

The issue of this ITT in no way commits the Authority to award the contract to any person or party. The Authority reserves the right to terminate the competition, to award a contract without prior notice, to change the basis, the procedures and the timescales set out or referred to in this ITT, or to reject any or all Responses and to terminate discussions with any or all Tenderers at any time. Nothing in this ITT should be interpreted as a commitment by the Authority to award a Contract to a Tenderer.

The Authority does not make any representation or warranty (express or implied) as to the accuracy, reasonableness or completeness of the Information. All such persons or entities expressly disclaim any and all liability (other than in respect of fraudulent misrepresentation) based on or relating to any such information or representations or warranties (express or implied) contained in, or errors or omissions from, this document or based on or relating to the recipient’s use, or the use by any of its subsidiaries or the respective representatives of any of them, in the course of its or their evaluation of the  service or any other decision. In the absence of express written warranties or representations as referred to below, the Information shall not form the basis of any agreements or arrangements entered into in connection with this procurement.

The Information has been provided in good faith and all reasonable endeavours have been made, and will be made, to inform you of the requirements of the Authority. However, the Information does not purport to be comprehensive or to have been independently verified. You should form your own conclusions about the methods and resources needed to meet these requirements. In particular, neither the Authority nor any of its advisers accept responsibility for representations, writings, negotiations or understandings in connection with this procurement made by the Authority (whether directly or by its agents or representatives), except in respect of any fraudulent misrepresentation made by it. Tenderers are expected to carry out their own checks for verification.

The only information which will have any legal effect and / or upon which any person may rely will be such information (if any) as has been specifically and expressly represented and / or warranted in the Contract or other relevant agreements entered into at the same time as the Contract is entered into or becomes unconditional.

Subject always to the provisions of the preceding paragraph, Tenderers considering entering a contractual relationship with the Authority should make their own investigations and enquiries as to the Authority's requirements beforehand. The subject matter of this ITT shall only have any contractual effect when it is incorporated into the expressed terms of an executed contract.

The issue of this ITT is not to be construed as a commitment by the Authority to enter into a contract as a result of this procurement process. Any expenditure, work or effort undertaken prior to the execution of a Contract is accordingly a matter solely for the commercial judgement of the Tenderer. The Authority reserves the right to withdraw from the  procurement at any time or to re-invite Responses on the same or any alternative basis.

Nothing in this ITT shall constitute legal, financial or tax advice. This ITT is not a recommendation by the Authority, nor any other person, to bid for, enter into or agree to enter into any contract in connection with this  procurement, nor to acquire shares in the capital of any company that is to carry out any part of the service or in any parent company of that company. In considering any investment in the shares of any company or in bidding for the award of the service, each Tenderer, potential contractor, funder and investor should make its own independent assessment and seek its own professional financial, taxation, insurance and legal advice and conduct its own investigations into the opportunity of being awarded a contract in relation to this procurement and of the legal, financial, taxation and other consequences of entering into contractual arrangements in connection with this the  procurement.

This ITT and the Information is confidential.

This ITT is subject to copyright. Neither this ITT, nor the Information, nor any other information supplied in connection with it, may, except with the prior written consent of the Authority, be published, reproduced, copied, distributed or disclosed to any person, nor used for any purpose other than consideration by each Tenderer of whether or not to submit a Response.

The Authority reserves the right at any time to issue further supplementary instructions and updates and amendments to the instructions and Information contained in this ITT as it shall in its absolute discretion think fit.

The Authority will not be responsible for the costs or expenses of any Tenderer in relation to any matter referred to in this ITT howsoever incurred, including the evaluation of the service opportunity, the award, or any proposal for the award of the contract or negotiation of the associated contractual agreements.

Each Tenderer's acceptance of delivery of this ITT constitutes its agreement to and acceptance of the terms set out in this Important Notice.

Table of Contents
	Section
	Contents
	Action

	1
	Tender Particulars
	For Information

	2
	Evaluation
	For Information

	3
	Specification of Requirements
	For Information


	Appendices
	Contents
	Action

	A
	Form of Tender
	Print, Sign, Scan and Upload to Bravo

	B
	Authority’s Conditions of Contract
	For Information

	C
	Not Used
	Not Used

	D
	Armed Forces Corporate Covenant
	For Information

	E
	Not Used
	Not Used


SECTION 1: TENDER PARTICULARS 

GLOSSARY

Unless the context otherwise requires, the following words and expressions used within this Invitation to Tender (except Appendix B: Authority’s Conditions of Contract) have the following meanings (to be interpreted in the singular or plural as the context requires):

	TERM
	MEANING

	“Authority”
	the Department for Environment, Food and Rural Affairs acting as part of the Crown.

	“Bravo”
	the e-Tendering system used by the Authority for conducting this procurement, which can be found at http://defra.bravosolution.co.uk

	“Contract” 
	the contract (set out in Appendix B) to be entered into by the Authority and the successful Tenderer.

	“EIR”
	the Environmental Information Regulations 2004 (as amended) together with any guidance and/or codes of practice issued by the Information Commissioner or any Government Department in relation to those Regulations. 

	“FOIA”
	the Freedom of Information Act 2000 (as amended) and any subordinate legislation made under that Act together with any guidance and/or codes of practice issued by the Information Commissioner or any Government Department in relation to that legislation.

	“Information”
	means the information contained in the ITT or sent with it, and any information which has been made available to the Tenderer by the Authority, its employees, agents or advisers in connection with the [insert name of lot] procurement.

	 “ITT”
	this invitation to tender and all related documents published by the Authority and made available to Tenderers.

	“Pricing Schedule”
	the form accessed via Bravo in which Tenderers are required to submit their pricing information as part of a Tender.

	“Regulations”
	the Public Contracts Regulations 2015.

	“Response”
	means the information submitted in response to the ITT via the online response forms on Bravo including the Tenderer’s formal Tender.

	 “Tender”
	a formal tender in response to this ITT.

	“Tenderer”
	anyone responding to this ITT and, where the context requires, includes a potential tenderer.

	“Timetable”
	the timetable set out in Part 2 of this Section. 


References to a “Section” and to an “Appendix” are references to a section and to an appendix in the ITT. 
Reference to a statute or statutory provision is a reference to such statute or statutory provision as amended or re-enacted. A reference to a statute or statutory provision includes any subordinate legislation made under that statute or statutory provision, as amended or re-enacted.
PART 1: GENERAL

1.1 1.1
The Authorities Environmental Quality Directorate, is looking for suppliers to analysis and report on the responses received from the three Major Waste Reform Consultations undertaken. (Outlined in detail in the specification section 3 in this document). 
1.2
This procurement is being carried out in accordance with the Public Contract Regulations (PCR 2015) ,to develop a contract to commence in December 2020 and conclude in March 2021. 
1.3
The Authority is using Bravo for this procurement which means the ITT and the forms for submitting a Tender are only available in electronic form. It can be accessed via your web browser at http://defra.bravosolution.co.uk. 
1.4
Tenderers are required to submit their Tender in accordance with the instructions set out in Bravo and the ITT.
1.5
The information contained in the ITT is designed to ensure that all Tenders are given equal and fair consideration. It is important that Tenderers provide all the information asked for in the format and order specified so that the Authority can make an informed decision.

1.6
Tenderers should read the ITT carefully before submitting a Tender. It sets out:
•
the Timetable and process for the procurement;

•
sufficient information to allow Tenderers to submit a compliant Tender;

•
award criteria and evaluation criteria which will be used to assess the Tenders; and

•
the administrative arrangements for the receipt of Tenders.

1.7
Tenderers are responsible for ensuring that they understand the requirements for this procurement. If any information is unclear, or it a Tenderer considers that insufficient information has been provided, they should raise a query via the clarification process described in clause 3.13.

1.8 Tenderers are responsible for ensuring they have submitted a complete and accurate Tender and that prices quoted are arithmetically correct for the units stated.

1.9 Failure to comply with the instructions set out in the ITT or the provision of false, inaccurate or misleading information (at any stage of this procurement) may result in the Tenderer’s exclusion from this procurement.
1.10 If there is any conflict between the information set out in the ITT and the information displayed in Bravo, the information in the ITT shall take precedence over the information displayed in Bravo.
1.11 The copyright in the ITT is vested in the Crown and may not be reproduced, copied or stored in any medium without the prior written consent of the Authority, The ITT, and any document issued as a supplement to it, are and shall remain the property of the Crown and must be returned upon demand.

PART 2: PROPOSED TIMETABLE AND ADMINISTRATIVE ARRANGEMENTS 

2.1

The Timetable below is subject to change by the Authority and Tenderers will be informed accordingly.
	Publish advertisement for the procurement
	 
	20th November 2020

	Deadline for clarification questions
	Date
	7th December 2020

	
	Time
	17:00 Hours

	Site visits 
	 
	Not Used

	Deadline for Tenders 
	Date
	14th December 2020

	
	Time
	12:00 Hours

	Evaluation of Tenders 
	Start
	15th December 2020

	
	End
	12th January 2021

	Contract Award Notice
	 
	19th January 2021

	Pre-Award Meeting
	 
	26th January 2021

	Voluntary standstill period
	Start
	N/A

	
	End
	N/A

	Contract award
	 
	26th January 2021

	Contract start date
	 
	26th January 2021

	Transition period 
	 
	N/A

	Service commencement date  
	 
	29th January 2021

	Duration of Contract
	 
	6 Months

	Extension Period  
	 
	N/A


PART 3: COMPLETION OF TENDER

3.1
By submitting a Tender, Tenderers agree:

•
to be bound by the ITT; and

•
that if the Authority accepts the Tender in writing, the Tenderer will execute the Contract in the form set out in Appendix B or in such amended form as may be agreed in writing by the Authority.

3.2
The Authority may terminate or amend the procurement or the ITT at any time.  Any such termination or amendment will be notified in writing to all Tenderers. In order to give Tenderers reasonable time in which to take an amendment into account in preparing their Tenders, the Authority may, at its discretion, extend the deadline for Tenders.

3.3
Unless otherwise stated in the ITT or in writing by the Authority, all communications from Tenderers (including Tenderers’ sub-contractors, consortium members, consultants and advisers) during the procurement must be made using Bravo. The Authority will not respond to communications made by other means and Tenderers should not rely on communications from the Authority unless they are made through Bravo.

Submission of Tenders

3.4
Tenderers must complete all parts of the Tender form in Bravo in accordance with the instructions therein. 

3.5 Tenderers should print off the Form of Tender which must be signed by an authorised signatory. The signed Form of Tender must be uploaded and submitted via Bravo as part of a Tender in accordance with the instructions in Bravo.  

3.6 The Tender and any documents accompanying it must be in English.
3.7 Prices must be submitted in £ Sterling exclusive of VAT.

3.8 Tenders will be checked for completeness and compliance with the requirements of the ITT and only compliant Tenders will be evaluated. 

3.9 Tenderers must be explicit and comprehensive in their Tender as, this will be the single source of information used to score and rank Tenders. The Authority will take into account only information which is specifically asked for in the ITT.

3.10 Where a length of response is stipulated, for example, a word count limit, only the information within the set limit will be evaluated.

3.11 Failure to provide the information required or supply documents referred to in the Tender within the deadline for Tenders may result in rejection of the Tender.

3.12 Tenderers should avoid reference to general marketing or promotional information/material (except where this is specifically required by the relevant question). General marketing or promotional brochures may not be accepted where these are not deemed to be specifically relevant to the question.

3.13 Different persons may be responsible for evaluating different responses to questions in a Tender. Therefore, Tenderers should not cross-refer to answers given elsewhere in a Tender but should answer each question so that it forms a stand-alone response. This may mean Tenderers need to repeat certain information in response to different questions if this is required by those questions.

Clarifications sought by Tenderers

3.13
Any request for clarification regarding the ITT should be submitted at the earliest opportunity via Bravo and in any event no later than the deadline for clarifications set out in the Timetable. The Authority is under no obligation to respond to queries raised after the clarification deadline.

3.14
The Authority will respond to all reasonable clarifications as soon as possible but cannot guarantee a minimum response time. The Authority will publish all clarifications and its responses to all Tenderers other than in exceptional circumstances.

3.15
If a Tenderer believes that a request for clarification is commercially sensitive or that publishing the same together with the Authority’s response as set out above would reveal information, disclosure of which would be detrimental to the Tenderer, it should clearly state this when submitting the clarification request.  However, if the Authority considers either that:
· the clarification and response is not commercially sensitive; and/or
· all Tenderers may benefit from its disclosure,


the Authority will notify the Tenderer of this (via Bravo), and the Tenderer will have an opportunity to withdraw the request for clarification. If the request for clarification is not withdrawn within 48 hours of the Authority’s notification, the Authority may publish the clarification request and its response to all Tenderers and the Authority shall not be liable to the Tenderer for any consequences of such publication.

3.16 The Authority may not respond to a request for clarification or publish it where the Authority considers that the response may prejudice the Authority’s commercial interests. In such circumstances, the Authority will inform the Tenderer of its view.

Changes to Tenders 

3.17
Tenderers may modify their Tenders prior to the deadline for Tenders. No Tenders may be modified after the deadline for Tenders. 

3.18
Tenderers may withdraw their Tenders at any time by submitting a notice via Bravo. Unless withdrawn, Tenders shall remain valid and open to acceptance by the Authority for 120 days from the deadline for Tenders.   

Receipt of Tenders

3.19
Tenders must be uploaded onto Bravo no later than the time and date set out in the Timetable as the deadline for Tenders. The Authority will not consider Tenders received after the deadline. The Authority may, however, at its own discretion, extend the deadline and in such circumstances the Authority will notify all Tenderers of any change.

3.20
If a Tenderer experiences problems when uploading its Tender, it should contact the Bravo helpdesk for assistance and also inform the Authority.  

Acceptance of Tenders

3.21
By issuing the ITT, communicating with a Tenderer or a Tenderer’s representative or agents or any other communication in respect of this procurement, the Authority shall not be bound to accept any Tender or award any contract.

Costs of Tendering

3.22
Tenderers shall bear all their own costs and expenses incurred in the preparation and submission of their Tenders, site visits and presentations and the Authority will in no case be responsible or liable for those costs, regardless of the outcome of the procurement in relation to individual Tenders, even if the procurement is terminated or amended by the Authority.

Clarifications sought by the Authority

3.23
The Authority reserves the right (but is not obliged) to seek clarification of any aspect of a Tender and/or provide additional information during the evaluation phase in order to carry out a fair evaluation. Failure to respond adequately may result in the Tender being rejected.
3.24
Tenderers must give the names of two people in their organisation who can answer the Authority’s clarification questions. The Authority will not contact any other persons. Tenderers must notify the Authority promptly of any changes.
Confidentiality of the ITT and related documents

3.25 The contents of the ITT and of any other documents and information published or provided by the Authority in respect of this procurement are provided on condition that they remain the property of the Authority, are kept confidential (save in so far as they are already in the public domain) and that the Tenderer shall take all necessary precautions to ensure that they remain confidential and are not disclosed, save as described below.

3.26 Tenderers may disclose information relating to the procurement to their advisers and sub-contractors in the following circumstances:
· disclosure is for the purpose of enabling a Tender to be submitted and the recipient of the information undertakes in writing to keep it confidential on the same terms as the Tenderer;
· the Authority gives prior consent in writing to the disclosure;
· the disclosure is made for the purpose of obtaining legal advice in relation to the procurement; or
· the Tenderer is legally required to disclose the information.

3.27 Tenderers shall not undertake any publicity activities in relation to the ITT without the prior written agreement of the Authority, including agreement on the format and content of any publicity.  For example, no statements may be made to the media regarding the nature of any Tender, its contents or any proposals relating to it without the prior written consent of the Authority.
3.28 All Central Government Departments, their Executive Agencies and Non Departmental Public Bodies are subject to control and reporting within Government. In particular, they report to the Cabinet Office and HM Treasury for all expenditure. Further the Cabinet Office has a cross-Government role delivering overall Government policy on public procurement, including ensuring value for money and related aspects of good procurement practice.

3.29 For these purposes, the Authority may disclose within Government any of the Tenderer’s documents and information (including any that the Tenderer considers to be confidential and/or commercially sensitive) provided in its Tender. The information will not be disclosed outside Government during the procurement. Tenderers consent to these terms as part of the procurement.

Confidentiality: References and third party evaluators:

3.30 When providing details of contracts as part of a Tender, Tenderers agree to waive any contractual or other confidentiality rights and obligations associated with these contracts.

3.31 The Authority may contact any named customer contact given as a reference or otherwise referred to as part of a Tender (and including any contacts or references given as part of the Tenderer’s PQQ response). The named customer contact does not owe the Authority any duty of care or have any legal liability, except for any deceitful or maliciously false statements of fact. 

3.32 Subject to clauses 3.35 to 3.39 the Authority confirms that it will keep confidential and will not disclose to any third parties any information obtained from a named customer contact, other than to the Cabinet Office and/or contracting authorities defined by the Regulations.
3.33 The Authority may use third parties in the course of its evaluation of Tenders. The Authority may disclose information contained therein to such third parties for the purposes of the Authority’s evaluation of Tenders in accordance with the ITT. This right shall be in addition to the provisions of clauses 3.28, 3.29 and 3.34 to 3.38.

Commercially sensitive information and Freedom of Information

3.34 In accordance with the obligations placed on public authorities by the FOIA and the EIR, which provide a public right of access to information held by public bodies, the Authority may disclose information submitted to the Authority by the Tenderer.

3.35 If the Tenderer considers any information which it supplies to be commercially sensitive or confidential it should complete the schedule of Commercially Sensitive Information set out in Bravo and:
· clearly identify such information as confidential or commercially sensitive;
· explain the potential implications of disclosure of such information; and
· provide an estimate of the period of time during which the Tenderer believes that such information will remain confidential or commercially sensitive.

3.36 Where a Tenderer identifies information as confidential and/or commercially sensitive, the Authority will endeavour to maintain the confidentiality of that information, and will, where practicable, consult with the Tenderer before information relating to that Tenderer is disclosed pursuant to a request for information under FOIA and/or EIR to establish whether an exemption from disclosure may apply. 
3.37 However, even where information is identified as being confidential or commercially sensitive, there may be circumstances in which the Authority may be required to disclose such information in accordance with the FOIA or the EIR (in addition to any other transparency obligations as set out in clauses 3.29 and 3.30). In particular, the Authority is required to form an independent judgment concerning whether the information is exempt from disclosure under the FOIA or the EIR and whether the public interest favours disclosure or not. Accordingly, the Authority cannot guarantee that any information marked “confidential” or “commercially sensitive” will not be disclosed and accepts no liability for any loss or prejudice caused by the disclosure of information.

3.38 If a Tenderer receives a request for information relating to this procurement under the FOIA or the EIR during the procurement, this should be immediately passed on to the Authority and the Tenderer should not respond to the request without first consulting the Authority.

Disclaimers

3.39
Whilst the information in the ITT and supporting documents have been prepared in good faith the Authority does not warrant that it is comprehensive or that it has been independently verified.

3.40
Neither the Authority nor its respective advisors, directors, officers, members, partners, employees, other staff or agents:

•
makes any representation or warranty (express or implied) as to the accuracy, reasonableness or completeness of the ITT or of any other written or oral communication transmitted (or otherwise made available) to any Tenderer;

•
accepts any liability for the information contained in the ITT or in any other written or oral communication transmitted (or otherwise made available) to any Tenderer, or for the fairness, accuracy or completeness of that information; or

•
shall be liable for any loss or damage (other than in respect of fraudulent misrepresentation) arising as a result of reliance on such information or any subsequent communication.

Any party considering entering into contractual relationships with the Authority following receipt of the ITT should make its own investigations and independent assessment of the Authority and its requirements for the goods and/or services and should seek its own professional financial and legal advice.

3.41
Neither the issue of the ITT nor any of the information presented in it should be regarded as a commitment or representation on the part of the Authority to enter into a contractual arrangement. Nothing in the ITT or in any other communication made between the Authority and any other party should be interpreted as constituting a contract, agreement or representation between the Authority and any other party (save for a formal award of contract made in writing) or as constituting a contract, agreement or representation that a contract shall be offered.

Canvassing

3.42
Any Tenderer which directly or indirectly canvasses any officer, member, employee, or agent of the Authority or its members or any other relevant body or any of its officers or members concerning the Contract or this procurement which directly or indirectly obtains or attempts to obtain information from any such officer, member, employee or agent concerning any other Tenderer or Tender will be excluded from this procurement and its Tender rejected.

3.43
The Tenderer shall not make contact with any employee, agent or consultant of the Authority which is in any way connected with this procurement during this procurement, unless instructed otherwise by the Authority.

Conflicts of Interest

3.44 The concept of a conflict of interest includes any situation where relevant staff members of the Authority, involved in this procurement have, directly or indirectly, a financial, economic or other personal interest which might be perceived to compromise their impartiality and independence in the context of the procurement procedure and/or affect the integrity of the contract award. 

3.45 If the Tenderer is aware of any circumstances giving rise to a conflict of interest or has any indication that a conflict of interest exists or may arise you should inform the Authority of this as soon as possible (whether before or after they have submitted a Tender). Tenderers should remain alert to the possibility of conflicts of interest arising at all stages of the procurement and should update the Authority if any new circumstances or information arises, or there are any changes to information already provided to the Authority. Failure to do so, and/or to properly manage any conflicts of interest may result in a Tender being rejected. 

3.46 Provided that it has been carried out in a transparent manner, routine pre-market engagement carried out by the Authority should not represent a conflict of interest for the Tenderer.
Changes to a Tenderer’s Circumstances

3.47
The Authority may:

•
reject a Tender if there is a subsequent change of identity, control, financial standing which may affect the Authority’s evaluation of the Tender;

•
revisit information contained in a Tender at any time to take account of subsequent changes to a Tenderer’s circumstances; or

•
at any point during the procurement require a Tenderer to certify there has been no material change to information submitted in its Tender and in the absence of such certificate, reject the Tender.

Sub-Contracting
3.48 Where the Tenderer proposes to use one or more sub-contractors to deliver some or all of the contract requirements, all information requested in the Tender should be given in respect of the prime contractor and a separate appendix should be used to provide details of the proposed bidding model that includes:

· members of the supply chain;

· the percentage of work being delivered by each sub-contractor; and

· the key contract deliverables each sub-contractor will be responsible for

3.49 The Authority recognises that arrangements in relation to sub-contracting may be subject to future change, and may not be finalised until a later date. However, Tenderers should note that where information provided to the Authority indicates that sub-contractors are to play a significant role in delivering key contract requirements, any changes to those sub-contracting arrangements may affect the ability of the Tenderer to proceed with the procurement process or to provide the supplies and/or services required. If the proposed supply chain changes at any time after submission of its Tender, the Tenderer should inform the Authority immediately via Bravo. The Authority may deselect the Tenderer prior to any award of contract, based on an assessment of the updated information.
Pricing

3.50
Prices must be submitted in £ Sterling exclusive of VAT.

3.51
The Contract is to be awarded as a fixed price which will be paid according to the deliverables stated in the Specification of Requirements, for Phase 1 (15.0%) and Phase 2 (85.0%) of the total fixed price.

3.52
The Pricing Schedule sets out the minimum level of pricing information required for the Tender. The Authority may request a detailed breakdown of any Tender.

Notification of Award and Standstill

3.53
Not Used
TUPE 

3.54
Tenderers should determine whether or not they believe the Transfer of Undertakings (Protection of Employment) Regulations 2006 (TUPE) applies to this procurement. Notwithstanding this, Tenderers will note that it is the Authority’s view that TUPE is not likely to apply if this procurement results in a contract being awarded, although the Authority is not liable for this opinion. The Authority will wish to satisfy itself that Tenders are responsibly calculated and take full account of any likely TUPE obligations.

3.55
If Tenderers have a contrary view to that of the Authority on the applicability of TUPE they should advise the Authority, giving reasons, prior to the deadline for Tenders.

TUPE Information for submission of a Tender 

Not Required.
PART 4: GOVERNMENT POLICY IN RELATION TO TRANSPARENCY
4.1
Tenderers should be aware that the Government has set out the need for greater transparency in public sector procurement. Tenderers should note that if they are awarded a Contract, the tender documents and Contract will be published on the Contracts Finder website https://www.gov.uk/contracts-finder. In some circumstances, limited redactions may be made to some contracts before they are published.      

PART 5: ARMED FORCES COVENANT

5.1
The Armed Forces Covenant is a public sector pledge from Government, businesses, charities and organisations to demonstrate their support for the armed forces community. The Covenant was brought in under the Armed Forces Act 2011 to recognise that the whole nation has a moral obligation to redress the disadvantages the armed forces community face in comparison to other citizens, and recognise sacrifices made.

5.2
The Covenant’s 2 principles are that:

· the armed forces community should not face disadvantages when compared to other citizens in the provision of public and commercial services; and

· special consideration is appropriate in some cases, especially for those who have given most such as the injured and the bereaved.

The Authority encourages all Tenderers, and their suppliers, to sign the Corporate Covenant, declaring their support for the Armed Forces community by displaying the values and behaviours set out therein.
5.3 

Guidance on the various ways you can demonstrate your support through the Armed Forces Corporate Covenant is provided in Appendix D.

5.4 
If you wish to register your support you can provide a point of contact for your company on this issue to the Armed Forces Covenant Team at the address below, so that the MOD can alert you to any events or initiatives in which you may wish to participate. The Covenant Team can also provide any information you require in addition to that included on the website.

Email address: covenant-mailbox@mod.uk

Address: Armed Forces Covenant Team

Zone D, 6th Floor, Ministry of Defence,

Main Building, Whitehall, London, SW1A 2HB

5.5 
Paragraphs 5.1 – 5.4 above are not a condition of working with the Authority now or in the future, nor will this issue form any part of the tender evaluation, contract award procedure or any resulting contract. However, the Authority very much hopes you will want to provide your support.
SECTION 2: EVALUATION
Evaluation comprises the stages set out in the table below. More information on evaluation criteria is set out in Bravo 

	Stage
	Section Reference
	Evaluation Criteria
	Question Scoring/ Weighting (%)

	Stage 1 
	Form of Tender
	This stage is not scored but if you do not upload a complete, signed and dated Form of Tender in accordance with the instructions in Bravo, your Tender will be rejected as non-compliant.


	Pass/Fail

	Stage 2


	Organisation and Contact Details
	This stage is not scored but you will be eliminated from the procurement if the information is not provided in full.
	Pass/Fail 

	Stage 3
	Grounds for Mandatory Rejection 
	This stage is not scored but if you answer “Yes” to any of the questions the Authority will reject your Tender.
	Pass/Fail. 



	Stage 4
	Grounds for Discretionary Rejection
	This stage is not scored but if you answer “Yes” to any of the questions the Authority may reject your Tender.
	Pass/Fail. 



	Stage 5


	Financial & Economic Standing 


	This stage is not scored but you may be eliminated from the procurement if the Authority believes your organisation does not have the financial resources to provide the goods/services required.
	Pass/Fail 



	Stage 6


	Past Performance 
	This stage is not scored but you may be eliminated from the procurement if the information is not provided in full or if your past performance has not been satisfactory.


	Pass/Fail

	Stage 7


	Technical & Professional Ability – Project Specific Requirements) (Technical Questionnaire) 
	This stage will be evaluated in accordance with the criteria set out in the Technical Questionnaire. 

Some requirements are mandatory and if you cannot provide them your Tender may be rejected.


	Score Pass/Fail

	Stage 8
	Site Visits
	This stage will be evaluated in accordance with the criteria set out in the Technical Questionnaire. 


	N/A

	Stage 9
	Interview/Presentations
	This stage will be evaluated in accordance with the criteria set out in the Technical Questionnaire. 


	N/A

	Stage 10
	Pricing Schedule
	Prices will be evaluated in accordance with criteria set out in the Pricing Schedule.

	Scored


	Stage 11
	Final score 
	If you pass stages 1 to 6 your Tender will be evaluated in stages 7 to 10 

The final score is calculated as follows:  

70.0% is made up of the total of Stage 7

30.0% is made up from Stage 10 

The most economically advantageous Tender will be the Tender with the highest final score.


1.1
Tenders will be evaluated on quality and price using the evaluation criteria set out in Bravo to determine which Tender is the most economically advantageous. The Authority will award the Contract to the Tenderer which submits the most economically advantageous tender which will be the highest scoring Tender after the weightings in clause 1.3 are applied.    

1.2
Each question will be scored separately and no reference will be made between the questions.  

1.3
To ensure that the relative importance of both sets of criteria is correctly reflected in the overall score, a weighting system will be applied to the evaluation:  

· the total quality scores awarded will form 70.0% of the final score;
· The score awarded for price will form 30.0% of the final score.

1.4
Each scoring question in the quality evaluation is given a weighting to indicate the relative importance of that question in the overall quality score. Weightings for quality scores are provided with the evaluation criteria and are detailed on Bravo for each question in the response form. The evaluation criteria for price are set out in the Pricing Schedule.
1.5
Evaluation of Tenders will be undertaken by a panel appointed by the Authority. Each panel member will first undertake an independent evaluation of the Tenders applying the relevant evaluation criteria for each question. Then, a moderation meeting will be held at which the evaluation panel will reach a consensus on the marking of each question.
	Score
	Justification

	For a score of hundred (100):  
	Excellent - Response is completely relevant and excellent overall.  The response is comprehensive, unambiguous and demonstrates a thorough understanding of the requirement and provides details of how the requirement will be met in full.

	For a score of seventy (70):  
	Good - Response is relevant and good.  The response demonstrates a good understanding and provides details on how the requirements will be fulfilled. 

	For a score of fifty (50):  
	Acceptable - Response is relevant and acceptable.  The response provides sufficient evidence to fulfil basic requirements.

	For a score of twenty (20):  
	Poor - Response is partially relevant and/or poor.  The response addresses some elements of the requirements but contains insufficient / limited detail or explanation to demonstrate how the requirement will be fulfilled.

	For a score of zero (0):  
	Unacceptable - Nil or inadequate response.  Fails to demonstrate an ability to meet the requirement.


Weighting 

1.6      The weighting and maximum marks available for the price will be 30% and will be awarded to the Tenderer with the lowest tender price. The remaining Tenderers will receive marks on a pro rata basis from the lowest to the highest price. The calculation used is the following:

Score = Lowest Tender Price x 30 (Maximum available marks)

               Tender Price    


For example, if three tender responses are received and Tenderer A has quoted £30,000 as their total price, Tenderer B has quoted £50,000 and Tenderer C has quoted £60,000 then the calculation will be as follows:

· Tenderer A Score = £30,000/£30,000 x 30% (Maximum available marks) = 30% 

· Tenderer B Score = £30,000/£50,000 x 30% = 18% 

· Tenderer C Score = £30,000/£60,000 x 30% = 15%
1.7    The weighting and maximum marks available for the quality will be 70.0% and will be awarded to the Tenderer with the highest overall score. The remaining Tenderers will receive marks on a pro rata basis from the highest to the lowest score. The calculation used is the following:

            Marks = Quality Score x 70.0 % (Maximum available marks)

                           Highest Quality Score    

           For example, if three Tender Responses are received and Tenderer A has a total weighted quality score of 75, Tenderer B has a score of 70, and Tenderer C has a score of 60, then the calculation will be as follows: 

· Tenderer A Score = 75.0/75.0 x 70.0 % (Maximum available marks) = 70.0%

· Tenderer B Score = 70.0/75.0 x 70.0 % (Maximum available marks) = 65.33%

· Tenderer C Score = 60.0/75.0 x 70.0 % (Maximum available marks) = 56.0%

Site visits 

1.8
Not Used.

Interviews/Presentations 

1.9
Not Used.

SECTION 3: SPECIFICATION OF REQUIREMENTS
This Section sets out the Authority’s requirements.
Specification for the major waste reforms consultation analysis 

Background:
The UK Government (in conjunction with the Devolved Administrations for EPR and DRS) will be launching a second consultation on three major waste reforms (extended producer responsibility for packaging, a deposit return scheme for drinks containers, and consistent recycling collections) in early 2021. We wish to commission an analysis of the responses to these three consultations. 

Each consultation features questions directly related to final policy proposals and so responses need to be analysed within a tight timeframe to ensure a government response for each is published quickly and implementation timelines are met. 
Consultants with capacity to undertake this project should submit a tender application to undertake the analysis of all three consultation responses, and produce separate reports summarising the findings for each, as set out below. 
Details of each consultation:
Extended Producer Responsibility for packaging:

In 2019, the UK Government together with the devolved administrations published a consultation on proposed changes to the UK producer responsibility regime for packaging. This proposal included setting out objectives and mechanisms to incentivise better packaging design, encourage the use of recyclable materials and ensure that producers pay the full net costs of managing the packaging they place on the market, once it becomes waste. There was strong support for the introduction of an extended producer responsibility (EPR) scheme which embraces the polluter pays principal. Government committed to introduce packaging EPR following a further consultation. This second consultation will focus on specific policy proposals, including the scope of full net costs, producer obligations, scheme governance, regulation of the scheme, and recycling targets. 
The previous consultation can be found here:

https://consult.defra.gov.uk/environmental-quality/resource-and-waste-and-plastic-packaging-tax-consu-1/supporting_documents/packagingeprconsultdoc.pdf
The analysis of responses to the previous consultation can be found here: https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/819467/epr-consult-sum-resp.pdf 
Deposit Return Scheme for drinks containers:
In 2019 we launched a first consultation on introducing a Deposit Return Scheme (DRS) for drinks containers in England, Wales and Northern Ireland. There was overwhelming support for the introduction of the scheme and we have therefore pressed ahead with developing the proposed policy which will form the basis of our DRS. Introducing a DRS will see a refundable deposit added to the price of an in-scope container, which people can reclaim when they return their empty drinks containers to a return point. This will help to increase recycling of plastic bottles and reduce littering, by incentivising the return of containers in good condition to then be reprocessed. This consultation will set out our final policy positions in greater detail, and include chapters on Scheme Governance, Scope, Targets, Financial Flows, Return Points, Labelling, Local Authorities, and Enforcement.
The previous consultation can be found here: https://consult.defra.gov.uk/environment/introducing-a-deposit-return-scheme/ 
The analysis of responses to the previous consultation can be found here: https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/826853/drs-consult-sum-resp1.pdf 
Consistent Recycling Collections: 

We consulted in 2019 on the principles of increasing the consistency of materials collected for recycling from households, businesses and other organisations in England. There was support for the introduction of a core set of materials to be collected by waste collection authorities from households (plastic; paper and card; glass; metal; food waste and garden waste) and this statutory requirement is being legislated for in the Environment Bill. Businesses and other organisations will also be required to arrange for the collection of the same core set of materials for recycling, with the exception of garden waste. This second consultation will ask more detailed policy questions including on the materials in scope, statutory and non-statutory guidance for local authorities, and exemptions to the requirements introduced through the Environment Bill. 

The previous consultation document can be found here: 

https://consult.defra.gov.uk/environmental-quality/consultation-on-consistency-in-household-and-busin/supporting_documents/recycleconsistencyconsultdoc.pdf
The analysis of the responses to the previous consultation can be found here: 
Public: https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/819779/consistent-recycling-consult-part1a.pdf 
Business:
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/819780/consistent-recycling-consult-part2.pdf 
For recycling consistency, we published one consultation document at first consultation, but are considering publishing two consultation documents this time, to minimise responses from householders on business waste and ensure that respondents answer the relevant parts of the consultation which was an issue at first consultation. This would require producing two summary documents for recycling consistency. A final decision on this has not been made as we are finalising proposals. This can be confirmed at the pre-commencement meeting or earlier if appropriate. 
Budget:
There is up to around £120,000 in total available for the analysis of the responses to the three consultations and preparation of a summary of responses report for each, excluding VAT, and value for money will be a key criterion in assessing the bids.
The project will be split into two phases, one in the current financial year (2020/2021), and the second in the next financial year (2021/2022). This two-phased approach applies to all three consultations which will be conducted simultaneously, with phase one focused on planning, and phase two where the analysis is carried out and the reports produced. 

More detail of the tasks to be undertaken in each phase are detailed in the table below.

Project Purpose and objectives:
The overall purpose of this project is to analyse the responses to each of the three major reform consultations and use this data to produce consultation response summary documents, which will summarise the responses received, bringing out the key findings, and which will inform the Government’s next steps and intentions when implementing these reforms. 
The objectives of the analysis are to:

1. Identify, and quantify the frequency of, main themes in response to each question within the consultation documents for each major reform. The aim of these consultations is to receive clear feedback and preferences for the specific policy proposals put forward.  

2. Identify the views expressed by different types of respondent. The analysis will cover both public (individual) and organisational (businesses, local authorities, NGOs and representative organisations etc.) responses. Analysis should enable us to understand and compare the motivations of each group. The nature of the consultation means that responses from stakeholders with detailed knowledge and experience of each area are of particular interest to us, and therefore the analysis should pay particular attention to these stakeholders. It should also identify whether there are particular differences in the views of key stakeholders in the devolved administrations in the EPR and DRS consultations (this information is not required for consistency). Further context about key stakeholders will be provided to the successful bidder. 

3. Identify evidence submitted by respondents to inform our understanding of the costs and benefits of the proposals.
Expected number of responses for each consultation:

Due to the public nature of these consultations, it is difficult to predict the number of responses that will be received. In the previous consultations we received the following number of responses to each:
· Extended Producer Responsibility: We received 679 responses to the consultation launched in February 2019

· Deposit Return Scheme: We received 1,180 responses to the consultation launched in February 2019, alongside 207,089 campaign responses. The campaign responses were collated by the organisation running the campaign and so consultants would not be expected to analyse these in detail but would be required to summarise the responses.

· Consistency in recycling collections: We received 1,713 responses to the consultation launched in February 2019

All three of these consultations ran for 12 weeks. The new consultations will run for the same length of time so we would expect a similar number of responses. 
We will want consultants to submit their application to tender on the assumption that the total number of consultation responses to be analysed across all three consultations will be 4,500. 

Consultants are asked to provide their commercial rate for analysis of batches of 50 additional responses, in their application to tender. This is in the event that the number of responses received across all three consultations exceeds 4,500.
Receipt of responses:
The three consultations will be published on Citizen Space, an online consultation platform where the majority of responses will be submitted. We will also publish the consultations on the gov.uk website, with the option to submit responses via email (although Citizen Space is the preferred response option). The number of email responses received for the previous consultations are listed below. 
Extended Producer Responsibility – 200 responses via email (just under 1/3 of the total number of responses)

Deposit Return Scheme – 387 responses via email (of 1180 total). 

Consistent Recycling Collections – approx. 150 responses via email (of 1713 total). These were mainly from organisations. 
Defra will access the responses to the three consultations on the Citizen Space platform and provide these to the consultant in an excel spreadsheet format at weekly intervals from the beginning of phase 2 to allow qualitative analysis to begin before the closing date of each consultation. The citizen space platform also has some automated functionality that could help in making broad initial calculations on the responses received to individual questions if appropriate. The email responses will also be collated and sent to the consultants as they are received. 

It is possible that campaign organisations may also respond to these consultations, which will increase the number of responses (as demonstrated by the previous DRS consultation). The organisation running the campaign will take responsibility for collating the responses received as a result of their campaign and providing a summary to Defra. Should this happen, the consultant will need to include the details of this summary in the analysis of the responses, and in the final report. However, they will not be required to analyse campaign responses individually. 

The consultant will need to have capacity to analyse the responses submitted via Citizen Space and those submitted via email, which are likely to contain more ‘free text’ answers and may not necessarily follow the same format as the Citizen Space questions. However, we will be directing people to citizen space via an automated email response to reduce the number of email responses and free text answers where possible.

We will want consultants to submit their application to tender on the assumption that the number of email responses they will be expected to analyse will be up to 20% of total responses (estimated from previous levels). Consultants are asked to include the commercial rate for analysis per 20 additional responses received by email above the 20%.

Type of analysis needed: 

The analysis will involve a combination of reading written responses, qualitative text analysis, response coding in Microsoft Excel, data cleansing and rudimentary statistical analysis to provide insight from the consultation responses. The consultant will be required to analyse multiple choice answers as well as any supporting evidence provided in the open text field for each question or provided by email. Graphs and other data presentation tools should also be used to help clearly present the responses provided.

Due to tight implementation timelines we are procuring for response analysis before all three consultations are fully drafted. We are unable to say at this stage how many questions will need to be analysed within each consultation document. The previous consultation documents give you an idea of the number of questions asked last time. There is an aspiration to reduce the number of questions asked during the next consultations and the number of open text questions where possible. 
We are assuming each of the consultations will have the following number of maximum questions to analyse with the additional assumption that less than 50% of those will be free text questions (based on the number of questions in the previous consultation and the desire to reduce the number of free text responses):
Extended Producer Responsibility: 100

Deposit Return Scheme: 77

Consistency in recycling collections:  66

The questions will be broken down into the following question types, similar to those in the previous consultation documents:

· ‘Yes/no’ questions with a third option which is usually ‘neither’ or ‘don’t know’. These questions are in a single answer multiple choice format. 

· Questions which ask the respondent to choose between a number of options. These are also in single answer multiple choice format.

· Free text questions with no multiple-choice components. As previously mentioned, we hope to keep these types of questions to a minimum across all three consultations, as we are looking for clear steers on the proposed policy options in each consultation. 

Defra will update the consultants on the question numbers and details as this becomes available during the finalisation of the consultation documents, up until the tender clarification deadline (see procurement timeline in ITT).  
Phases, milestones, deliverables, and timelines:
The Deposit Return Scheme Consultation is due to be launched in February 2021, with the Extended Producer Responsibility consultation and the Consistency consultation launching in March 2021. All three consultations will run for 12 weeks. Response analysis and the development of summary documents are expected to be finalised and approved within 6 weeks of each of the consultations closing in order to meet public consultation requirements and deadlines.  

The following table sets out the phases and timelines for the project, along with key milestones to be met, deliverables to be produced and meetings to be held. Phase 1 will involve developing plans for the three consultation response analyses. Phase 2 will involve undertaking the response analyses and developing the summary response documents in accordance with the project aims and objectives set out above. Phase 2 will commence on the receipt and approval of the Phase 1 project plans and the confirmation of Phase 2 funding availability.

Please note, there will be work across all three consultations occurring simultaneously, so it is important that the consultant has adequate resource to meet the required timeframes for all three consultations.
	Date 
	Milestone 
	Deliverables
	Notes

	Phase 1: January – March 2021 

Project plans 

	end of January 2021
	Pre-commencement meeting 
	Pre-commencement meeting minutes detailing discussion, actions, contract management decisions, etc.
	Consultation documents should be able to be provided to consultants in advance of this meeting. Please note the documents would remain confidential until publication.

	January – March 2021
	Consultants to familiarise themselves with the consultation documents.  
	
	Any questions to be provided to the policy leads to look to answer where possible.

	
	Consultation response analysis plans developed
	Consultants to develop response analysis project plans for each of the three consultations and obtain agreement from Defra.
	These project plans will need to detail how the consultants plan to analyse the three consultations simultaneously having reviewed the consultation documents and questions. It should detail what format the response summary documents will take, providing examples of where or how data analysis and presentation tools may be used. 

	February 2021
	DRS consultation launched 
	
	This will run for 12 weeks. Consultation to close in May 2021. Launch date to be confirmed.

	Early March 2021
	EPR and Consistency consultations launched 
	
	These will both run for 12 weeks. Consultation to close in late May 2021. Launch date to be confirmed.

	Phase 2: April 2021 - August 2021

Analysis phase 

	April – June 2021
	Analysis of all three consultations in accordance with project plans. 
	Fortnightly meetings with project manager to check in on progress against project plans, provision of initial analysis updates and support provided by project team as required
	Defra to provide consultant with respondent data to begin analysis whilst consultations remain live.

	May 2021
	DRS consultation closes
	
	

	DRS

May 2021 – June 2021

(3 weeks)
	Analysis and draft DRS response summary report
	Consultants to produce for Defra approval:

· An initial draft summary of responses, to be reviewed and discussed with Defra before producing the final summary document.

· A register of responses which highlights ‘key evidence gaps’ noted by respondents or responses that could not be satisfactorily coded. 
	Interim meetings with DRS policy lead to occur within this timeframe to answer any questions and ensure that the report being produced fits the requirements. A meeting will be held once Defra have reviewed the draft, in order to provide feedback and ask questions.

To note – whilst producing the final DRS summary, analysis of the responses to the other two consultations will have to continue s, as these will still be live. 

	DRS 

June 2021 

(2 weeks)
	Final DRS response summary report 
	A concise final summary of the responses to the DRS consultation which meets the aims listed above and includes a concise summary for each of the questions in the DRS consultation.
	All data and evidence that supports the response summary report and its findings will also be provided to Defra. 

	End of May 2021
	EPR and Consistency consultations close
	
	

	EPR

End of May – mid-June 2021

(3 weeks)
	Analysis and draft EPR response summary report
	Consultants to produce for Defra approval:

· An initial draft summary of the EPR responses, to be reviewed and discussed with Defra before producing the final summary document.

· A register of responses which addresses ‘key evidence gaps’ or responses that could not be satisfactorily coded.
	Interim meetings with EPR/Consistency policy lead to occur within this timeframe to answer any questions and ensure that the reports being produced fit the requirements

To note – the production of these final reports for the EPR consultation and Consistency consultation will need to happen simultaneously.

All data and evidence that supports the response summary reports and their findings will also be provided to Defra.

Note, two consistency response summary documents may need to be produced as detailed above.



	EPR

Mid-June – start of July2021

(2 weeks)
	Final EPR response summary report
	· A concise final summary of the responses to the EPR consultation which meets the aims listed above and includes a concise summary for each of the questions in the EPR consultation.


	

	Consistency

End of May– mid-June 2021

(3 weeks)
	Analysis and draft Consistency response summary report/s
	Consultants to produce for Defra approval:

· An initial draft summary of consistency responses, to be reviewed and discussed with Defra before producing the final summary document.

· A register of responses which addresses ‘key evidence gaps’ or responses that could not be satisfactorily coded.
	

	Consistency

Mid-June– start of July 2021

(2 weeks)
	Final Consistency response summary report/s
	A concise final summary of the responses to the consistency consultation which meets the aims listed above and includes a concise summary for each of the questions in the consistency consultation document/s.
	


Document format and quality:

Both the initial draft response summaries and the final response summaries are to be produced in a Word document format. A register of responses (and respondents) which address key evidence gaps or responses that could not be satisfactorily coded should be provided in an Excel spreadsheet. Any supporting data or evidence that was used to present the summary of responses to the questions or to produce the graphs and information presentation tools should be provided separately to the reports. These should be provided in Excel spreadsheet format. Other format suggestions may be suggested by the tenderers but would need to be agreed by the project lead. 
The quality of the documents produced must be publishable – this means they have been quality assured and proof read for any typographical errors, are jargon-free, clear, and written in plain English with any figures clearly labelled so members of public can understand what they represent. The draft documents should highlight all the key findings and structure the findings in a way that relates them to the key questions.
Project governance and contract management 

Tenderers should put forward an experienced project team to manage and implement the proposed analysis. As part of this, it is expected that Tenderers will identify specific individual(s) as the main point(s) of contact with the Defra project lead based in the Environmental Quality (EQ) Directorate, and appropriate channels for escalating concerns as necessary.  
The contract will be managed by the Defra project lead based in the EQ Directorate who will be the main point of contact for the consultants. However, consultants will also be expected to work closely with consultation implementation leads in each of the three major waste reform teams. At least fortnightly contact is expected between the Defra project lead and the successful bidder.
Defra has established a Consultation Implementation Group consisting of the consultation implementation leads from the three major waste reform teams and other advisors and analysts from across Defra who are involved in delivering public consultations. It is possible that this group will attend key progress meetings outlined in the deliverables above. Further details of this group will be provided at the pre-commencement meeting.
The successful Tenderer will be required to provide project updates for any meetings as necessary. As mentioned in the table above, project meetings will be held fortnightly with the project team and consultants to check in on progress against the timeline, project plans, budget and deliverables. The meeting schedule and agenda will be agreed at the pre-commencement meeting. Covid-19 guidelines may also necessitate that this group meets virtually, with the platform to be agreed. Minutes will be taken and will capture actions and key discussion points from the monthly meetings. 

The below table sets out the breakdown of payment points when meeting key milestones within this project: 
	
	Payment points (dates to be confirmed)
	Description of milestone/deliverable
	Payment %

	Phase 1

	1
	25/01/21
	Pre-commencement meeting 
	5.00%

	2
	19/03/21
	Approval of project plans for the analysis of 3 consultations, 2 monthly meetings held 
	10.0%

	Phase 2

	3
	07/05/21
	2 monthly meetings held to discuss the analysis of responses to the 3 consultations 
	10.0%

	4
	28/005/21
	Draft DRS response summary provided, and monthly meeting held to discuss draft summary and obtain an update on the EPR and consistency analysis
	15.0%

	5
	25/06/21
	Final DRS summary response documents of publishable quality, provided. Draft EPR and consistency documents provided. Monthly meeting held to discuss and approve DRS final summary report, and review and discuss EPR and consistency draft summary documents. Payment made on approval of DRS final response summary documents.
	30.0%

	6
	09/07/21
	Final EPR and Consistency response summaries of publishable quality provided, and monthly meeting held to discuss and approve documents and agree final payment
	30.0%


Travel and Subsistence

All Travel and Subsistence should be in line with Defra’s Travel and Subsistence Policy. Claims should always be supported by valid receipts for audit purposes and must not exceed any of the stated rates below. Should the stated rated be exceeded, Defra reserve the right to reimburse only up to the stated rate. 

Rail Travel

All Journeys – Standard class rail unless a clear business case demonstrating value for money can be presented. This includes international rail journeys by Eurostar and other international and overseas rail operators.

Mileage Allowance

	Mileage Allowance
	First 10,000 business miles in the tax year
	Each business mile over 10,000 in the tax year

	Private cars and vans – no public transport rate*
	45p
	25p

	Private cars and vans – public transport rate
	25p
	25p

	Private motor cycles
	24p
	24p

	Passenger supplement
	5p
	5p

	Equipment supplement**
	3p
	3p

	Bicycle
	20p
	20p


*NB the ‘no public transport rate’ for car and van travel can only be claimed where the use of a private vehicle for the journey is essential e.g. on grounds of disability or where there is no practical public transport alternative. If the use of the vehicle is not essential the ‘public transport rate’ should be claimed.

** Under HMRC rules this expense is taxable.

UK Subsistence
	Location
	Rate (Upper Limit)

	London (Bed and Breakfast)
	£130

	UK Other (Bed and Breakfast)
	£75

	Rates for specific cities (bed and breakfast) 


	Bristol £100 per night 

Weybridge £100 per night 

Warrington £90 per night 
Reading £85 per night


APPENDIX A

FORM OF TENDER

To be returned by 12:00 (UK time) on 14th December 2020.
Mark Chamberlain 

Procurement Advisor

Department for Environment, Food and Rural Affairs

Procurement and Commercial Function
Nobel House / Foss House

17 Smith Square / Kings Pool, 1-2 Peasholme Green

London, SW1P 3JR / York, YO1 7PX

TENDER FOR THE: Major Waste Reform Consultation Analysis.  

Tender Ref: 31246

1. We have examined the invitation to tender and its schedules set out below (the ITT) and do hereby offer to provide the goods and/or services specified in the ITT and in accordance with the attached documents to the Authority commencing 29th January 2021 for the period specified in the ITT.

· Tender Particulars (Section 1)

· Specification of Requirements (Section 3)
· Form of Tender (Appendix A)
· Authority’s Conditions of Contract (Appendix B)

2. If this tender is accepted, we will execute the Contract and any other documents required by the Authority within 10 days of being asked to do so.

3. We agree that:

a. before executing the Contract substantially in the form set out in the ITT, the formal acceptance of this tender in writing by this Authority or such parts as may be specified, together with the documents attached shall comprise a binding contract between the Authority and us;
b. pursuant to EU Directive 1999/93/EC (Community Framework for Electronic Signatures) and the Electronic Communications Act 2000, the Contract may be executed electronically using the Authority’s electronic tendering and contract management system, Bravo;
c. we are legally bound to comply with the confidentiality provisions set out in the ITT;

d. any other terms or conditions or any general reservation which may be provided in any correspondence sent by the Authority in connection with this procurement shall not form part of this tender without the prior written consent of the Authority;
e. this tender shall remain valid for 120 days from the closing date for tenders specified in the ITT; and
f. the Authority may disclose our information and documents (submitted to the Authority during the procurement) more widely within Government for the purpose of ensuring effective cross-Government procurement processes, including value for money and related purposes.
4.
We confirm that:

a. there are no circumstances affecting our organisation which could give rise to an actual or potential conflict of interest that would affect the integrity of the Authority’s decision making in relation to the award of the Contract; or

b. if there are, or may be such circumstances giving rise to an actual or potential conflict of interest we have disclosed this in full to the Authority.
5.
We undertake and it shall be a condition of the Contract that:

a. the amount of our tender has not been calculated by agreement or arrangement with any person other than the Authority and that the amount of our tender has not been communicated to any person until after the closing date for the submission of tenders and in any event not without the consent of the Authority;

b. we have not canvassed and will not, before the evaluation process, canvass or solicit any member or officer, employee or agent of the Authority or other contracting authority in connection with the award of the Contract and that no person employed by us has done or will do any such act; and

c. made arrangements with any other party about whether or not they may submit a tender except for the purposes of forming a joint venture.
6.
I warrant that I am authorised to sign this tender and confirm that we have complied with all the requirements of the ITT. 

Signed

_____________________________________________________________

Date


_____________________________________________________________

In the capacity of
_____________________________________________________________

Authorised to sign 

Tender for and on 

behalf of

_____________________________________________________________

Postal Address
_____________________________________________________________

Post Code

_____________________________________________________________

Telephone No.
_____________________________________________________________

Email Address
_____________________________________________________________

APPENDIX B

AUTHORITY’S CONDITIONS OF CONTRACT

[image: image1.wmf] 
APPENDIX D
ARMED FORCES CORPORATE COVENANT
Section 1: Principles of the Armed Forces Covenant
We Company XYZ will endeavour in our business dealings to uphold the key principles of the

Armed Forces Covenant, which are:

· no member of the Armed Forces Community should face disadvantage in the provision of public and commercial services compared to any other citizen;

· in some circumstances special treatment may be appropriate especially for the injured or bereaved.

Section 2: Demonstrating our Commitment
Company XYZ recognises the value serving personnel, reservists, veterans and military families bring to our business. We (Company XYZ) will seek to uphold the principles of the Armed Forces Covenant, by:

· promoting the fact that we are an armed forces-friendly organisation;
· seeking to support the employment of veterans young and old and working with the Career Transition Partnership (CTP), in order to establish a tailored employment pathway for Service Leavers;

· striving to support the employment of Service spouses and partners;
· endeavouring to offer a degree of flexibility in granting leave for Service spouses and partners before, during and after a partner’s deployment;

· seeking to support our employees who choose to be members of the Reserve forces, including by accommodating their training and deployment where possible;

· offering support to our local cadet units, either in our local community or in local schools, where possible;

· aiming to actively participate in Armed Forces Day;
· offering a discount to members of the Armed Forces Community;
· any additional commitments XYZ could make (based on local circumstances).

You are encouraged to sign up to as many of the above as appropriate to your business. 

We will publicise these commitments through our literature and/or on our website, setting out how we will seek to honour them and inviting feedback from the Service community and our customers on how we are doing. Amended as appropriate for your business.
February 2016
Page 35

_1663576392.unknown

