## HoYEG Castleford Campus
CDM Rolling Risk Register
| Client: HoYEG (Wakefield College) |  | Prepared by: Curtins PD | Principal Supply Chain Partner (PSCP): N/A |  |  | Copies to: Client - HoYEG, Lead Designer - Mace, Principal Contractor - Code BS Ltd Originator Codes: TBC
| Project: Summer Works - Castleford Campus |  | Date: | Principal Designer: Curtins Consulting
| Location: Wakefield College, Castleford Campus, WF10 4UA |  | Checked by: | Lead Designer: Mace
| Project No: 081946 |  | Date: | Version: 01
| Originator Risk Ref. / Revision | Building Element / Activity | Hazard Identification | Initial Risk Level | Designer Comments / Design Control Measures including references where applicable | Has the Risk been eliminated? | Stage Required | Owner (Manager who is the current Risk Owner plus other external joint owner) | Impact (0-5)) | Likelihood (0-5) | Residual Risk Rating (0-25) | Action Required to Mitigate Risk | Final Status (This should include Isolation / Control / Protection Measures & any workforce discipline required) | Date Registered | Date Resolved | Is risk reduced sufficiently to allow work to start? | Has this been passed to the supply chain? | Client Pre-Construction Information | H&S File
| CUR-001 | Client Duties - General | Compliance with the Construction (Design and Management) Regulations 2015 | Medium | Meeting with the Client to be arranged to discuss roles and responsibilities and arrangements for inclusion within the Pre-Construction Information. | No | Pre Construction | HoYEG Curtins PD | 3 | 1 | 3 | Curtins CDM Client duties letter to be issued. Curtins PD are to inform HoYEG of their duties as Client under the Construction (Design and Management) Regulations 2015. |  | 2023-05-15 | On-going | No | N/A | N/A | N/A
| CUR-002 | Radcliffe Building - Asbestos | Contact with asbestos containing materials (ACMs) | High | Scope of works does allow for interface with areas which contain ACMs | No | Pre Construction | HoYEG All Designers Principal Contractor | 4 | 4 | 16 | Principal designer requested Pre-Construction Information to be shared by the client. This is following on from the client confirming they have already issued a PCI pack. Curtins PD appointed late into the project at the point of the construction phase begining. Principal contractor confirmed that they have commissioned an R&D Survey to be undertaken prior to construction work commencing and the areas containing asbestos are to be removed. Clients asbestos management plan / register is to be updated to reflect the areas of abestos which have been remediated. | Castleford Campus is that of a new build construction (circa 2008) and as such did not use asbestos containing materials within it's construction. | 2023-05-15 | Closed | No | Yes | Yes | N/A
| CUR-003 | Castleford Campus - Existing estate information | Uknowns and assumptions of residual risks within the Radcliffe Building | High | Existing H&S File and O&M Manual to be provided to the design team and principal Contractor. | No | Pre Construction | HoYEG All Designers Principal Contractor | 4 | 4 | 16 | Pre-construction Information provided by the client. Assuming this is minus existing estate information i.e., exsiting H&S File & O&M Manual. Client to provide the above for review. |  | 2023-05-15 | On-Going | No | Yes | Yes | Required
| CUR-004 | Design Risk Information | Design Risk Review | High | Design risk information requested from the design team by the PD. | No | Pre Construction | All Designers | 4 | 3 | 12 | Design risk information to be provided to allow for a review of associated risks. Project team meetings have been ongoing thoughout the project on site. |  | 2023-05-15 | On-Going | Yes | Yes | Yes | Required
| CUR-005 | Access, Cleaning and Maintenance | Strategy to be provided for review | High | Access, cleaning and maintenance strategies required from the designer required and to be proportionate to the project. | Yes | Post Construction | All Designers | 3 | 3 | 9 | Architect to develop initial safe access and maintenance strategy for the building elements newly built for review with the project team. Discussions with the client team and estate team to further develop the staregy prior to implementation. |  | 2023-05-15 | On-Going | Yes | No | Yes | Required
s

## Sheet2
Pre Construction | Low | Yes | Required
Construction Phase | Medium | No | N/A
Post Construction | High
Design Stage