# YORWASTE LIMITED

# RESTORATION & AFTERCARE PROJECTS, 2017

# Y1622, HAREWOOD WHIN, PHASE 12 WEST AND PHASES 12 & 13 SOUTH EAST RESTORATION

# Y1622, HAREWOOD WHIN, PHASE 12 SOILING

CONDITIONS OF CONTRACT

NEC3 ECC OPTION C:

TARGET CONTRACT WITH ACTIVITY SCHEDULE

VOLUME ONE

RESTORATION & AFTERCARE PROJECTS, 2017 Y1622, HAREWOOD WHIN, PHASE 12 WEST & PHASES 12 & 13 SOUTH EAST RESTORATION Y1622, HAREWOOD WHIN, PHASE 12 SOILING

CONDITIONS OF CONTRACT

NEC3 ECC OPTION C:

TARGET CONTRACT WITH ACTIVITY SCHEDULE

VOLUME ONE

CONTENTS

GENERAL	1

1.1	CONDITIONS OF CONTRACT	1

1.2	THE WORKS	1

1.3	THE EMPLOYER	1

1.4	THE PROJECT MANAGER	1

1.5	THE SUPERVISOR	1

1.6	THE SITE MANAGERS	2

1.7	THE ADJUDICATOR	2

1.8	THE WORKS INFORMATION	2

1.9	THE SITE INFORMATION	2

1.10	THE BOUNDARIES OF THE SITE	2

1.11	THE LANGUAGE OF THIS CONTRACT	2

1.12	THE LAW OF THE CONTRACT	2

1.3	THE PERIOD FOR REPLY	2

THE CONTRACTORS’ MAIN RESPONSIBILITIES	2

1.14	LIABILITY FOR DEFECTS DUE TO THE CONTRACTORS’ DESIGN	2

TIME	3

1.15	THE STARTING DATE	3

1.16	THE ACCESS DATES	3

1.17	THE COMPLETION DATES	3

1.18	SUBMISSION OF REVISED PROGRAMMES	3

TESTING AND DEFECTS	3

1.19	THE DEFECTS DATE	3

1.20	THE DEFECTS CORRECTION PERIOD	3

PAYMENT	3

1.21	THE CURRENCY OF THIS CONTRACT	3

1.22	THE ASSESSMENT INTERVAL	3

1.23	THE PERIOD FOR PAYMENT	3

1.24	FORECASTS OF WORK DONE TO DATE	4

1.25	RETENTION	4

1.26	THE INTEREST RATE	4

1.27	THE EXCHANGE RATES	4

1.28	THE CONTRACTOR’S SHARE PERCENTAGE AND SHARE RANGE	4

COMPENSATION EVENTS	4

1.29	ASSESSMENT OF COMPENSATION EVENTS	4

TITLE	4

1.30	OBJECTS AND MATERIALS WITHIN THE SITE	4

RISKS AND INSURANCES	4

1.31	PUBLIC LIABILITY	4

1.32	THE CONTRACTOR’S EMPLOYER’S LIABILITY	5

DISPUTES AND TERMINATION	5

1.33	CHOICE OF NEW ADJUDICATOR	5

1.34	THE TRIBUNAL	5

SECTIONAL COMPLETION	5

1.35	COMPLETION DATES FOR EACH SECTION	5

1.36	DELAY DAMAGES FOR EACH SECTION	6

OPTION Z: ADDITIONAL CONDITIONS OF CONTRACT	6

1.37	ADDITIONAL CONDITIONS OF CONTRACT	6

AMENDMENTS TO THE CONDITIONS OF CONTRACT	6

1	GENERAL	6

2	THE CONTRACTOR’S MAIN RESPONSIBILITIES	6

3	TIME	6

4	TESTING AND DEFECTS	7

5	PAYMENT	7

6	COMPENSATION EVENTS	7

7	TITLE	8

8	OPTION Z ADDITIONAL CONDITIONS OF CONTRACT	8

DISCLAIMER:

This document and the information contained therein is for the exclusive use of Yorwaste

COPYRIGHT:

The copyright of this document is vested in Yorwaste and may not be reproduced in part or in whole without their express written permission.

RESTORATION & AFTERCARE PROJECTS, 2017 Y1622, HAREWOOD WHIN, PHASE 12 WEST AND PHASES 12 & 13 SOUTH EAST RESTORATION Y1622, HAREWOOD WHIN, PHASE 12 SOILING

CONTRACT DATA PART ONE

# GENERAL

## 1.1	CONDITIONS OF CONTRACT

The conditions of contract are the core clauses and the clauses for main Option C (Target contract with activity schedule), and Option W2 (Dispute Resolution), Option X2 (Changes in the Law), Option X4 (Parent Company Guarantee), X5 (Sectional Completion) and Option X16 (retention) of the third edition (June 2005 with amendments) of the NEC Engineering and Construction Contract as amended and added to by the Employer in this document.

## 1.2	THE WORKS

The works are all temporary and permanent work associated with the design and construction of the following Restoration & Aftercare Project:

Harewood Whin : Y1622 PHASE 12 WEST & PHASES 12 & 13 SOUTH EAST RESTORATION

Harewood Whin : Y1622 PHASE 12 SOILING

## 1.3	THE EMPLOYER

The Employer is

Yorwaste Limited

Mount View

Standard Way

Northallerton

North Yorkshire

DL6 2YD.

## 1.4	THE PROJECT MANAGER

The Project Manager is an individual from:

Yorwaste Limited

Mount View

Standard Way

Northallerton

North Yorkshire

DL6 2YD.

## 1.5	THE SUPERVISOR

The Supervisor is an individual from and individuals as notified to the Contractor from:

Yorwaste Limited

Mount View

Standard Way

Northallerton

North Yorkshire

DL6 2YD.

## 1.6	THE SITE MANAGERS

For details of the Employer’s Site Manager and other site staff, see Site Information

## 1.7	THE ADJUDICATOR

The Adjudicator is to be agreed between the Parties.

## 1.8	THE WORKS INFORMATION

The Works Information is in the latest revision of the Works Information document, titled, "Restoration & Aftercare Projects 2017, Y1622, Harewood Whin Phase 12 West and Phases 12 & 13 South East Restoration and Phase 12 Soiling"

The Works Information may include individual sections of the works applicable to other projects. These are not part of the Contract.

## 1.9	THE SITE INFORMATION

The Site Information is the latest revision of the Site Information, titled,

"Restoration & Aftercare Projects 2017, Harewood Whin Site Information".

## 1.10	THE BOUNDARIES OF THE SITE

The boundaries of the site are shown on the following drawings:

HAR-DR12-Y1622-010 & HAR-DR12-Y1622-011.

## 1.11	THE LANGUAGE OF THIS CONTRACT

The language of this contract is English.

## 1.12	THE LAW OF THE CONTRACT

The law of this contract is the law of England and Wales subject to the jurisdiction of the Courts of England and Wales.

## 1.3	THE PERIOD FOR REPLY

The period for a reply to a communication is two weeks.

# THE CONTRACTORS’ MAIN RESPONSIBILITIES

## 1.14	LIABILITY FOR DEFECTS DUE TO THE CONTRACTORS’ DESIGN

The Contractor’s liability for Defects due to his design that are not listed on the Defects Certificate is the total of the Prices.

# TIME

## 1.15	THE STARTING DATE

The starting date is 19th June 2017 for Phase 12 Soiling

The starting date is 19th June 2017 for Phase 12 West and Phases 12 & 13 South East Restoration.

## 1.16	THE ACCESS DATES

The access date  is 19th June 2017 for Phase 12 Soiling

The access date is 19th June 2017 for Phase 12 West and Phases 12 & 13 South East Restoration.

## 1.17	THE COMPLETION DATES

The completion date is 8th September 2017 for Phase 12 Soiling

The completion date is 8th September 2017 for Phases 12 West and Phases 12 & 13 South East Restoration.

## 1.18	SUBMISSION OF REVISED PROGRAMMES

The Contractor submits revised programmes at intervals of no longer than one calendar month.

# TESTING AND DEFECTS

## 1.19	THE DEFECTS DATE

The defects date for each section of the works is fifty two (52) weeks after each completion date.

## 1.20	THE DEFECTS CORRECTION PERIOD

The defects correction period is two weeks.

# PAYMENT

## 1.21	THE CURRENCY OF THIS CONTRACT

The currency of this contract is pounds sterling (£).

## 1.22	THE ASSESSMENT INTERVAL

The assessment interval is one calendar month.

## 1.23	THE PERIOD FOR PAYMENT

The period within which payments are made is four weeks from receipt of the Contractor’s correct VAT. invoice for the certified amount due.

## 1.24	FORECASTS OF WORK DONE TO DATE

The Contractor prepares forecasts of Work done to Date for the works at intervals of no longer than one calendar month.

## 1.25	RETENTION

The retention free amount is nil.

The retention percentage is 3%.

## 1.26	THE INTEREST RATE

The interest rate is 2% per annum above the base rate of Yorkshire Bank plc at the time the interest is due to be paid.

## 1.27	THE EXCHANGE RATES

The exchange rates are those published in the Financial Times on, 1st April 2017.

## 1.28	THE CONTRACTOR’S SHARE PERCENTAGE AND SHARE RANGE

The Contractor’s share percentages and the share ranges are

| Share range | Contractor’s share percentage |
| --- | --- |
| Less than 90% | 0% |
| From 90% to 110% | 50% |
| Greater than 110% | 100% |

# COMPENSATION EVENTS

## 1.29	ASSESSMENT OF COMPENSATION EVENTS

Assessment of the cost impact of a compensation event may, at the sole discretion of the Project Manager or his delegate, use information provided as Data for the Schedule of Cost Components as submitted by the Contractor in Contract Data Part Two as the basis to establish Actual Cost.

# TITLE

## 1.30	OBJECTS AND MATERIALS WITHIN THE SITE

The Contractor has no title to materials arising from excavation and demolition within the Working Areas unless notified by the Project Manager.

# RISKS AND INSURANCES

## 1.31	PUBLIC LIABILITY

The amount of the minimum limit of indemnity for insurance in respect of loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) due to activity in connection with this contract for any one event is £5,000,000.00 (five million pounds) with an unlimited of events in any one year.

## 1.32	THE CONTRACTOR’S EMPLOYER’S LIABILITY

The amount of the minimum limit of indemnity for insurance in respect of death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract for any one event is £10,000,000.00 (ten million pounds) with an unlimited number of events in any one year.

The Contractor also provides motor insurance to the full extent of his obligations required by current law.

# DISPUTES AND TERMINATION

## 1.33	CHOICE OF NEW ADJUDICATOR

In the event that an adjudicator cannot be agreed between the Parties within one week of a dispute being notified then the person who will choose a new adjudicator is the President for the time being of the Institution of Civil Engineers or his/her delegated representative.

ICE Dispute Administration Service:

The Institution of Civil Engineers

One Great George Street

Westminster

London

SW1P 3AA

Telephone 020 7665 2214

## 1.34	THE TRIBUNAL

The tribunal is arbitration.

The arbitration procedure is the Institution of Civil Engineers Arbitration Procedure (1997) or any amendment or modification to it in force when the arbitrator is appointed.

The procedure is amended so that all reference to Engineer are read as the Project Manager.

# SECTIONAL COMPLETION

## 1.35	COMPLETION DATES FOR EACH SECTION

The completion date for each section of the works is.

| Section of the Work | Completion Date |
| --- | --- |
| Phase 12 Soiling | 8th September 2017 |
| Phase 12 West and Phases 12 & 13 South East Restoration | 8th September 2017 |
| Construction Completion | 8th September 2017 |

## 1.36	DELAY DAMAGES FOR EACH SECTION

Delay Damages are £285 per day

# OPTION Z: ADDITIONAL CONDITIONS OF CONTRACT

## 1.37	ADDITIONAL CONDITIONS OF CONTRACT

The additional conditions of contract are as detailed in this document.

# AMENDMENTS TO THE CONDITIONS OF CONTRACT

## 1	GENERAL

### 11	Identified and defined terms

11.2	Add the following sub-clause:

“(31) A week is seven days.”

## 2	THE CONTRACTOR’S MAIN RESPONSIBILITIES

### 20	Providing the works

Insert new clause as follows:

“20.2	The Contractor prepares applications for payment of the Price for Work Done to Date, for each assessment date and submits them to the Project Manager.”

### 26	Subcontracting

26.2	To the following sentence “A reason for not accepting the subcontractor is that his appointment will not allow the Contractor to Provide the Works” add the following: “or that the subcontractor is not the subcontractor for the work named in the Contract Data or the Contractor’s Works Information where the work affects the design life, performance or costs of operation or maintenance of the works.”

### 28	Access to the work

Insert new clause as follows:

“28.2	The Contractor provides access to any records relating to the works including arranging for access to the records of any Subcontractors if requested by the Project Manager.”

## 3	TIME

### 36	Acceleration

36.2	Delete “or gives his reason for not doing so”.

## 4	TESTING AND DEFECTS

### 45	Uncorrected Defects

45.1	Replace “assesses” with “may assess”.

## 5	PAYMENT

### 50	Assessing the amount due

Delete this clause and replace with the following:

“50.4	The Contractor submits an application for payment within one week of each assessment date. The Project Manager gives the Contractor details of how the amount due has been assessed.”

### 51	Payment

Delete the first sentence and replace with the following:

“51.1	The Project Manager certifies payment within two weeks of each assessment date or within two weeks of the receipt of the Contractor’s application for payment, whichever is longer.”

Delete the first sentence and replace with the following:

“51.2	Each certified payment is made within four weeks of receipt of a Contractor’s VAT. invoice for the correct certified amount due.”

Add the following sub-clause:

“51.6	The Contractor submits a VAT. invoice for the amount certified by the Project Manager.”

## 6	COMPENSATION EVENTS

### 60	Compensation events

60.1	(4) Delete this clause and replace with the following:

“(4) The Project Manager gives an instruction to stop or not to start work, unless such instruction is due to the Contractor not complying with the contract or the applicable law.”

60.1	(13) Delete this clause and insert “not used”.

60.1	(14) Delete this clause and insert “not used”.

Add the following clause:

“60.4	The Contractor submits costs for any works that may be a compensation event on a weekly basis to the Project Manager, showing weekly and cumulative costs, these to be submitted by Tuesday of the following week. Non submission is a return of nil costs.”

### 62	Quotations for Compensation Events

62.3	Delete the first paragraph and replace with the following:

“The Contractor submits quotations within three weeks of being instructed to do so by the Project Manager. The Project Manager replies within three weeks of the submission. His reply is”

63	Assessing compensation events

63.11	Delete this clause and replace with the following:

“The Contractor provides the records required in the Works Information (Records clause), within the time specified, including records of costs for Compensation Events. Where the records are not provided to the specification or within the specified time, then the Project Manager assesses for that record period the value any Compensation Events that have not been approved.”

### 64	The Project Manager’s assessments

64.1	Line one: replace “assesses” with “may assess”.

## 7	TITLE

### 73	Objects and materials within the Site

73.2	Delete this clause and replace with the following:

“The Contractor has no title to materials from excavation and demolition except as stated in the Works Information.”

## 8	OPTION Z ADDITIONAL CONDITIONS OF CONTRACT

### Z1	ASSESSMENT DATES

Z4.1	From the starting date to Completion of the whole of the works the assessment date is the last Saturday of each calendar month.

### Z2	PREVENTION OF SURFACE WATER POLLUTION

The following clause in the Environmental section of the Works Information is also an Additional, Condition of Contract

Z2.1	On no account will the Contractor allow any unauthorised discharge to leave the site.

Z2.2	On no account will the Contractor allow any unauthorised discharge to leave the working area without permission from the Project Manager.

Z2.3	Contravention of this clause which results in any action by the Environment Agency against the Employer will be regarded with the utmost seriousness and will include, but not be limited to, the following actions against the Contractor :

a)	Non payment of any monies due to the Contractor under the contract.

b)	Banning of the Contractor from carrying out any works for the Employer on a contract or sub contract basis for a minimum period of six years.

Legal action to recover punitive damages for loss of the Employer’s good name or reputation and any consequential loss.