## Sheet1
Task Name | Duration | Start | Finish | BS/PM/QS Service | Contract Package Estimated Value
Tenders
Display Cases | 25 days | Fri 11/08/17 | Thu 14/09/17 | Yes | 100000
Tender Period | 3 wks | Fri 11/08/17 | Thu 31/08/17
Tender Return | 0 days | Fri 01/09/17 | Fri 01/09/17
Tender Evaluation | 10 days | Fri 01/09/17 | Thu 14/09/17
Contractor Appointment | 0 days | Thu 14/09/17 | Thu 14/09/17
Building Works | 22 days | Mon 14/08/17 | Tue 12/09/17 | Yes | 50000
Tender Period | 2 wks | Mon 14/08/17 | Fri 25/08/17
Tender Return | 0 days | Fri 25/08/17 | Fri 25/08/17
Tender Evaluation | 10 days | Tue 29/08/17 | Mon 11/09/17
Contractor Appointment | 0 days | Tue 12/09/17 | Tue 12/09/17
HVAC System | 71 days | Mon 10/07/17 | Mon 16/10/17 | Yes | 300000
HVAC Feasibility Study | 7 days | Mon 10/07/17 | Tue 18/07/17
Mobilise HVAC Designer | 5 days | Mon 07/08/17 | Fri 11/08/17
HVAC Design/Specification | 15 days | Mon 14/08/17 | Fri 01/09/17
Prepare Documentation | 10 days | Mon 04/09/17 | Fri 15/09/17
Expressions of Interest PQQ's | 10 days | Mon 14/08/17 | Fri 25/08/17
Review Expressions of Interest PQQ's | 5 days | Mon 28/08/17 | Fri 01/09/17
Notify Successful Pre-qualified Tenderers | 0 days | Mon 04/09/17 | Mon 04/09/17
Tender Period | 11 days | Mon 18/09/17 | Mon 02/10/17
Tender Return | 0 days | Mon 02/10/17 | Mon 02/10/17
Tender Evaluation | 10 days | Tue 03/10/17 | Mon 16/10/17
Appoint Contractor | 0 days | Mon 16/10/17 | Mon 16/10/17
Exhibition Fit-Out works | 23 days | Thu 24/08/17 | Mon 25/09/17 | Yes | 155000
Tender Period | 2.4 wks | Thu 24/08/17 | Fri 08/09/17
Tender Return | 0 days | Mon 11/09/17 | Mon 11/09/17
Tender Evaluation | 9 days | Tue 12/09/17 | Fri 22/09/17
Contractor Appointment | 0 days | Mon 25/09/17 | Mon 25/09/17
External Plinths and Barriers | 23 days | Thu 24/08/17 | Mon 25/09/17 | Yes | 60000
Tender Period | 2.4 wks | Thu 24/08/17 | Fri 08/09/17
Tender Return | 0 days | Mon 11/09/17 | Mon 11/09/17
Tender Evaluation | 9 days | Tue 12/09/17 | Fri 22/09/17
Contractor Appointment | 0 days | Mon 25/09/17 | Mon 25/09/17
Graphics/Wayfinding | 21 days | Wed 13/09/17 | Wed 11/10/17 | Yes | 45000
Tender Period | 11 days | Wed 13/09/17 | Wed 27/09/17
Tender Return | 0 days | Thu 28/09/17 | Thu 28/09/17
Tender Evaluation | 8 days | Fri 29/09/17 | Tue 10/10/17
Contractor Appointment | 0 days | Wed 11/10/17 | Wed 11/10/17
Object Mount Contractor | 26 days | Mon 18/09/17 | Mon 23/10/17 | No | £TBC
Tender Period | 3 wks | Mon 18/09/17 | Fri 06/10/17
Tender Return | 0 days | Fri 06/10/17 | Fri 06/10/17
Tender Evaluation | 10 days | Mon 09/10/17 | Fri 20/10/17
Contractor Appointment | 0 days | Mon 23/10/17 | Mon 23/10/17
Security (CCTV, Cameras, PIR's) - Dates TBC | 1 day? | Fri 09/02/18 | Fri 09/02/18 | Yes | £TBC
Tender Period
Tender Return
Tender Evaluation
Contractor Appointment
External Lights | 30 days | Tue 19/09/17 | Tue 31/10/17 | No | 50000
Tender Period | 4 wks | Tue 19/09/17 | Mon 16/10/17
Tender Return | 0 days | Mon 16/10/17 | Mon 16/10/17
Tender Evaluation | 10 days | Tue 17/10/17 | Mon 30/10/17
Contractor Appointment | 0 days | Tue 31/10/17 | Tue 31/10/17