| CHANGE CONTROL NOTICE (CCN) |  |  |  |
| --- | --- | --- | --- |
| Contract Title: | The Provision of an External Evaluator for Deliberative Public Engagement (The Contract). |  |  |
| Contract Reference: | CCZZ19A47 | Contract Change Number: | CCZZ19A47-1 |
| Date CCN issued: | 04/02/2020 | Date Change Effective from: | 01/12/2019 |
| This is a retrospective variation to the Contract between National Infrastructure Commission (The Customer) and 3KQ Limited (The Supplier). The Terms and Conditions of the Contract remain unchanged but there will be the following amendment: - Uplift in Value of an additional £4,100.00 (Excluding VAT), increasing the total Contract value from £13,600.00 (Excluding VAT) to £17,700.00 (Excluding VAT). Please refer to Section one (1) for revised deliverables. Words and expressions in this Change Control Notice shall have the meanings given to them in the Contract. The Contract, including any previous Contract changes, authorised in writing by both Parties, shall remain effective and unaltered expect as amended by this Change Control Notice. - Additional Deliverables - The additional deliverables for this requirement are the following: Ref; Description; Price; Timeframe. 1; 2 extra workshop location observations; [REDACTED]; February 2019. 2; Observing 2 x focus groups; [REDACTED]; December 2019. 3; Designing questionnaire for focus groups; [REDACTED]; December 2019. 4; Analysis of focus group questionnaires; [REDACTED]; January 2019. 5; Focus group reporting; [REDACTED]; February 2019. Total; £4,100.00. |
| - The following supplier resources will be engaged in this work: [REDACTED] |  |  |  |
| [REDACTED] [REDACTED] 17/02/2020 Change authorised to proceed by: (Customer representative): Signature Print Name and Job Title Date |  |  |  |
| Authorised for and on behalf of the Supplier: [REDACTED] [REDACTED] 22/02/2020 Signature Print Name and Job Title Date |  |  |  |
| Authorised for and on behalf of the Customer: [REDACTED] [REDACTED] 17/02/2020 Signature Print Name and Job Title Date |  |  |  |