Specification for research to assess the impact of recently-built flood alleviation schemes in managing long-term residual flood risk in England.

Tender Reference Number: MD/1116

Specification of Requirements

Invitation to Tender - Assess the impact of recently-built flood alleviation schemes in managing long-term residual flood risk in England

Tender Reference Number: MD/1116

Deadline for Tender Responses: 1PM 21/11/16

Contents

1.	Introduction and summary of requirements / Preamble	0

2.	Background	0

3.	Aims and Objectives	0

4.	Methodology	0

5.	Outputs Required	0

6.	Ownership and Publication	0

7.	Quality Assurance	0

8.	Timetable	0

9.	Challenges	0

10.	Ethics	0

11.	Working Arrangements	0

12.	Required Skills	0

13.	Consortium Bids	0

14.	Budget	0

15.	Evaluation of Tenders	0

# Introduction and summary of requirements / Preamble

The Adaptation Sub-Committee (ASC) of the Committee on Climate Change (CCC) has a statutory duty to report to Parliament with an independent assessment of the UK Government’s progress in implementing its National Adaptation Programme.  This programme, published in July 2013, sets out the Government’s objectives and policies for adaptation primarily in England, addressing the risks and opportunities identified by the UK Climate Change Risk Assessment (CCRA), first published in January 2012.

In 2015, the ASC produced its first statutory assessment of the National Adaptation Programme. This report considered through a series of indicators what actions were taking place to adapt to the effects of climate change across a number of sectors, and how vulnerability to climate hazards is changing over time.  It also assessed the extent to which policies and programmes were set up to promote or deliver adaptation actions.  The ASC reported on progress through a series of adaptation priorities.  Each priority was given a traffic light score to represent whether appropriate plans were in place, actions were occurring as set out, and trends in vulnerability were moving in the right direction.  The ASC also provided a set of recommendations for further action as a result of this analysis, which the Government subsequently responded to.

In the first statutory assessment, the ASC considered current Government policies, plans and actions to manage flood risk in England, and their impact on reducing exposure and vulnerability to flooding. The ASC acknowledged progress in developing a six-year investment plan of flood and coastal defence schemes to be taken forward over the period 2015- 2021. The analysis also assessed the long-term investment scenarios published by the Environment Agency in 2014, considering the optimal investment path to the 2060s. The ASC concluded that even in the best case scenario of no new development in the floodplain, optimal investment over several decades, and every cost-effective flood and coastal defence being built, there are still expected to be more homes in areas of high flood risk in the coming years that at present due to deterioration in exiting assets combined with the impacts of climate change.

The ASC is required to produce a second progress report on the National Adaptation Programme by the end of June 2017.  This report will consider any changes in policy and action since the first report was produced, and include any updates in the evidence base.  To inform this second progress report, the ASC wishes to assess how recent flood defence schemes have helped contribute towards the long-term management of residual flood risk in the context of climate change.

# Aims and Objectives

The objective of this project is to better understand to what extent recently delivered flood alleviation schemes in England have been designed to support the long-term reduction in residual flood risk.

The specific aims of this project are to review a sample of the major schemes contributing towards the delivery of better flood protection to 180,000 households over the 2010/11 to 2014/15 period and understand:

- The impact of the flood alleviation schemes in managing long-term flood risks, by assessing the current and future standard of protection achieved by the scheme in comparison to what was in place previously. This would include considering how climate change has been factored in to the scheme design, for example the allowances included for future sea level rise or increase in peak river flows at the outset.

- The extent to which future options to upgrade defence standards are included as an explicit element of the scheme design, for example identified upgrade paths and trigger points consistent with taking a ‘managed adaptive’ approach.

- The justification provided to support the choice of the particular engineering solution(s) and standard of protection against other options.

- To what extent the schemes work with natural processes and deliver co-climate change adaptation co-benefits, such as the creation or restoration of habitats that help absorb heavy rainfall or wave energy, or natural flood management techniques such as rewilding, tree-planting, more natural hydromorphology.

- The consistency of these schemes with sub-national flood risk strategies i.e. the immediate and longer-term risk management policies identified for the area within catchment management plans, shoreline management plans, and the 2014 Long-Term Investment Scenarios.

# Methodology

Bids should include a suggested methodology to address the five aims and meet the overall objective, within the budget provided.  Tenders should include details on: the number of schemes that will be assessed; the proposed criteria for selecting the schemes, to be agreed with the ASC; and the specific analysis and principles that will be applied to assess each of the aims above.  The study is expected to focus primarily on an analysis of project documentation (for example, Project Appraisal Reports, Business Case documents) backed by expert interviews with Environment Agency and the contractors involved in the design and delivery of schemes. The study should include an assessment of 20-30 schemes over the period of interest. The ASC will be able to share the full list of schemes, including location and number of properties protected.

# Outputs Required

The ASC expects that the project will deliver the following outputs:

- A report outlining the method and the findings. This would include the overall conclusions for each of the five aims listed above; as well as the main conclusion against the project’s objective.

- A database or spreadsheet with the results of the assessment made for each flood alleviation scheme.

- An electronic copy of all the documents considered in the study.

# Ownership and Publication

The datasets created and results of the analysis will be owned and published by the Adaptation Sub-Committee.

# Quality Assurance

Quality assurance methods must be more sophisticated than a simple internal check, and should include details of records of how the analysis has been checked and what changes were made as a result.  The QA process to be followed should be outlined in the bid.

# Timetable

An indicative timeline for deliverables is presented below. The contractors can propose modifications to the timeline to better suit their analysis if appropriate, though the final submission date must remain the same. Any proposed modifications should be set out in their bid and will require approval from the ASC secretariat.  Although the timescales for this analysis are short, much of the work in finding relevant evidence has already been completed by the ASC.

| Phase | Deliverable | Date |
| --- | --- | --- |
| Bidding | Bids received | 21st November 2016 |
|  | Interviews conducted | w/c 28th November 2016 |
|  | Contract awarded | 9th December 2016 |
| Project development | Kick off meeting with ASC | w/c 12th December 2016 |
|  | Schemes to include in the study agreed | 16th December 2016 |
|  | Initial findings presented to ASC secretariat | 11th February 2017 |
| Reporting | Draft report to ASC | 28th February 2017 |
|  | Draft report reviewed | 15th March 2017 |
|  | Final amends to report made | 31st March 2017 |

# Challenges

The specific challenges that the ASC envisage with this project include:

- Retrieving detailed information on the schemes.

- Ensuring that conclusions based on the assessment of a subset of schemes are representative at national scale.

- Ensuring that conclusions are evidence-based and include sufficient quantitative data.

# Working Arrangements

# The successful contractor will be expected to identify one named point of contract through whom all enquiries can be filtered. A CCC project manager will be assigned to the project and will be the central point of contact.

# Skills and experience

CCC would like you to demonstrate that you have the experience and capabilities to undertake the project. Your tender response should include a summary of each proposed team members experience and capabilities.

Contractors should propose named members of the project team, and include the tasks and responsibilities of each team member. This should be clearly linked to the work programme, indicating the grade/ seniority of staff and number of days allocated to specific tasks.

Contractors should identify the individual(s) who will be responsible for managing the project.

# Consortium Bids

In the case of a consortium tender, only one submission covering all of the partners is required but consortia are advised to make clear the proposed role that each partner will play in performing the contract as per the requirements of the technical specification.  We expect the bidder to indicate who in the consortium will be the lead contact for this project, and the organisation and governance associated with the consortia.

Contractors must provide details as to how they will manage any sub-contractors and what percentage of the tendered activity (in terms of monetary value) will be sub-contracted.

If a consortium is not proposing to form a corporate entity, full details of alternative proposed arrangements should be provided. However, please note CCC reserves the right to require a successful consortium to form a single legal entity in accordance with Regulation 28 of the Public Contracts Regulations 2006.

CCC recognises that arrangements in relation to consortia may (within limits) be subject to future change. Potential Providers should therefore respond in the light of the arrangements as currently envisaged. Potential Providers are reminded that any future proposed change in relation to consortia must be notified to CCC so that it can make a further assessment by applying the selection criteria to the new information provided.

# Budget

The budget for this project is £25,000 including VAT.

Contractors should provide a full and detailed breakdown of costs (including options where appropriate). This should include staff (and day rate) allocated to specific tasks. Cost will be a criterion against which bids which will be assessed.

Payments will be linked to delivery of key milestones. The indicative milestones and phasing of payments can be adjusted and agreed with the contractor and Project Manager. Please advise in your tender response how this breakdown reflects your usual payment processes.

In submitting full tenders, contractors confirm in writing that the price offered will be held for a minimum of 60 calendar days from the date of submission. Any payment conditions applicable to the prime contractor must also be replicated with sub-contractors.

The Department aims to pay all correctly submitted invoices as soon as possible with a target of 10 days from the date of receipt and within 30 days at the latest in line with standard terms and conditions of contract.

# Evaluation of Tenders

Contractors are invited to submit full tenders of no more than 30 pages, excluding declarations. Tenders will be evaluated by at least three CCC staff.

CCC will select the bidder that scores highest against the criteria and weighting listed below, see the ITT for further information.

EVALUATION CRITERIA AND SCORING METHODOLOGY

| #### Criterion | #### Description | #### Weighting |
| --- | --- | --- |
| 1 | RELEVANT EXPERIENCE / DEMONSTRATION OF CABABILITY | 20% |
| 3 | QUALITY ASSURING THE SERVICES YOU PROVIDE | 10% |
| 4 | MANAGEMENT STRUCTURE | 10% |
| 5 | PROJECT TEAM – SKILLS AND KNOWLEDGE | 20% |
| 6 | METHOD, ABILITY AND TECHNICAL CAPACITY | 30% |
| 7 | UNDERSTANDING OF REQUIREMENTS | 10% |
|  |  | 100% |

Scoring Method

Tenders will be scored against each of the criteria above, according to the extent to which they meet the requirements of the tender. The meaning of each score is outlined in the table below.

The total score will be calculated by applying the weighting set against each criterion, outlined above; the maximum number of marks possible will be 100.  Should any contractor score 1 in any of the criteria, they will be excluded from the tender competition.

| Score | Description |
| --- | --- |
| 1 | Not Satisfactory: Proposal contains significant shortcomings and does not meet the required standard |
| 2 | Partially Satisfactory: Proposal partially meets the required standard, with one or more moderate weaknesses or gaps |
| 3 | Satisfactory: Proposal mostly meets the required standard, with one or more minor weaknesses or gaps. |
| 4 | Good: Proposal meets the required standard, with moderate levels of assurance |
| 5 | Excellent: Proposal fully meets the required standard with high levels of assurance |

Structure of Tenders

Contractors are strongly advised to structure their tender submissions to cover each of the criteria above and supply a price schedule specifying the daily rates (ex-VAT) you will charge for each level of your staff.

Evaluation for Interviews, if held

CCC reserves the right to award the contract based on applicants’ written evaluation only if one candidate emerges from the evaluation stage as significantly stronger than the others.

Should interviews go ahead, CCC will shortlist the top three suppliers with the highest marks from the written proposals. Interviews are provisionally expected to be held on the 28th November.  If this date changes, CCC will notify applicants.

The areas to be covered in the interview, and markings allocated to each topic area will be sent to the shortlisted supplier prior to interview.

Further details of interviews will be sent to successful applicants on selection.

Feedback

Feedback will be given in letters or emails.