[image: image1.png]-
Lambeth





Request for Quotation

For Purchases Valued Below £100,000


	Summary Information

Reference number

Notice Title

Agnes Riley Gardens, Atkins Road, SW12 0AH

3G pitch resurface
Quotation request data

12th June 2017
Closing date

30thJune 2017
Anticipated contract start date

3rd July 2017
Anticipate contract end date

21st September 2017
Is this a smaller part of a primary contract

No
Lowest value (£)

£50,000
Highest value (£)

N/A
Is it suitable for SME and/or VCSE
(SME – Small and Medium Enterprise, VCSE – Voluntary Community and Social Enterprise)

CPV Code (if known)



	Officer Name
	Greg Knight
	Phone
	02079260395

	Directorate
	Neighbourhoods and growth
	Address
	Phoenix House 3rd Floor
10 Wandsworth Road
London
SW8 2LL

	Team or Section
	Sport and Leisure
	E Mail
	gknight@lambeth.gov.uk

	


The London Borough of Lambeth Needs to Procure: ​

	Site location
	Sports facility
	Required works

	Agnes Riley Gardens, Atkins Road, SW12 0AH


	41.1m x 34m artificial grass pitch
	· Replace the 3G artificial grass surface, incorporating a shock pad suitable for competitive football (FA approved specification)

· Apply line markings to FA approved 5v5 specification

· Replace existing perimeter fencing with the same height twin wire fencing

· Replace the existing netting behind the goals 

· Removal and ethical disposal of the existing carpet and fencing.



key milestones

The Potential Provider should note the following project milestones that the Authority will measure the quality of delivery against:

	Milestone
	Description
	Timeframe

	1
	Request for quotation closes 
	21st June 2017 

	2
	Contractor appointed
	28th June 2017

	3
	Order materials and begin works, resurfacing the pitch and replacing the fencing.
	From 3rd July 2017

	4
	Complete and sign off pitch and fencing
	21st September 2017


Quality requirements

	Sports facility
	Standard requirements

	3G artificial grass
	- FA approved surface quality standards

- SAPCA approved contractor or equivalent 


	Payment Terms:
	30% at the beginning of the contract, 60% at the end of the programme and  10% after final sign off/practical completion

	
	

	Lambeth’s Standard Terms and Conditions of Contract:
	See attached consultancy contract

	Quotation Evaluation Methodology:
	Price + Quality   FORMCHECKBOX 
             Lowest price  FORMCHECKBOX 
 

We recommend to consider whole lifetime costing as well as risks and dependencies. If required, please seek advice from your procurement team.

See attached evaluation of pricing and quality


Note to Suppliers

Prices should be shown exclusive of VAT and inclusive of carriage and delivery and all discounts. 

The Supplier Declaration, Table 1 and attached pricing schedule. should be completed and submitted with a proposal document of no more than 4 pages A4, Arial size 11 font, to gknight@lambeth.gov.uk by the closing date. 
The London Borough of Lambeth reserves the right to refuse submissions that are not delivered on the date specified.  Any costs incurred by the supplier in the preparation and submission of this quote will be borne by the supplier and not the Council.

The winning bidder will be required to complete a Supplier Self Certification form. See attached.

For Completion by the Supplier

Table 1

	(Supplier Name)

	

	Quotation Submission Date:
	

	Contact Name:
	
	Phone:
	

	Department (if needed):
	
	Fax:
	

	Address:
	
	E Mail:
	


This quotation will remain valid for 6 months from the Quotation Submission Date above.  

Supplier Declaration

After you have completed this form, please read the statements below and agree to the following statements:
· I have read and understood Lambeth’s procurement guidance for suppliers, “Selling to the Council”
· I accept the Terms and Conditions indicated on this form

· If I am selected to provide the above services and/or supplies this form and the information on it will form part of my contract with the London Borough of Lambeth

· If I am selected to provide the above services and/or supplies I will complete the Council’s Supplier Self Certification form.  Failure to complete this form will result in my quotation not being accepted

· Lambeth is under no obligation to accept the final results of the quotation competition or the lowest price for any particular item submitted by a supplier

· Non-delivery of services or products will result in non-payment by the Council

· False representation could result in de-selection from any competition or termination of contract

· It is a criminal offence to give or offer any gift or consideration whatsoever as an inducement or reward to any servant of a public body.  I understand that any such action will empower the Council to cancel any contract or commission currently in force and may result in my exclusion from future work

· Lambeth has the right to use this information for the prevention and detection of  fraud

If you understand and agree to these statements please check the box below.  By checking the box you also certify that the information you have supplied is accurate to the best of your knowledge, has been prepared by your firm with the absence of collusion and that you accept the conditions and undertakings in this form.  If you do not check the box you will not be able to work with the London Borough of Lambeth:

Yes  FORMCHECKBOX 

  
3

