## CDM1 Pre-Construction Tinwell
CDM1 PRE-CONSTRUCTION STAGE INFORMATION
In accordance with regulation 4 of the Construction (Design & Management) Regulations 2015 The following information covering the planned works, site and environment is made available to prospective principal contractors to assist in the health and safety planning and management aspect of the tender process. This document will form the basis for the Construction Phase Plan and associated health and safety file that will be developed throughout the works.
POLICY OBJECTIVE STATEMENT
The Employer takes its obligations under environmental and health and safety legislation seriously and requires that its contractors and agents do likewise. This project will be designed and constructed as far as is reasonably practicable such that it is safe and without risk to the health or safety of the public, the people who will construct it or the subsequent users and other people affected by the completed project.
(1) Project information
Project Title | A1 Concrete Testing - A1/147.00 Tinwell
Project Reference
Designer | Highways England
Employer | Highways England
Principal Designer | Highways England
(2) PLANNING AND MANAGEMENT OF THE PROJECT
(a) LOCATION OF THE PLANNED WORKS O.S Grid Reference. Road Number, River crossing etc. Nearest Settlement. Approach roads/Hazards. Post code if available | The works are at A1/147 Tinwell Bridge. The bridge is located to the west of Stamford, Lincolnshire and carries the A6121 over the A1 trunk road and slips roads. Marker Post 44.3 - Grid Reference 501209/306502 - Lat: 52.646823, Long: -0.50551505. The nearest postcode is: PE9 3UB. The works areas:(East, centre and west piers and deck soffits (N/B and S/B) and edge beams.
(b) CONTRACTOR DESIGN Extent of their design. Temporary works design. Specific elements design. Refer to further details included in the contract | The Contractor will be responsible for the provision of temporary access equipment. The type of access equipment is to be determined by the Contractor to ensure that it best suits their needs and the access restrictions.
(c) Arrangements for ensuring cooperation between duty holders and work is coordinated
(3) Client Brief
(a) NATURE & DESCRIPTION OF THE PLANNED WORKS Purpose of the works including main function and operational requirements of the finished project Main elements of the works and what they comprise | Inspections have found areas requiring concrete repairs on the east, centre and west piers as well as N/B and S/B soffits and edge beams. Concrete testing is required to inform the design of the repair works.
(b) PROGRAMME (TIMEFRAME AND BUDGET) Start date. (provisional or set), Contract period, budget. Restrictions imposed at certain times of year. | Roadspace and traffic management will be provided during the week commencing the 29th October 2018, between the hours of 19:00 and 06:00. The traffic management will comprise back to back lane 2 closures.
(c) CLIENT Main point of contact | Client: Highways England, Stirling House, Lakeside Court, Osier Drive, Sherwood Business Park, Nottingham, NG15 0DS. | Contact: Helen Kenneth Highways England, Stirling House, Lakeside Court, Osier Drive, Sherwood Business Park, Nottingham, NG15 0DS.
(d) SIGNIFICANT HAZARDS & PRECAUTIONS IDENTIFIED AT THE DESIGN STAGE Reference should be made to the designer’s hazard identification to provide greater depth and detail and suggested precautions. Utilising wherever possible drawings and schedules. Refer contractor to specific appendices in the contract for risks at different stages of construction. Eg. Traffic Management. Site hoarding, pedestrian routes, underground and overhead services. | Traffic management will be provided by Highways England. Asbestos has not been identified.
(e) SIGNIFICANT HAZARDS & PRECAUTIONS IDENTIFIED AT THE CONSTRUCTION STAGE Include what steps the design team should reasonably take to ensure their designs help manage foreseeable risks during the construction phase and when maintaining, cleaning or demolishing a structure Compliance with Specification. Contamination. Risk associated with storage of materials. | Details of invasive and protected species identified in the area of the works can be found in site information document and appendix 3.
(f) HIGH RISK OR COMPLEX HAZARDS (IF APPLICABLE SEE SCHEDULE 3) Include expected standards of health and safety, including safe working practices, and how these standards will be maintained throughout.
(4) Existing Information Relevant to the Project
(a) STRUCTURAL DRAWINGS AND SURVEYS Include any existing drawings or surveys e.g. Asbestos | The following documents contain information relevant to the works: E046202/BD/A1/147.00/14. General Arrangement Drawing (As Built) 373A/17/38/1 Elevation (As built) 561336.16.01 Indicative Testing Location and Location Plan Asbestos Action Plan Copies are within Appendix 1,2 and 3 of the Works Information.
(b) THE HEALTH AND SAFETY FILE Include any relevant information from an existing health and safety file. | Not Applicable

## Sidney Farm
CDM1 PRE-CONSTRUCTION STAGE INFORMATION
In accordance with regulation 4 of the Construction (Design & Management) Regulations 2015 The following information covering the planned works, site and environment is made available to prospective principal contractors to assist in the health and safety planning and management aspect of the tender process. This document will form the basis for the Construction Phase Plan and associated health and safety file that will be developed throughout the works.
POLICY OBJECTIVE STATEMENT
The Employer takes its obligations under environmental and health and safety legislation seriously and requires that its contractors and agents do likewise. This project will be designed and constructed as far as is reasonably practicable such that it is safe and without risk to the health or safety of the public, the people who will construct it or the subsequent users and other people affected by the completed project.
(1) Project information
Project Title | A1 Concrete Testing - A1/148.10 Sidney Farm
Project Reference
Designer | Highways England
Employer | Highways England
Principal Designer | Highways England
(2) PLANNING AND MANAGEMENT OF THE PROJECT
(a) LOCATION OF THE PLANNED WORKS O.S Grid Reference. Road Number, River crossing etc. Nearest Settlement. Approach roads/Hazards. Post code if available | The works are at A1/148.10 Sidney Farm Bridge. The bridge is located to the west of Stamford, Lincolnshire and carries the A606 over the A1 trunk road. Marker Post 45.4. Grid Reference: 500663 / 307433. Lat: 52.655291, Long: -0.51329849. The nearest postcode is: PE9 2JY. The works areas:(East, central and west piers and deck soffits in N/B and S/B. A site visit is recommended to ensure that the Contractor takes the all safety and access requirements into account.
(b) CONTRACTOR DESIGN Extent of their design. Temporary works design. Specific elements design. Refer to further details included in the contract | The Contractor will be responsible for the provision of temporary access equipment. The type of access equipment is to be determined by the Contractor to ensure that it best suits their needs and the access restrictions.
(c) Arrangements for ensuring cooperation between duty holders and work is coordinated
(3) Client Brief
(a) NATURE & DESCRIPTION OF THE PLANNED WORKS Purpose of the works including main function and operational requirements of the finished project Main elements of the works and what they comprise | Inspections have found areas requiring concrete repairs on the east, centre and west piers as well as N/B and S/B soffits. Concrete testing requires to identify the design works.
(b) PROGRAMME (TIMEFRAME AND BUDGET) Start date. (provisional or set), Contract period, budget. Restrictions imposed at certain times of year. | Roadspace and traffic management will be provided during the week commencing the 29th October 2018, between the hours of 19:00 and 06:00. The traffic management will comprise back to back lane 2 closures.
(c) CLIENT Main point of contact | Client: Highways England, Stirling House, Lakeside Court, Osier Drive, Sherwood Business Park, Nottingham, NG15 0DS. | Contact: Helen Kenneth Highways England, Stirling House, Lakeside Court, Osier Drive, Sherwood Business Park, Nottingham, NG15 0DS.
(d) SIGNIFICANT HAZARDS & PRECAUTIONS IDENTIFIED AT THE DESIGN STAGE Reference should be made to the designer’s hazard identification to provide greater depth and detail and suggested precautions. Utilising wherever possible drawings and schedules. Refer contractor to specific appendices in the contract for risks at different stages of construction. Eg. Traffic Management. Site hoarding, pedestrian routes, underground and overhead services. | Traffic management will be provided. Asbestos has not been identified.
(e) SIGNIFICANT HAZARDS & PRECAUTIONS IDENTIFIED AT THE CONSTRUCTION STAGE Include what steps the design team should reasonably take to ensure their designs help manage foreseeable risks during the construction phase and when maintaining, cleaning or demolishing a structure Compliance with Specification. Contamination. Risk associated with storage of materials. | Details of invasive and protected species identified in the area of the works can be found in site information document and appendix 3.
(f) HIGH RISK OR COMPLEX HAZARDS (IF APPLICABLE SEE SCHEDULE 3) Include expected standards of health and safety, including safe working practices, and how these standards will be maintained throughout.
(4) Existing Information Relevant to the Project
(a) STRUCTURAL DRAWINGS AND SURVEYS Include any existing drawings or surveys e.g. Asbestos | The following documents contain information relevant to the works: Drg. No. 373A/17/39/1 - Elevations and Sections Drg. No. 373A/17/39/2 - Deck Details Drg. No. 373A/17/39/3 - Pier Details 561336.16.02 Indicative Testing Location and Location Plan Asbestos Action Plan Copies are within Appendix 1, 2 and 3 of the Works Information.
(b) THE HEALTH AND SAFETY FILE Include any relevant information from an existing health and safety file. | Not Applicable