## Sheet1
Highways England Confirmation of Task Order
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | Atkins
Project Title: | Chichester A27 – assessment of concepts from BABA27
Contract Ref. | 2589 | CPA No.: | Redacted |  | BPA No.: | Redacted
PIN Description: | Chichester a27 Technical Assessment | Sub Pin: | Redacted |  | PIN No.: | Redacted
HE Reference: | SE 49 18/19ATK | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | 5165058.422 | Consultant Contact: |  |  | Redacted
Start & End Date: | 31/10/2018 - 09/11/2018 | CTO Authorisation No.
Task Overview
Overview Highways England consulted in 2017 on five options for RIS1 improvements to the A27 at Chichester. The five options had been arrived at following 21 concept options that had gradually been dismissed as assessment progressed. The five on line improvement options consulted on did not include any to the north of the city, this lead to an action group promoting a “vote for none of the above” consultation response in the hope a northern option would come forward. Following the consultation, the Secretary of State opted to cancel the scheme due to the split community - almost 50/50 between those wanting a northern and southern option, of which a slight majority of the latter opted for Option 2. West Sussex County Council and Chichester District Council indicated that to obtain public consensus on a route option they wished to take the project forward and did so through the Build a Better A27 (BABA27) group supported by consultant Systra. The report from this work now needs to be assessed and developed to arrive at viable and buildable options that can be costed and promoted through the future RIS process. Where possible background papers from the previous work will be provided to help deliver the outputs of this brief. Methodology An initial brief was provided by Redacted on the 17th August 2018. A subsequent telecon was held with Redacted, Redacted and Redacted on the 11th September to discuss the proposal history, issues and discuss a way forward. It was agreed that a revised brief would be provided by HE; this was received on the 17th September and forms the basis of this CTO. Accordingly we envisage the following key tasks: • Inception & Mobilisation • Document reviews/familiarisation • Task One: Tabulation of scheme elements cross-referencing the Systra Report (Section 8) including appraisal, referencing to origin of design feature and with a RAG rating considering viability for both Mitigated North and Full South o Suggested deliverable alternatives for non-viable elements o Identification of potential Value Engineering opportunities • Task Two: Identification and discussion of non-viable options (RAG rating Red) • Task Three: Suggested deliverable alternatives for non-viable elements (RAG rating Red to Amber) • Task Four: Identification of potential value engineering • Draft Reporting and incorporate HE comments on draft into a Final Report. • Meeting with HE/WSCC (assumed Guildford) Documents available: • A27 Chichester RIS2 concept • Chichester Technical Appraisal Report (rev PO2) • Chichester A27 Systra Situation Assessment and Recommendations Assumptions • A key element of the work is clarifying the definition of ‘viable’ as this will underpin any subsequent analysis. Most proposals could be considered viable given sufficient cost, time and political will. Therefore we propose an assessment of a scheme / option being viable based on engineering only (I.e. ‘Buildability). We propose to agree this definition with HE at the outset. • A fortnightly progress call is proposed – with key actions minuted – to enable timely updates and assurance of the findings to date (total of three calls assumed). • Focus on the Systra Report only (Task 1 and 2) with a review and consideration of alternative Task 3) and Value Management (Task 4) of Highways England derived versions of Mitigated North and Full South options. • Reporting will be largely tabular where possible and fully cross-reference with the Systra report; providing a concise deliverable that can support Redacted ongoing discussions with WSCC. • Desk top exercise only; no survey requirements, CAD or OS Mapping. • The options presented are highly schematic in nature and commensurate to the level of detail for RIS2: as such the level of review provided as part of this task will reflect this and any drawings will be conceptual/sketches only. • This work will be the view of experienced highway engineers covering a range of potential issues and not explicitly engage technical specialists in e.g. traffic modelling, environmental constraints etc. • Focus on the highway engineering, not wider transport package measures. • All costings to be provided by Highways England. • Technical piece; remote from political context and not aiming to deliver recommendations. • Attendance at 1x meeting with WSCC to discuss issues and alternatives. • A five week programme commencing 1st October.
Task Objectives and Milestones
Objectives The viability and buildability of both BABA27 options will be assessed, with a technical paper giving detail of issues. This will include: 1. A technical appraisal of the proposals put forward in the Systra report for Mitigated North and Full South options, quoting the relevant paragraph numbers from the Systra report; (60%) 2. Identification and discussion of proposed elements of the Systra options that are not technically viable, noting non-compliances with standards etc; (15%) 3. Suggested deliverable alternatives for those non-viable elements; where appropriate cross referring to the HE versions for Mitigated North and Full South schemes; (15%) 4. Identification of those areas where there may be greatest potential for Value Management within the spirit of the Systra report. (10%) Milestone • This task has required ongoing discussions to clarify the required tasks. Accordingly we propose the following programme the required level of works and on availability of key staff and: - Inception call: w/c 01/10 - Progress call to inform discussions before meeting with WSCC – 10th October - Draft report – Friday 2nd November - Final report – Friday 9th November This is programmed as such, as the tasks will be undertaken in sequence, consequently a Draft Report will naturally occur later in the programme. However we will maintain regular communication to report on and assure HE of our progress throughout via weekly calls.
Task Outcomes
Provide an independent review of Systra’s work to support HE in their discussions with WSCC and their objective of arriving at viable and buildable options for A27 at Chichester that can be costed and promoted through the future RIS process.
Project Risk and Management
Risks • The timescales provided for this review preclude detailed assessment of the full background to, and rationale behind, the current options proposed by Highways England. This includes the original RIS sifting report and why the northern Bypass was eliminated. Our completed report will therefore need to be reviewed by Highways England to ensure compatibility with the rationale behind earlier decisions • Drawings and technical assessment not available therefore review focused on high-level overview of report only. • Precise scope of requirements is likely to evolve over the course of the task therefore it is very difficult to align to cost/time KPIs. We will revisit progress and issue EWN as appropriate. Management • Contract Manager / Technical Reviewer – Redacted • Task Manager – Redacted • Technical Lead – Redacted
Project Title: | Chichester A27 – assessment of concepts from BABA27 |  |  |  | HE Reference: | SE 49 18/19ATK
HE Project Sponsor | Sign: Redacted |  | Print Name: | Ariel Brook |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Time Online
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 49 18/19ATK | 14829.86 | 0 |  |  | 14829.86 | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 14829.86
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 14829.86
Total Project Fee Estimate |  |  |  |  | 14829.86
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted (Atkins Office) | Associate Director | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Principal Planner / Engineer | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Director | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Principal Planner / Engineer | Redacted | @ | Redacted | Redacted
Redacted (Atkins Office) | Associate Director | Redacted | @ | Redacted | Redacted
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2018-10-29 |  | Works Total |  | 14829.86
Confidential and commercially sensitive information which shall not be disclosed to third parties
|  |  | Sub Total |  | 14829.86
|  |  | Expenses |  | 100
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 14929.86