## Sheet1
CLARIFICATION LOG
Tender: | MAR0038 Refurbishment of Halls of Residence and Village Accommodation 2023
Tender Reference: | 0038
Published Date: | 2023-02-28
Version number: | 0.2
Number | Clarification | Response | Reply date
1 | Please confirm that the consultant appointment will be let under an unaltered version of the NEC Professional Service Contract, with exception of insurance levels and project specific dates. | The contract will consist of the tender documents and the applicant submitted information | 2023-03-06
2 | Please advise on form of contract for construction works | As noted in the Scope of Service the options for the procurement of the works contractor are to be discussed and agreed with the Client | 2023-03-06
3 | Please supply existing As Built plans, and site survey information including FRA and Asbestos Management Plan | No. There is a substantial amount of hardcopy as-built information which cannot reasonably be digitised and uploaded | 2023-03-06
4 | Please confirm the contact to arrange access for Pre-Tender site visit | pkay@marjon.ac.uk | 2023-03-06
5 | Please provide a schedule of equipment being provided by the University | Kitchen appliances/white goods only | 2023-03-06
6 | With regard to selection question 6.1, we are intending to provide the two project case study based on a contract carried out for City College 2 years ago at contract value c £450k, these are not refurbishment of dwellings in multiple occupancy projects but are similar scale fast track refurbishments for teaching and student spaces within a college campus that needed to be undertaken and completed by the start of the new college year in September. As Q6.1 is so tightly specific on the experience and contract examples, can PMU please indicate whether this approach will likely be a pass given the selection criteria. | The question will be evaluated against the criteria, i.e. •Refurbishment of dwellings in multiple occupancy •Minimum works contract value of £250,000 exc VAT •Minimum Total floor area of 600m2. This can be the total of one building or the total of a number of smaller premises combined If a submitted project does not include each of these it will not meet the 'Pass' criteria | 2023-03-07
Clarifications will be published against the Contract Notice on Find a Tender and Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: tenders@marjon.ac.uk