CALL OFF SCHEDULE 12: VARIATION FORM

No of Call Off Order Form being varied: CCCC18A32………

Variation Form No: CCCC18A32-01………

BETWEEN:

|  |
| --- |
| insert name of Customer ("**the Customer"**) The Cabinet Officeandinsert name of Supplier (**"the Supplier"**) PricewaterhouseCoopers LLP |

1. This Call Off Contract is varied as follows:

This is an extension to the Contract between the Cabinet Office and PricewaterhouseCoopers LLP. The Terms and Conditions of the Contract apply but with the following amendments:

* Uplift in Value of an additional £124,927.00 (Exc. VAT), increasing total Contract value from £249,881.00 (Exc. VAT) to £374,808.00 (Exc. VAT).
* Variation to the Contract End Date - The original Contract period was 2nd April 2018 until 31st May 2018. The intention of the Authority is to vary the Contract end date by eighteen (18) days, to 26th June 2018.
* Inclusion of revised deliverables - Please refer to Annex 1 and 2 revised deliverables.
1. Words and expressions in this Variation shall have the meanings given to them in this Call Off Contract.
2. This Call Off Contract, including any previous Variations, shall remain effective and unaltered except as amended by this Variation.
3. 12/08/2013

Signed by an authorised signatory for and on behalf of the Customer

|  |  |
| --- | --- |
| Signature | REDACTED TEXT |
| Date | REDACTED TEXT |
| Name (in Capitals) | REDACTED TEXT |
| Address | REDACTED TEXT |

Signed by an authorised signatory to sign for and on behalf of the Supplier

|  |  |
| --- | --- |
| Signature | REDACTED TEXT |
| Date | REDACTED TEXT |
| Name (in Capitals) | REDACTED TEXT |
| Address | REDACTED TEXT |