2nd Condition Data Collection Programme

Technical and Quality Management Services

*** INVITATION TO TENDER ***

VOLUME 2 – STATEMENT OF REQUIREMENTS

Contents

1.	Introduction	5

1.1.	Background	5

1.2.	CDC 1	5

1.3.	The CDC2 Programme	5

2.	CDC2 Programme Responsibility	8

2.1.	The Authority (Department for Education or “DfE”)	8

2.2.	Technical and Quality Management Services	9

2.3.	Surveying Organisations	11

2.4.	IT Supplier	12

3.	General Requirements	13

3.1.	General Obligations	13

3.2.	Implementation Period	14

3.3.	Meetings and Workshops	22

3.4.	Additional Services	27

4.	Consultant Delivery Requirements	28

4.1.	Delivery Requirements	28

4.2.	Management Functions	28

4.3.	Data and Systems Assurance Requirements	28

4.4.	Training Management	29

4.5.	Quality Assurance Management	31

4.6.	Audit of School/FE College Data	31

4.7.	Exit Management	38

Appendices
Appendix A - CDC2 Delivery Process

Appendix B - CDC2 Experience, Qualifications, Training and Passporting Requirements

Appendix C - CDC2 Technical Reference Manual Part 1 Schools

Appendix D – CDC Technical Reference Manual Part 2 Schools

Appendix E – FECDC  Technical Reference Manual Part 1

Appendix F – FECDC Technical Reference Manual Part 2

Appendix G - CDC2 Draft Data Collection Proforma

Appendix H – CDC2 Draft Scope for NCA Solution

Appendix I - CDC2 IT NCA Data Points and Space Types

Appendix J – Not used

Appendix K – Assessing the Net Capacity of Schools

Appendix L - CDC1 Desktop Fabric Audit Proforma SAMPLE

Appendix M - CDC1 Desktop M&E Audit Proforma SAMPLE

Appendix N – Not used
Appendix O – IT Design Workshop and UAT Involvement

Introduction

Background

The James Review of Education Capital (2011) recommended independent condition surveys on a rolling 20% sample of the estate, repeating this to develop a full picture of the estate’s condition over five (5) years and thereafter. The Property Data Survey (“PDS”) was delivered between 2012 and 2014 providing the first response to this recommendation and included approximately 18,500 Schools. The first Condition Data Collection programme (“CDC1”) was commissioned in 2016 to collect condition and estates information on the entire School estate (circa 22,000 Schools) over a period of three (3) years. CDC1 started in March 2017 and the Schools programme completed in September 2019. In November 2018, the CDC1 scope was extended to include 261 FE Colleges. These were surveyed between May and December 2019.

CDC 1

CDC1 has provided a comprehensive picture of the condition and nature of all School/FE College buildings. By building on the programme’s predecessor, the PDS, it continued to meet the recommendation in the 2011 Sebastian James review of school capital funding in that the Authority carries out a rolling programme of building condition data collection across all Schools/FE Colleges, to provide a credible picture of needs. A rolling programme also set a foundation to bring the Authority into line with good practice in managing large estates in the private sector.

The CDC1 programme included all publicly funded Schools in England, circa 22,000 Schools with 63,000 buildings of over 77 million m2 of floor space and 261 FE Colleges with circa 2 million m2 of floor space.

The CDC2 Programme

Following the success of CDC1, the Authority now wishes to follow even more closely the Sebastian James recommendations in delivering the CDC2 Programme. The CDC2 Programme is a five (5) year programme of data collection which will include all Schools/FE Colleges.

The CDC2 Programme and, therefore, the SOs, will need to collect the following data, matching the CDC1 approach:

Asset/Contextual data which describes the estate and the buildings which form it including their size, construction type and context (listings, location in flood plains, shared use etc.);

Condition data which describes the condition of buildings and the priority associated with addressing that condition in a directly comparable form to that collected through CDC1; and

Management (Compliance) data which captures the existence of key management/compliance documentation and the date of most recent inspections/reviews. Although high level, this data will contribute to building the evidence base for good asset stewardship.

The IT Solution is expected to support the CDC2 Programme in order to help deliver the abovementioned high-level objectives by:

- Being ready for the Consultant to deliver Implementation Services by 19 October and the SOs to deliver Implementation Services by 16 November 2020 (indicative), as further detailed in Section 3.2 (Implementation Period) below;

- Fully supporting the CDC2 Programme’s data collection process, allowing or providing:

- In-the-field collection of data;

- Storage and hosting of collected data;

- Functionality to facilitate collection and maintenance of high quality and robust data; and

- Reporting functionality.

It is expected that the IT Solution will be available for the duration of the Agreement Period including the Implementation Period.

The Authority’s allocation of Schools/FE Colleges to the SOs shall be carried out in accordance with the methodology set out in paragraphs 1.3.6 to 1.3.8 below. Table 1 and Table 2 set out the notional number (based on data as at the Commencement Date) of Schools/FE Colleges to be allocated per region and per Tranche respectively. The data in Table 1 and Table 2 below will vary during the Agreement Period as a result of new Schools/FE Colleges coming into existence, Schools/FE Colleges being decommissioned and School/FE College changes.

The Authority will not allocate Schools/FE Colleges until after the Commencement Date and allocations shall be made in Tranches. The SOs shall ensure that Services are only delivered at the Sites within a released Tranche (i.e. neither the Consultant nor the SOs shall attempt to carry out Services at Sites in later Tranches before they have been instructed to do so).

The Schools/FE Colleges will be divided evenly between SOs using a filter by region and within this a filter by each gross internal floor area (“GIFA”) band and then division of this number by three (3). This will ensure that across the country there is an even split and that within each region each SO has an even split of GIFA band Schools/FE Colleges. Where the number of Schools/FE Colleges does not divide evenly between three (3) SOs, the Authority will allocate as fairly as possible by ensuring overall each SO has a similar number and size of Schools/FE Colleges at which to carry out the Services.

The Authority will carry out a check using a formula to verify that there is an even split of Schools/FE Colleges across the three (3) SOs and that each SO also has an even split of Schools/FE Colleges within each pricing band. A check on the number of Schools/FE Colleges that each SO has within each region is also carried out to ensure there is a fair split across the country.

The Consultant shall deliver its Services across all Schools/FE Colleges.

All terms used in this Statement of Requirements shall have the same meaning as contained in Clause 1 (Definitions) of the Agreement unless expressly stated otherwise. This Statement of Requirements shall be construed and interpreted in accordance with the Agreement to which it forms part.

Table 1: Anticipated Regional allocation of Schools/FE Colleges

The information in this table is indicative, is not fixed, and may vary during the course of the Agreement Period.

| Region | Total Schools | Notional number per SO | Total FE Colleges | Notional number per SO |
| --- | --- | --- | --- | --- |
| East Midlands | 2075 | 692 | 16 | 5 |
| East of England | 2568 | 856 | 23 | 8 |
| London | 2630 | 877 | 36 | 12 |
| North East | 1148 | 383 | 21 | 7 |
| North West | 3219 | 1073 | 38 | 13 |
| South East | 3383 | 1128 | 48 | 16 |
| South West | 2379 | 793 | 21 | 7 |
| West Midlands | 2419 | 807 | 35 | 12 |
| Yorkshire and the Humber | 2260 | 754 | 23 | 8 |

Table 2: Anticipated number of Schools/FE Colleges per Tranche

| Tranche | Schools/FE Colleges | Notional number per SO |
| --- | --- | --- |
| 1 | 1000 | 334 |
| 2 | 2635 | 879 |
| 3 | 2635 | 879 |
| 4 | 2635 | 879 |
| 5 | 2635 | 879 |
| 6 | 2635 | 879 |
| 7 | 2635 | 879 |
| 8 | 2635 | 879 |
| 9 | 2636 | 879 |
| 10 (FE) | 261 | 87 |

CDC2 Programme Responsibility

There are four (4) organisational roles with defined responsibilities within the CDC2 Programme; each interacting and working with the others to deliver the CDC2 Programme. The successful delivery of the CDC2 Programme will require the development and pro-active maintenance of good working relationships between the four (4) roles, as illustrated in the diagram below.

The Authority (Department for Education or “DfE”)

The Authority will be both client and programme manager, responsible for the CDC2 Programme direction and delivery, provision of key information, approval of standards, contract management and wider engagement with the sector and will:

Produce a list of Schools/FE Colleges to be surveyed in a given Tranche and a given period (to be set by the Authority in accordance with the detail set out in Section 1.3 (The CDC2 Programme) and Table 1 and Table 2 above);

Undertake contract management of the Consultant;

Undertake IT Solution contract management;

Undertake contract management of SOs and monitor performance;

Manage relationships with external stakeholder groups (e.g. Responsible Bodies, multi academy trusts, single academies etc.) and correspondence (but note that routine engagement with Schools/FE Colleges and Responsible Bodies to enable delivery of the Services is the responsibility of the SOs and to an extent the Consultant to arrange Shadow Audits and Revisit Audits where required);

Manage relationships with internal stakeholders;

Undertake technical governance/liaison between the Consultant, SOs, and IT Supplier;

Undertake investment model governance, i.e. model ownership and development, including different dimensions of need;

Develop and maintain a technical enquiry and response log to triage any technical enquiries from the Sites during the Agreement Period and will include this in the Supplier Management Meetings (as detailed in Table 4 below) and ongoing update reports. The Authority will also escalate enquiries to SOs via the Consultant for rectification as necessary;

Be responsible for CDC2 Programme monitoring and management, including the management and operation of complex Site definition and process;

Be responsible for reviewing management information, programme reporting and KPI monitoring;

Be responsible for monitoring the effectiveness of the data capture application used to capture data on Sites and the data storage solution, providing feedback to the IT Supplier on material IT issues that need to be prioritised for resolution;

Be responsible for CDC2 Programme delivery plan and development, as illustrated in the CDC2 Delivery Process contained in Appendix A (CDC2 Delivery Process) to this Schedule 2 (Statement of Requirements);

Be responsible for Authority document ownership and development; and

Be responsible for the School/FE College and Responsible Body IT Solution account set up and management processes.

Technical and Quality Management Services

The Consultant shall provide technical and quality leadership and advise all relevant CDC2 Programme stakeholders. The Consultant will also be responsible for ensuring the maintenance of standards, continuous improvement, training and quality assurance of survey provision to ensure the provision of consistent high-quality data throughout the Agreement Period and the Consultant shall:

Engage with the Authority and the IT Supplier during the design, scoping and UAT of the IT Solution during the IT Supplier’s implementation period;

Arrange CDC2 Technical and Quality Programme Review Workshops including technical and quality assessments with the CDC2 Programme leadership to review how this is impacting CDC2 Programme delivery;

Support the Authority in finding a resolution for any issues identified and carry out interventions when required, including problem solving and trouble-shooting with all relevant stakeholders based on general observation and results from all audits;

Be responsible for CDC2 Programme quality assurance process and control, ensuring quality assurance is robust and proactive; Operate processes which follow industry standards and best practice, such as ISO 9000/9001 or similar;

Ensure Consultant personnel have  valid Enhanced DBS checks, in accordance with the requirements detailed in Appendix B (CDC2 Experience, Qualifications, Training and Passporting Requirements) of this Schedule 2 (Statement of Requirements), and produce evidence if required by a School/FE College’s safeguarding policy when carrying out any Visits to Schools/FE Colleges as set out in clauses 5.7 and 5.8 of the Agreement;

Undertake training and standards maintenance which includes regular updates to the CDC2 Programme Technical Reference Manuals which are set out in Appendix C (CDC2 Technical Reference Manual Part 1 Schools), Appendix D (CDC Technical Reference Manual Part 2 Schools), Appendix E (FECDC Technical Reference Manual Part 1) and Appendix F (FECDC Technical Reference Manual Part 2) of this Schedule 2 (Statement of Requirements) and training modules to ensure clarity of requirements and common methodology across all Visits;

Carry out a wholesale review, as part of the Consultant’s Implementation Services, of the CDC2 Draft Data Collection Proforma contained in Appendix G (CDC2 Draft Data Collection Proforma) of this Schedule 2 (Statement of Requirements) and the Technical Reference Manuals which are set out in Appendix C (CDC2 Technical Reference Manual Part 1 Schools), Appendix D (CDC Technical Reference Manual Part 2 Schools), Appendix E (FECDC Technical Reference Manual Part 1) and Appendix F (FECDC Technical Reference Manual Part 2) of this Schedule 2 (Statement of Requirements) to align them with any changes to methodology and proforma since CDC1. This review will not have any substantive/significant impact on the manner in which the Consultant is expected to deliver the Services;

As part of the update to the Technical Reference Manuals set out in Appendix C (CDC2 Technical Reference Manual Part 1 Schools), Appendix D (CDC Technical Reference Manual Part 2 Schools), Appendix E (FECDC Technical Reference Manual Part 1) and Appendix F (FECDC Technical Reference Manual Part 2) of this Schedule 2 (Statement of Requirements) provide specific updates to system build sections of the Technical Reference Manuals as above, and also further training to assist surveyors to identify and classify system builds on each Site;

Maintain CDC2 Programme technical resource and technical passporting records in accordance with the requirements detailed in Appendix B (CDC2 Experience, Qualifications, Training and Passporting Requirements) of this Schedule 2 (Statement of Requirements).  Take responsibility for updating material as necessary and inform the Authority of any onboarding/offboarding of SO personnel so that changes can be made to the IT Solution accordingly by the Authority;

Throughout the CDC2 Programme, oversee the quality assurance of the SOs data collection activities and regularly update the Authority on items requiring review and action to ensure consistent, high-quality levels of data. To minimise the effect of any SO variability that impacts on quality assurance, the Consultant shall undertake assurance procedures throughout the pre-survey, survey and post survey stages of the CDC2 Programme. This will be achieved through the Consultant undertaking Shadow Audits, Revisit Audits, and Desktop Audits, and reporting (audits are as detailed in Section 4.6 (Audit of School/FE College Data) below) independently of the SOs to verify survey data provided by the SOs. Timing of these Shadow, Revisit and Desktop Audits shall be in line with the Contract and Delivery Management Meetings, Supplier Management Meetings with SOs and the TQM, and Technical and Quality Programme Review Workshops;

Take part in the Technical and Quality Programme Review Workshops with the Authority tracking and guiding the development of the technical and quality aspects of the CDC2 Programme, including, for example, at the CDC2 Advisory Group;

The Consultant will audit and assure each SO’s approach to quality assurance once during the Implementation Period and annually thereafter to ensure quality assurance systems and processes are robust and comply with CDC2 Programme data collection requirements. This task may require the Consultant to visit SOs to review and assess their internal processes and approach to quality assurance before feeding back to the Authority.

Surveying Organisations

There are three (3) SOs appointed for the CDC2 Programme. The SOs are required to:

Provide the appropriate IT hardware for surveyors and engineers along with all other surveying equipment necessary to carry out the data collection throughout the Agreement Period, including personal protective equipment (“PPE”), where appropriate, and adequate surveying equipment,  including electronic device with height tracking, to achieve the levels of accuracy required;

Ensure the selection, provision and maintenance of building surveying and mechanical and electrical (“M&E”) engineering resource, along with management, project management office (“PMO”) and computer-aided design (“CAD”) resources to undertake the collection of consistent, high-quality data at pace and scale, and responsibility for the data collection team selection (surveyors, engineers, desktop support);

Engage with individual Schools/FE Colleges and represent the CDC2 Programme consistently and professionally;

Undertake Pre-Site Visit desktop work by arranging a Preliminary Virtual Meeting (by video conference) where details of the SO’s Visit will be arranged and confirmed, and a number of questions will be posed to the School/FE College from the data collection proforma, and the Site plan is reviewed. The data collected should be subsequently checked and anything missing followed up and completed by the surveyor on Site;

Carry out a Reconnoitre Visit at FE Colleges only;

Undertake School/FE College data collection using the CDC2 Draft Data Collection Pro Forma contained at Appendix G (CDC2 Draft Data Collection Proforma) of this Schedule 2 (Statement of Requirements) and ensure upload of collected data onto the IT Solution;

Undertake all post Visit desktop work;

Quality assure and quality control their own work, providing high quality data in accordance with the issued Technical Reference Manuals set out in Appendix C (CDC2 Technical Reference Manual Part 1 Schools), Appendix D (CDC Technical Reference Manual Part 2 Schools), Appendix E (FECDC Technical Reference Manual Part 1) and Appendix F (FECDC Technical Reference Manual Part 2) of this Schedule 2 (Statement of Requirements)to this Schedule 2 (Statement of Requirements);

Undertake and maintain quality assurance checking in line with the CDC2 Programme requirements to ensure provision of high-quality reports. This may be reviewed by the Consultant/Authority team at any time. Quality will be solely the SOs responsibility and it is the SOs responsibility to provide high quality reports to be audit approved by the Consultant;

Attend training initiated by the Consultant/Authority (which may also involve training by the IT Supplier) throughout the CDC2 Programme and roll out/cascade to teams to maintain quality and consistency;

Update CDC2 Programme technical resource registers and technical passporting records in accordance with the requirements detailed in Appendix B (CDC2 Experience, Qualifications, Training and Passporting Requirements) of this Schedule 2 (Statement of Requirements). Take responsibility for updating material as necessary and inform the Consultant of any onboarding/offboarding of personnel so that the Consultant can inform the Authority to make changes to the IT Solution accordingly;

Review, record and undertake a specific review of the first CDC2 Programme data output from their surveyors and engineers to ensure surveyors and engineers have understood and applied the training that they have received and take appropriate corrective action if they have not;

Contribute on experience of working with Schools/FE Colleges to help shape the development of the CDC2 Programme, for example. at the CDC2 Advisory Group, continuous improvement/lessons learned and other CDC2 Programme wide processes including technical innovation;

Respond to any corrective action in line with the CDC2 Delivery Process shown in  Appendix A (CDC2 Delivery Process) to this Schedule 2 (Statement of Requirements), as well as data fixes or other data queries from the Consultant or the Authority where identified (including after receipt of any School/FE College feedback) as outlined in the CDC2 Delivery Process set out in Appendix A (CDC 2 Delivery Process) to this Schedule 2 (Statement of Requirements); and

Immediately upon becoming aware of any issues in respect of consistency or quality that could impact delivery of the CDC2 Programme notify the Consultant and the Authority.

IT Supplier

The IT Solution will support the CDC2 Programme by allowing the collection, storage and interrogation of data. Specifically, the IT Supplier will:

Provide the solution for data collection;

Provide the solution for data storage;

Provide the solution for data reporting and interrogation;

Cover all hosting, support and system maintenance activities as well as interim and ad-hoc development where deemed necessary by the Authority;

Through application of Validation Rules within the IT Solution, help support the quality of the data collected under the CDC2 Programme;

Deliver technical support relating to the functionality of data capture/mobile device application for all of the visits to establishments within the scope of the CDC2 Programme;

Ensure that the IT Solution is capable of exporting data for plugging into third party tools, such as analysis and business intelligence products;

Accommodate a user base likely to be in excess of 27,000, including Authority staff as well as Schools/FE Colleges, Responsible Bodies and SO surveyors; and

Provide support to users including training and self-training materials.

The IT Solution will not:

- Be a project management tool in its own right, although data extracted from it will support project management functions;

- Be a customer relationship management (“CRM”) tool; or

- Provide an editing facility for site plans and other building information as part of its function.

The system log data provided by the IT Supplier detailing who made changes to data within the IT Solution and when will be conclusive and final. If the system log data shows that the Consultant made the change then the Consultant shall be responsible (at its own cost) for any corrective action required.

General Requirements

All activities described below must be delivered by the Consultant in the context of and subject to the detailed technical information provided about the CDC2 Programme and its approach, processes, requirements etc. in the Appendices to this Schedule 2 (Statement of Requirements).

General Obligations

The Consultant shall (along with the high level obligations identified in Section 2.2 (Technical and Quality Management Services) of this Schedule 2 (Statement of Requirements)):

- Work in a collaborative manner with the Authority, IT Supplier, and SOs to develop and maintain good working relationships;

- Engage with the Authority, IT Supplier and SOs during the IT Solution implementation period to help ensure the developed IT Solution is fit for purpose;

- Contribute to CDC2 Programme management and project delivery, ensuring that all team members are prepared and able to participate in collaborating with the partner organisations and that, when required, facilities are made available in mutually agreed locations for meetings, workshops and other collaborative activities at no additional cost;

- Work with the Authority in providing assistance and clarification regarding any CDC2 Programme related items;

- Demonstrate their team working skills and commitment to partnering and collaborative working to ensure mutual benefits and the most successful outcome for the Authority;

- Provide and maintain appropriately qualified and trained personnel with adequate knowledge of health and safety Law and good industry practice, (including knowledge of the Royal Institution of Chartered Surveyors (“RICS”) ‘Surveying Safely’ document) environmental and security issues which are relevant to the Services (including all audit functions), and other personnel required to deliver the Services with appropriate qualifications and experience in the relevant professional disciplines and specialist areas. The Consultant’s role and delivery of Services for the CDC2 Programme shall be led by a director/partner (as described in the staff grading definitions in Schedule 1 (Fees) of the Agreement) with chartered surveying, or equivalent status qualification, with experience specifically in the building condition surveying sector;

- Provide and maintain personnel who have adequate experience in, and knowledge of, building condition surveying and related projects, and where they undertake any audit work, they meet the minimum requirements included in Appendix B (Experience, Qualification, Training and Passporting Requirements) to this Schedule 2 (Statement of Requirements);

- Develop and deliver required training activities to SOs to ensure sufficient knowledge regarding the CDC2 Programme delivery requirements and activities are achieved and maintained within the SO teams delivering the CDC2 Programme;

- Ensure that the Services are progressed and delivered within the agreed milestones and timescales;

- Demonstrate the ability to effectively review its Services in order to continually improve performance to the benefit of the Authority;

- Operate appropriate quality assurance processes in line with ISO 9000/9001 and other industry best practice to help ensure that the CDC2 Programme produces high-quality, consistent and reliable data;

- Provide hardware which operates iOS 11 or above which can capture necessary data, including images at an acceptable level of detail; and

- Provide a secure document sharing and collaboration platform (e.g. Sharepoint, MS Teams) accessible to the Consultant, Authority and SOs throughout the Agreement Period.

Implementation Period

The Consultant shall perform the following key activities during the Implementation Period:

Undertake a detailed review, amendment and update of the Technical Reference Manuals and proforma as set out in Appendix C (CDC2 Technical Reference Manual Part 1 Schools), Appendix D (CDC Technical Reference Manual Part 2 Schools), Appendix E (FECDC Technical Reference Manual Part 1),Appendix F (FECDC Technical Reference Manual Part 2) and Appendix G (CDC2 Draft Data Collection Proforma) of this Schedule 2 (Statement of Requirements), and other training material as detailed in paragraphs 2.2.1.6 and 2.2.1.7 above in order to enable ongoing ownership and maintenance of the content of these manuals for the duration of the CDC2 Programme, including specific updates to system build sections of the Technical Reference Manuals and also further training to assist surveyors to identify and classify system builds on each Site.  All documentation and material produced by the Consultant is subject to final approval by the Authority;

Preparation for and delivery of Implementation Period Training Meetings (to SOs) in accordance with all the requirements of the CDC2 Programme. The training shall be delivered in conjunction with the CDC2 Programme pilot surveys (described in Table 3) and SO implementation activities;

Provision and implementation of online training resources for use by the SOs ahead of passporting arrangements for surveyors, engineers and SO support staff as detailed in the Technical Reference Manuals set out in Appendix C (CDC2 Technical Reference Manual Part 1 Schools), Appendix D (CDC Technical Reference Manual Part 2 Schools), Appendix E (FECDC Technical Reference Manual Part 1) and Appendix F (FECDC Technical Reference Manual Part 2), of this Schedule 2 (Statement of Requirements), along with preparing training modules based on the aforementioned Appendices. The training modules will be based on CDC1 training modules as amended by the Consultant to suit the requirements of the CDC2 Programme.  All material produced by the Consultant is subject to final approval by the Authority;

Provide and maintain the learning management system (“LMS”) to enable the SOs to access and complete the e-learning modules (including but not limited to completion of training in relation to data protection) and ensure effective user account management and licences are issued for use of the LMS system accordingly.  The Consultant shall provide, on request, data from the LMS relating to which surveyors or engineers pass or fail the process;

Establishment of CDC2 Programme resources, training and passporting registers in accordance with the requirements in Appendix B (CDC2 Experience, Qualifications, Training and Passporting) of this Schedule 2 (Statement of Requirements).  All documentation produced by the Consultant is subject to final approval by the Authority.

These Implementation Services, including the Gateway Review Workshop, may be subject to change, but are intended as a high level indication of the Implementation Services the Consultant shall be required to perform:

Proforma & validation rules review;

Attendance at IT Design Workshops and IT Solution Functionality UAT Workshops;

IT Solution training (by IT Supplier);

SO training delivery;

IT Solution end-to-end UAT;

Surveyor passporting for pilot surveys;

Gateway Review Workshop.

The Consultant shall participate in the IT Solution User Acceptance Testing (“UAT”) in which the data collection process is run end to end (as more fully set out in Table 3):

Each of the CDC2 Programme Implementation Period stages and the activities required in order to successfully complete the Implementation Period of the wider CDC2 Programme are detailed in Table 3 below:

Table 3: CDC2 Programme Process Stages

| CDC2 Programme Process Stage | Phase | Passing Implementation Period Phase Activity Milestone |
| --- | --- | --- |
| Stage 1 | CDC2 Programme implementation and planning | Authority assigns pilot Sites to the SOs (45 – 15 per SO). |
| Stage 2 | Pre-Site Visit | The SO’s PMO assigns Site to surveyor. The SO’s PMO schedules and holds Preliminary Virtual Meeting and collects data (by video conference). The SO’s PMO generates blank survey. |
| Stage 3 | Site Visit | SO surveyor carries out Visit (completes data collection and ‘submits’ data). Other post Visit tasks completed such as plan production and input of measurements. This results in ‘Pre SO Checked and Approved’ data. |
| Stage 4 | SO Quality Assurance | SO assigns survey to SO audit personnel and other SO Quality Assurance personnel. Any corrective action cycles from Checkpoint Report or other analysis conducted. Upon completion, the SO PMO assigns ‘SO Checked and Approved’ status to the survey data (after any corrective action). |
| Stage 5 | TQM Desktop Audit | The Consultant chooses survey for Desktop Audit and carries out Desktop Audit. Any corrective action cycles from this Desktop Audit are identified by the Consultant and carried out by the SO. The Consultant undertakes report analytics, including Checkpoint Report. The Consultant ‘passes’ a Batch of Sites or a Site after any corrective action cycles by the SO if there are errors. This results in ‘Ready for Release’ data. |
| Stage 6 | Data Release | Following Batch approval, and if the Site has passed the Checkpoint Report, the Authority will release the data. |

The Process Stages will involve assessment by the Consultant of the SOs training of its surveyors and engineers and will include the Desktop Audit of three (3) Schools (one (1) per SO), and will culminate in participation in a Gateway Review Workshop at the end of the Implementation Period.  It is intended that the Implementation Period data collection will be part of the final dataset. The Consultant shall attend the Gateway Review Workshop (as set out in Table 4 below).

IT Solution Design, Scoping and UAT

As part of the Implementation Services, the Consultant shall participate in a small number of IT Design Workshops run by the IT Supplier.  These will focus on the design and scoping of a number of functional requirements that the IT Supplier is required to implement as part of their own implementation services.

For the School data collection, the Consultant’s anticipated engagement in IT Design Workshops is outlined in column C of Appendix O (IT Design Workshop and UAT Involvement) of this Schedule 2 (Statement of Requirements).

For the FE College data collection, the Consultant’s anticipated engagement in IT Design Workshops is outlined in column E of Appendix O (IT Design Workshop and UAT Involvement) of this Schedule 2 (Statement of Requirements) (these will take place in Year 5 of the Agreement Period).

The Consultant shall also participate in UAT of IT Solution functionality (including participation in IT Solution Functionality UAT Workshops), for both School and FE College data collection implementations.  The IT Solution UAT will encompass testing of all required functionality and will be undertaken by the Consultant, SOs and the Authority as outlined in Appendix O (IT Design Workshop and UAT Involvement) of this Schedule 2 (Statement of Requirements).   UAT for School data will take place in Year 1 of the Agreement Period and will be as per column D of Appendix O (IT Design Workshop and UAT Involvement) of this Schedule 2 (Statement of Requirements).  UAT for FE College data will take place in Year 5 of the Agreement Period and will be as per column F of Appendix O (IT Design Workshop and UAT Involvement) of this Schedule 2 (Statement of Requirements). The UAT will consist of forty-five (45) School Visits (fifteen (15) per SO) selected from Tranche One (1) of the CDC2 Programme.  The Consultant shall Visit not less than one (1) School per SO as part of this UAT.

The UAT will be for the purpose of testing the data collection and quality assurance methodologies and delivering UAT of the supporting mobile data collection app and web app components of the IT Solution. It will ensure sufficient infrastructure is in place for the delivery of the CDC2 Programme.

As a precursor to testing activity, the Consultant shall create test scripts detailing how elements of functionality implemented by the IT Solution will be tested by the Consultant during UAT.  The test scripts will be subject to final approval by the Authority prior to the start of UAT. The testing undertaken by the Consultant will determine whether the tested functionality meets pre-defined success criteria.  Success criteria will be formulated with the Consultant and the Authority, will be subject to final approval by the Authority and will be based on functional requirements agreed between the Authority, the Consultant and the IT Supplier during the design and scoping stage of the IT Supplier’s implementation period.

Implementation Plan

The Consultant shall provide a detailed Implementation Plan to the Authority within ten (10) Working Days of the Commencement Date. The Implementation Plan must include (but is not to be limited to):

        - Proposed timescales for achieving relevant implementation milestones (including but not limited to the Process Stages and the Passing Implementation Period Activity Milestone);

        - Proposed timescales for all Implementation Services;

        - Clearly outlined roles and responsibilities of the Authority and the Consultant during the Implementation Period;

        - Proposed timescales for training and passporting activities;

        - Provision for involvement in the IT Solution UAT. UAT is anticipated to take place during the period November 2020 to February 2021.  The Consultant’s involvement in UAT will be focussed on all aspects of the Consultant led process only rather than full system testing. Consequently, the Consultant shall not be required to be involved for the entirety of this period.

Following receipt of the Implementation Plan from the Consultant, the Authority shall:

        - review and comment on the Implementation Plan as soon as reasonably practicable; and

        - notify the Consultant in writing that it approves or rejects the Implementation Plan no later than five (5) Working Days after the date on which the Implementation Plan is first delivered to the Authority.

If the Authority rejects the Implementation Plan:

        - the Authority shall inform the Consultant in writing of its reasons for its rejection; and

        - the Consultant shall then revise the Implementation Plan (taking reasonable account of the Authority's comments) and shall re-submit a revised Implementation Plan to the Authority for the Authority's approval within ten (10) Working Days of the date of the Authority's notice of rejection. The provisions of this paragraph 3.2.7.3 shall apply again to any resubmitted Implementation Plan, provided that either Party may refer any disputed matters for resolution in accordance with clause 19 (Disputes) of the Agreement at any time.

Technical and Quality Programme Review Workshops

- The Consultant shall:

Lead a Gateway Review Workshop at the end of the Implementation Period where the Consultant shall provide the technical and quality assurance to the Authority that the technical and quality requirements of the CDC2 Programme have been met by the SO.  The outcome of the Gateway Review Workshop will determine whether the Authority commences the Services on the Services Commencement Date as intended. The determination will be subject to all relevant assurances being provided to the Authority and will be dependent on the satisfactory completion of:

the IT solution;

the SO programme planning and resource allocation;

the audit functionality development;

the training & passporting of surveyors and mechanical engineers; and

the first forty-five (45) pilot surveys;

Hold/Lead two (2) CDC2 Programme Technical and Quality Programme Review Workshops each year throughout the Agreement Period. At these Technical and Quality Review Workshops the Consultant shall demonstrate their expertise and technical leadership role. The Technical and Quality Programme Review Workshops will focus on CDC2 Programme technical and quality output and issues;

During the Agreement Period, provide a detailed technical performance review of the CDC2 Programme focussing on technical output and quality (and Implementation Services) and all available performance data to assess the effectiveness and efficiency of technical and quality CDC2 Programme delivery. This review shall include consultation with each of the SOs, the IT Supplier and the Authority, as well as analysis of available data. At the CDC2 Technical and Quality Programme Review Workshops the Consultant will;

Provide an agenda and facilitate the Technical and Quality Programme Review Workshops and deliver the above review. Continuous improvement should be the focus of the Technical and Quality Programme Review Workshops;

Undertake post Technical and Quality Programme Review Workshop process development amendments to the Technical Reference Manuals as set out in Appendix C (CDC2 Technical Reference Manual Part 1 Schools), Appendix D (CDC Technical Reference Manual Part 2 Schools), Appendix E (FECDC Technical Reference Manual Part 1) and Appendix F (FECDC Technical Reference Manual Part 2), of this Schedule 2 (Statement of Requirements) and undertake training material amendments.  All material produced by the Consultant is subject to final approval by the Authority;

Prepare and deliver agreed CDC2 Programme interventions in written report format for discussion and agreement with the Authority.

Implementation Period for FE Colleges

The Implementation Period for the FE Colleges will be conducted separately to the other Schools and will include one (1) Site Visit attended by the three (3) SOs along with the Consultant as a multi surveyor/engineer team approach to collect the data.

FE College implementation will also include the IT Solution UAT in which the data collection process is run end to end following the process set out in Table 3 above and will replicate the CDC2 Programme Schools’ process.  The Consultant shall undertake a Desktop Audit of the data collected from the pilot.

The FE College implementation will take place in the fifth (5th) year of the Agreement Period in the three (3) months’ immediately prior to the start of Tranche ten (10) (as referred to in Table 2 above).  The implementation stage for FE Colleges will run concurrently with the Service delivery of Tranche nine (9) to ensure continuity.  There will be no break to the CDC2 Programme Schools delivery whilst the FE College data collection programme is implemented.

The Consultant shall undertake the following key activities during the FE College Implementation Period:

review, amend and update of the FE College Technical Reference Manuals (parts 1 and 2) which are set out in Appendix E (FECDC Technical Reference Manual Part 1) and Appendix F (FECDC Technical Reference Manual Part 2) of this Schedule 2 (Statement of Requirements), and the CDC2 Data collection proforma as set out in Appendix G (CDC2 Draft Data Collection Proforma) of this Schedule 2 (Statement of Requirements);

IT Design Workshop for IT Solution functionality (where required);

Review and where appropriate, amend and update existing FE College training material which will become FE College E-learning training material, consisting of four (4) modules:

- FE College process, Methodology, Technical and IT Solution;

- Implementation planning meetings with the Authority to develop, review and progress implementation activities for FE College;

- Preparation for and delivery to all three (3) SOs of a Technical Training Workshop in accordance with all the requirements of the FE College CDC2 Programme;

- Reconnoitre Visit and Site Visit to one (1) FE College to assess both methodology and SO’s delivery against the methodology.  In addition, assessing IT Solution as outlined in Appendix O (IT Design Workshop and UAT Involvement) of this Schedule 2 (Statement of Requirements); The Visit will form part of the FE College dataset;

- DRAFTING NOTE: Activities listed under ii), iii) and iv) above do not refer to the four (4) FE College E-learning training modules but to key activities to be undertaken by the Consultant during the FE College Implementation Period.

Final review of any training or other material to reflect the outcome of the Site Visit;

FE College Gateway Review Workshop with all parties;

Implementation of FE College CDC2 Programme resources, training and passporting registers (based on existing FE College material).

ISMS and Security Management Plan

The Consultant shall supply for approval by the Authority an ISMS within fifteen (15) Working Days of the Commencement Date, as detailed in Schedule 13 (Security Management) of the Agreement.

The Consultant shall supply a Security Management Plan for the Authority’s approval within twenty (20) Working Days of the Commencement Date, as detailed in Schedule 13 (Security Management) of the Agreement.

Meetings and Workshops

The Consultant shall attend the meetings/workshops detailed in Table 4 below and contribute as necessary to the effective and efficient delivery of the CDC2 Programme.

The Consultant will be taking the role of technical advisor to the Authority at the meetings on all aspects of CDC2 Programme methodology and technical and quality delivery.

Table 4 below sets out a non-exhaustive list of the meetings/workshops the Consultant is required to attend/participate in.  The Authority reserves the right to alter the frequency, purpose, number, duration and required attendees of the meetings/workshops as may be required to facilitate delivery of the CDC2 Programme.

Meeting/workshop locations will be mutually agreed based on staff and room availability, with final decisions taken by the Authority.  The Consultant will be expected to host face to face meetings/workshops on a regular basis, at no additional cost.

- Note: VC = video conferencing 
Per year = per contractual year

Table 4: Meeting/Workshop Requirements

|  | Name of Meeting/Workshop and Attendees | Minimum attendees for the Consultant | Duration | Meeting Type (Face to Face or VC) | Approximate Number of Meetings |
| --- | --- | --- | --- | --- | --- |
| IMPLEMENTATION PERIOD (SCHOOLS ) | IT Functionality (Schools) IT Design Workshop for IT Solution functionality where required. The Consultant, the Authority and the IT Supplier. | 2 Key Personnel | Half Day (up to 4 hours) | Face to Face | 4 |
|  | IT Solution Functionality UAT Workshop (mobile app and web app) (Schools) | 2 Key Personnel | Half Day (up to 4 hours) | Face to Face | 2 |
|  | Three (3) Implementation Planning Meetings with the Authority to develop, review and progress Implementation Services. The Consultant and the Authority. | 2 Key Personnel | Half Day (up to 4 hours) | Face to Face | 3 |
|  | Implementation Period training: three (3) Implementation Period Training and Preparation Meetings with the full delivery team. The Consultant, SOs, IT Supplier and the Authority. | 2 Key Personnel | Half Day (up to 4 hours) | Face to Face | 3 |
|  | One (1) Gateway Review Workshop. The Consultant, SOs, IT Supplier and the Authority. | 2 Key Personnel | Half Day (up to 4 hours) | Face to Face | 1 |
| IMPLEMENTATION PERIOD (FE COLLEGES) | IT Functionality (FE Colleges) One (1) IT Design Workshop for IT Solution functionality (where required). The Consultant, the Authority and the IT Supplier. | 2 Key Personnel | Half Day (up to 4 hours) | Face to Face | 1 |
|  | IT Solution Functionality UAT Workshops (mobile app and web app) (FE Colleges) | 2 Key Personnel | Half Day (up to 4 hours) | Face to Face | 2 |
|  | One (1) Implementation Period Implementation Planning Meeting with the Authority to develop, review and progress Implementation Services for FE Colleges. The Consultant and the Authority. | 2 Key Personnel | Half Day (up to 4 hours) | Face to Face | 1 |
|  | One (1) Implementation Period Preparation and Training Meeting with the full delivery team. The Consultant, SOs, IT Supplier and the Authority. | 2 Key Personnel | Half Day (up to 4 hours) | Face to Face | 1 |
|  | One (1) FE College Gateway Review Workshop The Consultant, SOs, IT Supplier and the Authority. | 2 Key Personnel | Half Day (up to 4 hours) | Face to Face | 1 |
|  | Technical and Quality Programme Review Workshops. The Consultant and the Authority. | 2 Key Personnel | Half Day (up to 4 hours) | Face to Face | 9 |
|  | Technical Training Workshops delivered by the Consultant to SOs. The Consultant, SOs, and the Authority. May involve IT Supplier if required. | All Key Personnel | 1 day (8 hours) | Face to face | 10 (allow 2 per year – every 6 months) |
|  | Contract and Delivery Management Meeting. The Consultant, SOs, Authority and IT supplier. | 1 Key Personnel | Half day (up to 4hrs) | Face to face | 20 |
|  | Contract and Delivery Management Meeting. The Consultant, SOs, the Authority and IT supplier. | 1 Key Personnel | Half Day (up to 4hrs) | VC | 20 |
|  | Supplier Management Meeting. The Consultant and the Authority. These will be monthly. | 1 Key Personnel | 2 hrs | VC | 60 |
|  | Continuous Improvement Session Meeting. The Consultant, SOs and the Authority. May involve IT Supplier if required. | 5 (including 3 Key Personnel) | Half day (up to 4hrs) | Face to Face | 5 |
|  | CDC2 Advisory Group -Stakeholder Engagement Meeting The Consultant, SOs and the Authority. | 1 Key Personnel | Half day (up to 4hrs) | Face to Face | 15 (3 per year) |
|  | Attendance at part of SO supplier meetings | 1 Key Personnel | 1 hour | VC | 30 over the life of the programme (10 per SO / 2 per SO per year) |

Additional Services

Additional Services may be instructed by the Authority in accordance with clause 13 (Additional Services) of the Agreement.

Net Capacity and Schedule of Accommodation Capture

Supplementary to the CDC2 Programme and process, data may also be collected to support School/FE College Net Capacity Assessments (“NCA”) and use of spaces within the School/FE College buildings and external areas on School/FE College Sites. This data is used by the Authority and local authorities to measure and plan School/FE College places provision.

Further guidance and detail in respect of the NCA is set out in Appendix K (Assessing the Net Capacity of Schools) to this Schedule 2 (Statement of Requirements).

Further context and detail regarding NCA is set out in Appendix H (CDC2 Draft Scope for NCA Solution) and Appendix K (Assessing the Net Capacity of Schools) to this Schedule 2 (Statement of Requirements).Potential NCA data points are shown in Appendix I (CDC2 IT NCA Data Points and Space Types) to this Schedule 2 (Statement of Requirements) in ‘Net Establishment’, ‘Net Section’, ‘Net Space’ sheets.  Appendix I (CDC2 IT NCA Data Points and Space Types)) shows proposed data points for Schools. FE College NCA data points are to be confirmed but will be similar in scope.

Appendices H (CDC2 Draft Scope for NCA Solution), I (CDC2 IT NCA Data Points and Space Types)) and K (Assessing the Net Capacity of Schools) to this Schedule 2 (Statement of Requirements) are provided to the Consultant for reference purposes only. The Consultant shall note that all references to “Consultant” within these appendices are to the SOs.

The SO, as part of this requirement shall:

Capture survey information at a space/room level including (but not limited to) dimensions, usage and facilities (e.g. sinks, toilets, playing fields);

Capture new floor plans of buildings/Sites (including external areas) and record annotations/mark ups linked to space/room level surveys;

Record survey data for the CDC2 Programme and NCA as separate or conduct integrated survey exercises depending on the Authority’s operational requirements. For example, the Authority may use different organisations, processes and survey schedules to capture CDC2 Programme and NCA information respectively; and

If required based on the Authority’s operational requirements, engage with Responsible Bodies to ensure they view, update, and submit (via spreadsheet template if required) updated NCA data.

In accordance with clause 13.4 (Additional Pre-Priced Variation) of the Agreement the NCA is a Pre-Priced Variation. If the Authority elects to implement the Pre-Priced Variation then the Consultant shall:

Lead on the implementation of the NCA process ensuring SOs know the level and detail of data they are collecting before commencing;

Develop audit processes in conjunction with the Authority; and

Audit and quality assure the data collected.

Consultant Delivery Requirements

Delivery Requirements

Consultant’s responsibility for delivering training to SOs and evaluating their processes; and

Consultant’s responsibility for managing and maintaining the quality assurance of data collection.

All activities described below must be delivered in the context of and subject to the detailed technical information which is set out in Appendix C (CDC2 Technical Reference Manual Part 1 Schools), Appendix D (CDC Technical Reference Manual Part 2 Schools), Appendix E (FECDC Technical Reference Manual Part 1) and Appendix F (FECDC Technical Reference Manual Part 2) to this Schedule 2 (Statement of Requirements). The aforementioned Appendices detail the CDC2 Programme, its approach, processes and requirements.

Management Functions

- The Consultant shall:

Attend and contribute proactively to appropriate CDC2 Programme wide activities;

Develop with the Authority joint ways of working that enhance close collaboration between the Authority and the Consultant;

In compliance with clauses 15.1 and 15.2 (Confidentiality and Publicity) of the Agreement, submit for review and approval to the Authority any publicity or press material to be released as part of the Consultant’s involvement in the CDC2 Programme;

Provide specific and expert advice where the Authority has queries in its approach to the use of CDC2 Programme data in condition allocations;

Develop and maintain a Technical and Quality Risk and Issues log for the CDC2 Programme and include this in the Supplier Management Meetings as an ongoing update to the Authority; and

Support the Authority in any lessons learnt or continuous improvement activity relating to the technical and quality management of the CDC2 Programme.

Data and Systems Assurance Requirements

The Authority has a number of data security and compliance considerations that the Consultant shall meet and demonstrate evidence of.

The Consultant shall:

Meet or exceed the expectations set out in:

The Authority Security Standards out in Annex 1 of Schedule 13 (Security Management) of the Agreement; and

The Government’s Minimum Cyber Security Standard (https://www.gov.uk/government/publications/the-minimum-cyber-security-standard);

Ensure effective security management is in place for any hardware managed and provided by the Consultant (tablets, desktop computers, smartphones etc);

Hold ISO 27001:2013 certification;

Ensure processing of data is undertaken within the European Economic Area (“EEA”);

Comply with all relevant Law, including but not limited to the DPA 2018 and GDPR; and

Ensure annually commissioned IT Security Health Checks (“ITHC”) for their IT Environment are conducted using a CHECK certified provider.

Training Management

The Consultant shall:

Develop and maintain training modules to enable passporting of the SOs. The Consultant shall be responsible for the provision and maintenance of an online training resource for use by all SOs. The Consultant shall provide a separate training package for fabric surveyors, M&E surveyors and SO support teams.  Each training package must support the communication of the key requirements of the Technical Reference Manuals set out in Appendix C (CDC2 Technical Reference Manual Part 1 Schools), Appendix D (CDC Technical Reference Manual Part 2 Schools), Appendix E (FECDC Technical Reference Manual Part 1) and Appendix F (FECDC Technical Reference Manual Part 2), of this Schedule 2 (Statement of Requirements),  and support the SOs in achieving the required quality standards.  The training is not intended to provide technical training for any SO personnel, but to communicate the unique methodology and requirement of this particular CDC2 Programme. There must be a test to assess how well the material is being assimilated and the results shall be available for review at the Technical and Quality Programme Review Workshops described in Section 3.2.8 (Technical and Quality Programme Review Workshop) above;

Be responsible every six (6) months for the preparation and delivery of a Technical Training Workshop for SOs. This will highlight any changes and continuous improvements flowing from the Technical and Quality Programme Review Workshops described in Section 3.2.8 (Technical and Quality Programme Review Workshop) above. The Consultant will arrange, facilitate and host these Workshops, which will be attended by circa eight (8) people from each SO, two (2) people from the IT Supplier and officers of the Authority, in addition to the Consultant’s own personnel.  The aforementioned Workshops must also include lessons learnt and feedback pro-forma updates;

Ensure all surveyors and engineers are suitably qualified and experienced and have all necessary training, professional knowledge expertise and CDC2 Programme specific training.  Pursuant to this, the Consultant shall maintain records of surveyors and engineers who are trained via the passport system and who are suitably qualified and experienced (as a consequence of training provided by the Consultant) and meet the requirements set out in Appendix B (CDC2 Experience Qualification Training and Passporting Requirements) of this Schedule 2 (Statement of Requirements) via a resources list;

Ensure that data entry is only provided by those with suitable experience, qualifications and training. The Consultant will issue survey ‘passports’ to each surveyor who successfully completes required training and demonstrates compliance with other qualifications and experience requirements.  The Consultant shall appreciate that there is likely to be a degree of change in the SO surveyors working on the CDC2 Programme. The anticipated number of surveyors is an estimate. The Consultant will maintain and make available for reporting the registers of surveyors trained and passports issued as detailed in Appendix B (CDC2 Experience, Qualifications, Training and Passporting Requirements) to this Schedule 2 (Statement of Requirements);

Arrange the training, as set out in the meeting schedule at Table 4 (Meeting Requirements) above and as set out in Section 4.2 (Management Functions) above;

During the Implementation Period, hold Implementation Period Training Meetings to ensure that each SO has had the opportunity for its SO staff to attend this training within the first month of the CDC2 Programme;

Ensure that the training is of suitable quality and has suitable attendance for establishing and maintaining the quality of Service delivery and to ensure that SOs have a working familiarity with all CDC2 Programme technical documentation;

As part of training development, provide a specific additional bespoke training module for identification and classification of system buildings in Schools/FE Colleges, to be given as part of technical training, receive feedback and roll out, as required, during the remaining CDC2 Programme as part of the passporting process as set out in Appendix B (CDC2 Experience, Qualifications, Training and Passporting Requirements) to this Schedule 2 (Statement of Requirements);

Work with the IT Supplier to train the SOs on the use of the IT Solution, ensuring that training is cascaded and ensuring that any changes to the look, feel and functionality of the IT Solution are reflected in updated training which is cascaded to SOs as appropriate.

Quality Assurance Management

The Consultant shall:

Manage and maintain the CDC2 Draft Data Collection Proforma shown in Appendix G (CDC2 Draft Data Collection Proforma) of this Schedule 2 (Statement of Requirements) including all liaison and subsequent implementation with the IT Solution.  All changes must be submitted for final approval by the Authority;

Manage, maintain and deliver the requirements of the quality processes set out in the Technical Reference Manuals at Appendix C (CDC2 Technical                                                                                                                                                                                                                                                                             Reference Manual Part 1 Schools), Appendix D (CDC Technical Reference Manual Part 2 Schools), Appendix E (FECDC Technical Reference Manual Part 1) and Appendix F (FECDC Technical Reference Manual Part 2), of this Schedule 2 (Statement of Requirements), developing and improving on these where necessary as the CDC2 Programme develops;

Contribute to the continuous improvement of all technical documents, training material and other CDC2 Programme standards to ensure that high quality, reliable and consistent data is provided;

Identify and agree with the Authority thresholds and levels of accuracy required, building on the work contained in the quality manuals, technical documents and the CDC2 Programme KPIs; and

In conjunction with the Authority, review all audit templates.  The CDC2 Programme audits will be based on the CDC1 audit proforma updated and validated by the Consultant, including review of critical data points. All CDC1 template process documents will be made available to the Consultant as a starting point, please refer to Appendix L (CDC1 Desktop Fabric Audit Proforma SAMPLE) and Appendix M (CDC1 Desktop M&E Audit Proforma SAMPLE) to this Schedule 2 (Statement of Requirements).  Audit data points for FE Colleges will be broadly similar to Schools but will be reviewed by the Consultant.  The IT Solution will offer other data quality functions to validation of data submitted.

Audit of School/FE College Data

The Consultant is charged with assuring the quality of the data through a series of audits; Shadow Audit, Revisit Audit, and Desktop Audit.  Audit selection across the CDC2 Programme will be representative of the School/FE College estate in terms of type, size and region.

The frequency of any audit (Shadow Audit, Revisit Audit, Desktop Audit) may be adjusted as necessary to assure the quality of the CDC2 Programme data.

Shadow Audits

Shadow Audits will be undertaken as agreed with the Authority but will include at least two (2) Shadow Audits per SO during the Implementation Period, and at least two (2) Shadow Audits per SO during each subsequent six (6) monthly period.  Shadow Audits will also be used if concerns are raised about a particular SO/surveyor/engineer.  Shadow Audits will focus on all aspects of the Visit, including the Preliminary Virtual Meeting and the Pre-CDC2 Meeting.

During a Visit for the purposes of a Shadow Audit the Consultant’s surveyor and/or engineer will accompany the SO surveyor and/or engineer. The Consultant’s surveyor and/or engineer will check that the SO’s surveyors and engineers understand the CDC2 Programme methodology contained in the Technical Reference Manuals (see Appendix C (CDC2 Technical Reference Manual Part 1 Schools), Appendix D (CDC Technical Reference Manual Part 2 Schools), Appendix E (FECDC Technical Reference Manual Part 1) and Appendix F (FECDC Technical Reference Manual Part 2), of this Schedule 2 (Statement of Requirements), and that the correct approach is being followed. The Consultant will report their results to both the Authority and the SO. Where necessary the Consultant will agree with the SO the corrective action the SO is required to take as a consequence of the results of the Shadow Audit.

Revisit Audits

The Consultant, as agreed with the Authority, shall undertake a Revisit Audit where:

there are any concerns with a particular surveyor/engineer or the SO more generally;

where significant errors are identified as part of the Desktop Audit; or

where complaints or discrepancies/disagreement with grades are reported by a School/FE College or Responsible Body.

In a Revisit Audit the Consultant will take a School/FE College’s CDC2 Programme data or access a School/FE College’s CDC2 Programme data for the purpose of revisiting the Site to check the robustness of the data captured by the SO.

Desktop Audits - Schools

The SO will upload the SO Checked and Approved datasets for each Site in an allocated Tranche. The SO Checked and Approved data sets for each calendar month shall constitute a Batch.

Data for Sites which passes the Desktop Audit (on first review or following successful completion of the corrective action cycle) and which has passed a Checkpoint Report becomes Ready for Release by the Authority to Schools and Responsible Bodies.

The Consultant shall audit each monthly Batch. This process will provide the basis for assessing the SO’s data quality across all completed data by checking the robustness of the data in each Batch by using captured photographs and Site/block plans held. The Desktop Audit will be undertaken by a qualified technical resource within the Consultant.

The Desktop Audit is an independent review of the CDC2 Programme dataset and documents in terms of completeness, compliance, accuracy and condition assessment.  It is anticipated that the IT Solution will provide the facility to generate, process and report on Desktop Audits via inbuilt functionality that will enable Consultant auditors to assess a School, based upon the pass/fail criteria.

The Desktop Audit will be carried out by the Consultant on 5% or a minimum of six (6) datasets from each of the SO’s Batches, whichever is the greater.  Where there are six (6) or less datasets in a Batch they will all be subject to Desktop Audit. In any event the Authority reserves the right to adjust the percentage of Desktop Audits required. The Consultant shall be aware that whilst Desktop Audit will be part of the integrated function in the IT Solution, Shadow Audit and Revisit Audit reporting will sit outside of the IT Solution and will not be part of any integrated function.

Passing the Desktop Audit will be determined by a percentage error rate, based on critical datapoints, and will be calculated by the Consultant auditor by determining the overall number of data points (across fabric and M&E) within the dataset against which the number of data queries is identified, which will then define an error percentage.

The Pass Criteria are as follows:

<1% critical errors for an individual Desktop Audit (what constitutes a critical error is to be finalised by the Consultant) subject to final approval by the Authority; on

85% of audited datasets where 5% of a Batch has been subject to a Desktop Audit and 100% of a Batch where six (6) or less data sets have been subject to Desktop Audit; with

No Showstoppers present.

Desktop Audits will consider critical and non-critical audit queries and will define data queries/errors against the following data failure categories (NB: errors may appear in one or more categories):

Missing Data:  Where mandatory data is missing (e.g. measurement values for a Block);

Conflicting Data:  Where data is conflicting within the dataset (e.g. Elemental data suggests kitchen present but no kitchen selected);

Incorrect Assessment: where the surveyor or engineer have incorrectly assessed something and there is clear evidence to this effect such as a photograph;

Process or Measurement Error: where the surveyor or engineer have not followed the CDC2 Programme survey methodology or have made an error in calculating any measurements which are required;

Methodology Error: where the surveyor or engineer have not followed the process methodology as set out in the Technical Reference Manuals contained in Appendix C (CDC2 Technical Reference Manual Part 1), Appendix D (CDC2 Technical Reference Manual Part 2), Appendix E (FE Technical Reference Manual Part 1) and Appendix F (FE Technical Reference Manual Part 2) of this Schedule 2 (Statement of Requirements).

The Desktop Audit (and Revisit Audit Proforma) questions for Schools (Appendix L (CDC1 Desktop Fabric Audit Proforma SAMPLE) and Appendix M (CDC1 Desktop M&E Audit Proforma SAMPLE) of this Schedule 2 (Statement of Requirements)) detail critical (shown in blue) or non-critical (shown in purple) data-points.  Audit data points for FE Colleges will be broadly similar to Schools but will be subject to the Consultant’s review.

The following errors render the data completely or substantially unusable and therefore constitute Showstoppers. The Showstoppers are:

Whole Block, Element or Site data missing;

Fundamental error with the Site/Block;

Reference Plan (block missing, incorrect labelling leading to potential data misinterpretation, etc.);

Meta data fields >10% tolerance;

Methodology Error (i.e. surveyor/engineer creating multiple construction types in a Block);

Cover Photo not tagged (only critical photo that relies on a tag being present) (this is checked via Checkpoint Report);

Any photographic image that does not conform with the standards set out in the Technical Reference Manuals contained in Appendix C (CDC2 Technical Reference Manual Part 1), Appendix D (CDC2 Technical Reference Manual Part 2), Appendix E (FE Technical Reference Manual Part 1) and Appendix F (FE Technical Reference Manual Part 2)Appendices C, D, E and F of this Schedule 2 (Statement of Requirements);

Miscellaneous - where the error is so fundamental to the quality of the data and is not covered in any category above.

The list of Showstoppers is based on CDC1 and is indicative only. The list, and critical and non- critical datapoints, will be reviewed by the Authority/Consultant on the basis of the proforma set out in Appendix G (CDC2 Draft Data Collection Proforma) of this Schedule 2 (Statement of Requirements).

The Desktop Audit process for Schools described in the preceding paragraphs is outlined below in Flowchart 1:

Flowchart 1 Desktop Audit Process - Schools

Desktop Audits – FE Colleges

The Desktop Audit process for FE Colleges will differ from the School’s approach. The FE College Desktop Audit will consist of one (1) fabric survey, and one (1) M&E survey, per FE College, per SO, per month, because there may be multi surveyor and engineer teams collecting data.

Flowchart 2 below demonstrate the FE College Desktop Audit Process:

Flowchart 2 Desktop Audit Process – FE Colleges

The FE College data must be SO Checked and Approved and the Consultant will audit 100% of the data-points within the dataset. It is anticipated each FE College Desktop Audit will pass/fail against a <0.75% error rate pass criteria, but this may be reviewed.

Corrective Action for Schools/FE Colleges

Where the Desktop Audit identifies failures by the SO, corrective action is required by the SO.

The extent of corrective action required is dependent upon the presence of Showstoppers and/or percentage error rate as set out in Table 5 below, reference should also be made to Flowcharts 1 and 2 above. If the Consultant identifies Showstoppers during a Desktop Audit this will result in the SO being given an immediate fail of the Desktop Audit (although the audit process must be completed on the dataset).

Table 5:  Batch Results and Corrective Action Requirements

|  | First Review Batch Result | Corrective Action Required by the SO |
| --- | --- | --- |
| 1 | Batch achieves >85% error rate pass but with Showstoppers in one dataset. | Fix the Showstoppers identified in the individual dataset within the audit Batch window. |
| 2 | Batch achieves >85% error rate pass but there are Showstoppers in more than one data sets. | The SO will fix Showstopper errors in the audits and will also check the remaining 95% of the Batch for any corrections required. The 95% will be subject to additional 2.5% Showstopper Dip Test. |
| 3 | Batch does not achieve >85% pass with >1% errors and possible further Showstoppers present. | The SO shall fix errors and Showstoppers in the data sets and shall also check the remaining 95% as these will be subject to 2.5% additional Full Dip Test. |

A month end status report will be issued by the Consultant to the SO stating the outcome of the Desktop Audit and the required corrective actions.

Where the SO has not achieved the first Batch pass, a corrective action cycle will be required (as identified in Table 5 above) and the data for that month will not be Ready for Release (unless corrective action on one ‘1’is  completed within the audit Batch window).

The Consultant shall reconfirm the quality of the dataset for that month via the corrective action cycle, after the data has been corrected by the SO.  Showstopper Dip Tests and Full Dip Tests consist of re-audits by the Consultant of failed but corrected datasets to ensure that corrections have been carried out by the SO. The Showstopper Dip Tests and the Full Dip Tests are each a 2.5% sample across the 95% of the remaining Batch.  The SO shall review the whole of the remaining dataset to check for errors.

The Authority shall monitor the Consultant’s performance of their obligations pursuant to the Agreement in accordance with Schedule 7 (Performance) of the Agreement. Any failure of the Consultant to achieve the required performance levels shall entitle the Authority to undertake the actions detailed in Schedule 7 (Performance) of the Agreement.

Audit Tracking

The Consultant shall undertake ongoing tracking and analysis of the audited datasets outside of the IT Solution. The tracking will record the data query/error against both the critical and non-critical data points to provide prevalence and trend analysis for review. This will inform future improvement strategies and will help develop requirements for corrective action and provide focus for future continuous improvement.

The Consultant will maintain this analysis on a live tracker which will detail by SO and by month, the status of each SO’s dataset in terms of meeting or missing the monthly target, and where the SO stands on the corrective action requirements.  The Consultant will notify the Authority immediately of any Batch passing Desktop Audit.

The tracker will be updated each month by the Consultant in respect of any change in status of a dataset which originally failed to meet the target but which has passed through corrective action requirements.  It will state the stage in the corrective action cycle the dataset is in, for example, first or other review.

Supporting the Authority’s Management of Key Performance Indicators

The Consultant shall report on technical and quality delivery and performance of the CDC2 Programme and this will feed into the Technical and Quality Programme Review Workshops detailed at Table 4 (Meeting Requirements) above.

On a monthly basis, the Consultant shall report on management information such as results of audits, training (passporting and resourcing) and any other relevant technical and quality issues.

The Consultant shall work with the Authority to refine the SO KPI measures during the live phase of data collection at agreed time intervals. The Consultant will make suggestions and/or revisions to the SO KPI measures to ensure that the SO KPI measures support and incentivise high quality delivery.

The Consultant shall also highlight material issues with the IT Solution, to be prioritised for resolution by the IT Supplier, taking into consideration those issues with greatest impact.

Exit Management

The Consultant shall provide an Exit Plan to the Authority before the start of the final year of the Agreement.  This Exit Plan will be reviewed and, where required, updated on a monthly basis, and shall set out the Consultant's proposed methodology for achieving an orderly transition of the Services from the Consultant to the Authority and/or any replacement consultant on the expiry or termination of the Agreement.

The Exit Plan must include details such as (but not limited to):

Data (including Authority Data) to be transferred to the Authority;

The mechanism for transferring that data;

The mechanism for securely returning or destroying data (including Authority Data) held by the Consultant;

An outline of risks, issues and dependencies;

Details of Consultant personnel that will be engaged in the off-boarding process, with roles and responsibilities outlined;

Contribution to post CDC2 Programme review, and post CDC2 Programme continuous improvement run by the Consultant and the Authority.