## Sheet1
Interim MEPT Procurement Timeline
Step No. | Stage Description | Mandatory Time | Start Date | Target Date | Achieved | Responsible
STAGE 1 - Pre-Advertising Stage
1 | Prior Information Notice (PIN) |  | 28/05/2017/2017 | 2017-06-12 | 2017-06-12 | Commercial
2 | Hold Industry Day |  | 2017-06-29 | 2017-06-29 | 2018-06-29 | Commercial/Technical
3 | Draft Business Case |  | 2017-06-19 | 2017-07-19 | 2017-10-01 | Technical
4 | Business Case is Approved |  | 2017-07-20 | 2017-08-04 | 2017-11-01 | Technical
5 | Draft SMS |  | 2017-07-21 | 2017-08-04 | 2017-10-16 | Technical
6 | SMS is Approved |  | 2017-08-04 | 2017-08-18 | 2017-10-23 | AIAC
7 | Request for Contract Action (RCA) raised on ASPECT. |  | 2017-08-19 | 2017-08-21 | 2017-12-01 | Technical
8 | Choose Selection Criteria, and draft Technical/Commercial questions for PQQ |  | 2017-06-19 | 2017-08-25 | 2017-10-16 | Commercial/Technical
9 | Complete SoR |  | 2017-06-19 | 2017-08-25 | 2017-12-13 | Technical
10 | Draft PQQ, ITT,Contract Notice, Marking Scheme, SOR & Contract |  | 2017-06-19 | 2017-08-25 | 2018-01-19 | Commercial/Technical
STAGE 2 - Advertising & Initial Suppier Selection Stage
11 | Publish CN, PQQ , SOR, Marking Scheme & Contract on DCO |  | 2018-01-25 | 2018-01-25 | 2018-01-30 | Commercial
12 | Suppliers Respond with Expressions of Interest & complete PQQ | 30 | 2018-01-31 | 2018-03-02 | 2018-03-02 | Bidders
13 | Record Expressions of Interest and PQQ Responses |  | 2018-01-31 | 2018-03-02 | 2018-03-02 | Commercial
14 | Commercial evaluation of PQQ responses |  | 2018-03-03 | 2018-03-10 | 2018-03-10 | Commercial
15 | Technical Evaluation of PQQ responses |  | 2018-03-03 | 2018-03-10 | 2018-03-10 | Technical
16 | Joint PQQ Evaluation Board to shortlist suppliers to invite to Tender stage |  | 2018-03-11 | 2018-03-12 | 2018-03-12 | Commercial/Technical
17 | Inform Unsuccessful Suppliers |  | 2018-03-13 | 2018-03-13 | 2018-03-13 | Commercial/Technical
STAGE 3 - Tendering Stage
18 | Invite Successful potential Suppliers to submit a Tender |  | 2018-03-14 | 2018-03-14 | 2018-03-14 | Commercial
19 | Publish Contract Bidders Notice in DCO, informing industry of who will be bidding |  | 2018-03-14 | 2018-03-14 | 2018-03-14 | Commercial
20 | Publish ITT, SOR and Contract T's&C's on Contracts Finder for Transparency |  | 2018-03-15 | 2018-03-15 | 2018-03-15 | Commercial
21 | Potential Suppliers put their bids together | 38 | 2018-03-14 | 2018-04-24 | 2018-04-24 | Bidders
22 | Respond to Clarification Questions , sharing information with all bidders. |  | 2018-03-14 | 2018-04-16 | 2018-04-16 | Commercial/Technical
STAGE 4 - Tender Assesment Stage
23 | Receive Tenders for assesment |  | 2018-04-26 | 2018-04-26 | 2018-04-26 | Commercial
24 | Commercial assessment of Tenders |  | 2018-04-26 | 2018-05-17 | 2018-05-21 | Commercial
25 | Technical assesment of Tenders |  | 2018-04-26 | 2018-05-17 | 2018-05-21 | Technical
26 | Joint Tender Evaluation Board to determine winning Bidder |  | 2018-05-18 | 2018-05-25 | 2018-05-22 | Commercial/Technical
27 | Obtain Commercial & technical sign off from management |  | 2018-05-25 | 2018-05-25 | 2018-06-06 | Commercial/Technical
28 | Inform Successful Bidder |  | 2018-05-26 | 2018-05-26 | 2018-06-06 | Commercial
29 | Inform Unsuccessful Bidders (DEFFORM 157) |  | 2018-05-26 | 2018-05-26 | 2018-06-06 | Commercial
30 | Standstill Period where Bidders can challenge decision and/or request a debrief | 10 | 2018-05-26 | 2018-06-05 | 07/06/2018* | *Date of start of Standstill
STAGE 5 - Contract Award & Debrief Stage
31 | Award Contract & Acceptance | 10 | 2018-06-05 | 2018-06-15 | 2018-06-21 | Commercial
32 | Debrief Unsuccessful Bidders if required. (Within 15 days of request) |  | 2018-05-29 | 2018-06-20 |  | Commercial/Technical
Key
Colour | Party Responsible
Bidders
AIAC
Technical
Commercial
Commercial/Technical/Finance
Commercial/Technical
Formulas:
Start Date = SUM([Achieved, row above]+1)
Start Date = SUM([Target Date, row above]+1)
Target Date = SUM([Start Date]+30)
Target Date = SUM([Start Date])
Achieved = SUM([Target Date])