| CHANGE CONTROL NOTICE (CCN) |  |  |  |
| --- | --- | --- | --- |
| Contract Title: | Contract for the Provision of Social Value Development Support (The Contract) |  |  |
| Contract Reference: | CCCM25A01 | Contract Change Number: | CCCM25A01-1 |
| Date CCN issued: | 23/9/2025 | Date Change Effective from: | 1st October 2025 |
| Between: Crown Commercial Service (The Buyer) and Smartsourcing Limited (The Supplier) - The Contract is varied as follows: - A six-month extension is being utilized from 1st October 2025 to 31st March 2026. - There is an increase in value of £55,440 excluding VAT in line with the extension being utilised. Therefore, the new contract value is £131,040 excluding VAT including the extension option. - Words and expressions in this Change Control Notice shall have the meanings given to them in the Contract. - The Contract, including any previous Contract changes, authorised in writing by both Parties, shall remain effective and unaltered except as amended by this Change Control Notice. |  |  |  |
| REDACTED TEXT under FOIA Section 40 Personal Information. REDACTED TEXT under FOIA Section 40 Personal Information. Change authorised to proceed by: (Buyer’s representative): Signature Print Name and Job Title Date |  |  |  |
| REDACTED TEXT under FOIA Section 40 Personal Information. REDACTED TEXT under FOIA Section 40 Personal Information. Authorised for and on behalf of the Supplier: Signature Print Name and Job Title Date |  |  |  |
| REDACTED TEXT under FOIA Section 40 Personal Information. REDACTED TEXT under FOIA Section 40 Personal Information. Authorised for and on behalf of the Buyer: Signature Print Name and Job Title Date |  |  |  |