## Control Page
NUMIDIAN LoCL Risk Register
| Name | Post title | Date
Created by | Ruth Stallard | LWC-Progs-PM-SO1G | 2021-10-19
Endorsed by
Version | Author | Reason | Date
0.1 | Ruth Stallard | Initial document creation | 2021-10-19
0.2 | Kate Cowley | Updated format | 2022-02-01
0.3 | PT | Reviewed by PT | 2022-03-11
0.3 | Fionnuala Vinaccia | Reviewed by SMEs and updated | 2022-03-10

## Risk Register
ID | DEFCON | Title | RIO Cause | RIO Event | RIO Effect (Consequence) | Threat/ Opportunity | Risk Response | Risk owner | Response Status | Cost Assumptions / Evidence | Inherent Impact | Inherent Probability | Inherent Score | Pre-Mit Likelihood | Pre-Mit Cost Minimum | Pre-Mit Cost Most Likely | Pre-Mit Cost Maximum | Mitigation activities | Residual Impact | Residual Probability | Residual Score | Post-Mit Risk Likelihood | Post-Mit Cost Minimum | Post-Mit Cost Most Likely | Post-Mit Cost Maximum | Proposed Limitation of Contractors Liability
1 | DEFCON 76 | DEFCON 76 - Terrorist attack by Contractor personnel | Terrorist Attack | Terrorist Attack leading to injury or loss of life to contractor staff or MOD personnel | 1. Death of personnel. 2. Infrastructure and equipment damage. 3. Fire. 4. Reputational damage. 5. Delay, Stop, change to MOD activity. | Threat | Transfer | Supplier | Live (?) | Personnel - £45M Cost of MOD activity - £2M Cost of MOD Property - £5M £1.5M per person (assume 30 pax) Proportion of the contract value assumes that Ex in question cancelled and future Exs cancelled Based on the amount of buildings/ property on Ex areas | E - Critical | 2 - Low | 19 | 0.01% |  |  | £52M | 1. Security checks. 2. Vetting. 3. Risk Assessments (MOD and Contractor), Arms Licences, Training, ID Badges, Nominal Roles, Briefings. | E - Critical | 1 - Very Low | 18 | 0.005% |  |  | £10M | £10M
2 | DEFCON 76 | DEFCON 76 - Accident involving contractor delivered training at MOD Site - vehicles | 1. Inadequate training 2. Failure to maintain vehicles 3. Negligence 4. Unforeseen incidents | Contractor crashes vehicle | 1. Death of personnel. 2. Severe personal injury. 3. Infrastructure damage. 4. Damage to vehicle. 5. Loss of livestock life. 6. Fire. 7. Reputational damage. 8. Delay, Stop, change to MOD activity. | Threat | Transfer | Supplier | Live (?) | Assumes 3 pax - £4.5M Infrastructure - minor Vehicle - minor Livestock - minor Fire - minor All - £0.5M Military intel | E - Critical | 3 - Medium | 22 | 5% |  |  | £5M | 1. Provision of roadworthy vehicles. 2. Policies and processes. 3. Medical/first aid response. 4. Valid training for white fleet and green fleet vehicles. 5. Pre-training recces. 6. Scenario rehearsals. | E - Critical | 2 - Low | 19 | 2% |  |  | £250K | £250K
3 | DEFCON 76 | DEFCON 76 - Accident involving contractor delivered training at MOD Site - weapons | 1. Inadequate firearms training 2. Faulty equipment 3. Negligence | Contractor causes accident involving weapons | 1. Injury to personnel. 2. Damage to equipment. 3. Reputational damage. 4. Delay, Stop, Change to MOD activity. | Threat | Transfer | Supplier | Live (?) | Injury - minor £0.5M Equipment - minor £2K Reputational - NA Delay etc - NA All - £502K | C - Major | 2 - Low | 8 | 3% |  |  | £0.502M | 1. Medical/first aid response. 2. Staff H&S Training. 3. Contractor and MOD Risk Assessments. 4. Policy Pamphlets. 5. Weapons handling tests. 6. Provision of appropriate GFE. | C - Major | 1 - Very Low | 4 | 1% |  |  | £10K | £10K
4 | DEFCON 76 | DEFCON 76 - Accident involving contractor delivered training at MOD Site - prohibited areas | 1. Inadequate battlefield simulation or pyrotechnics training. 2. Faulty equipment. 3. Negligence. 4. Personnel ignores guidance and enters a prohibited zone. | Contractor injures MOD personnel due to use of battlefield simulation and pyrotechnics or in the live firing area. | 1. Death of personnel. 2. Injury to personnel. 3. Damage to equipment. 4. Fire. 5. Reputational damage. 6. Delay, Stop, change to MOD activity. | Threat | Transfer | Supplier |  | Assumes 3 pax - £4.5M Infrastructure - minor Vehicle - moderate Fire - minor All - £0.5M Team discussion | E - Critical | 2 - Low | 19 | 3% |  |  | £5M | 1. Medical/first aid response. 2. Staff H&S Training. 3. Contractor and MOD Risk Assessments. 4. Policy Pamphlets. 5. Cordon Notices. 6. Weapons handling tests. 7. Fire response. | E - Critical | 1 - Very Low | 18 | 1% |  |  | £250K | £250K
5 | DEFCON 76 | DEFCON 76 - Injury caused by make-up ie CASSIM | 1. Inadequate Safety standards guidance and training. 2. Negligence. 3. Failure to comply with Safety standards. | Injury to contractor personnel. | 1. Allergic reaction leading to death. 2. Allergic reaction leading to injury. 3. Damage to equipment/clothing. | Threat | Transfer | Supplier |  | 1 pax - £1.5M Injury - minimum Minimum damage to clothing etc | E - Critical | 2 - Low | 19 | 3% |  |  | £1.6m | 1. Fully trained and qualified make-up artists. 2. Patch-tests. 3. Use of hypo-allergenic products. 4. Use of washable products. 5. Medical/first aid response. 6. H&S Training. | A - Minor | 1 - Very Low | 1 | 0.05% |  |  | £5K | £5K
6 | DEFCON 76 | DEFCON 76 - Contractor fails to follow force protection measures regarding COVID-19 | 1. Inadequate Exercise guidance training. 2. Inadequate Notices / Policies / Rules and Regulations. 3. Negligence. 4. Lack of/or inadequate equipment. | Spread of the virus. | 1. Illness. 2. Loss of life. 3. Reputational damage. 4. Delay, Stop, Change to MOD activity. | Threat | Transfer | Supplier |  | £3M Information from other Projects / discussions with Commercial | E - Critical | 2 - Low | 19 | 5% |  |  | £3M | 1. Medical/first aid response. 2. Staff H&S Training. 3. Contractor and MOD Risk Assessments. 4. Policy Pamphlets/Government guidance. 5. Adequate PPE and testing. | E - Critical | 1 - Very Low | 18 | 1% |  |  | £0K | £0K
7 | DEFCON 514 | DEFCON 514 - Contractor performance | Contractor performance falls significantly short of the contract terms and agreed KPIs eg availability of SQEP personnel. | Leading to the Authority activating contract termination clauses | Resulting in a gap in service while alternative commercial arrangements are found. | Threat | Transfer | Supplier |  | £10M PT discussion / Other Projects LoCL information. Discussed further with Commercial | E - Critical | 2 - Low | 19 | 1% |  |  | £10M | 1. Robust KPIs to monitor Contract performance with Payment plan linked to performance. 2. During tender evaluation the Supplier should confirm: a. Security procedures and valid proof conforming to MOD standards for both information and facilities; b. Demonstrate schedules and contingencies to ensure constant availability of platform; c. Inventory management and through life management procedures; d. Contingency plans for loss of persons and/or personnel due to ill-health or other reasons; e. Fire procedures. | E - Critical | 1 - Very Low | 18 | 0.5% |  |  | £5M | £5M
8 | DEFCON 611 | DEFCON 611 - Accident involving contractor delivered training at MOD Site - Fire | 1. Failure to follow H&S Procedures. 2. Failure to follow Fire Regulations. 3. Inadequate training. 4. Sabotage. | Contractor causes fire. | 1. Death of personnel. 2. Injury to personnel. 3. Damage or destruction of buildings. 4. Damage or destruction of vehicles or equipment. 5. Damage or destruction of land, including wildlife. 6. Delay, Stop, change to MOD activity. | Threat | Transfer | Supplier |  | Personnel - £6M Cost of MOD activity - £2M Cost of MOD Property - £5M £1.5M per person (assume 4 pax) Proportion of the contract value assumes that Ex in question cancelled and future Exs cancelled Based on the amount of buildings/ property/land/wildlife on Ex areas | E - Critical | 2 - Low | 19 | 2% |  | 50000000 | £13M | 1. Medical/first aid response. 2. Staff H&S Training. 3. Contractor and MOD Risk Assessments. 4. Policy Pamphlets. 5. Contractor undertakes Fire Safety Training. 6. Compliance checks against Fire Safety Regulations. 7. Fire Extinguishers. | E - Critical | 1 - Very Low | 18 | 0.5% |  | 5000000 | £2M | £2M
9 | DEFCON 612 | DEFCON 612 - Loss, damage or theft of GFE/X - See Annex TBC | 1. Inadequate training. 2. Insufficient supervision. 3. Failure to maintain assets. 4. Negligence. 5. Unforeseen incidents. | Loss, damage or theft of assets. | 1. Costs associated with replacement of equipment/vehicles. 2. Assets fall into the wrong hands. 3. Delay, Stop, Change to MOD activity. | Threat | Transfer | Supplier |  | Replacement - £1M Assets - minimum PT and commercial discussions | C - Major | 4 - High | 17 | 10% |  |  | £1M | 1. Policies and Processes. 2. Site CCTV capability. 3. Training. 4. Adequate equipment maintenance. 5. Search by guards on exit from site. 6. Contractor(s) to be correctly booked on to site. 7. Completion of all details on Site Notification/ Booking form(s). 8. Report to the police. | B - Moderate | 3 - Medium | 9 | 7.5% |  |  | £500K | £500K
10 | Residual Risk | Security breach | 1. Failure to follow Security Procedures. 2. Inadequate training. 3. Sabotage. 4. Negligence. | Contractor commits security breach. | 1. Leaked information of serving personnel and/or site security. 2. Terrorism incident resulting in injury or loss of life. 3. Reputational damage. 4. Personal impact on personnel. 5. Loss of IT asset/equipment. 6. Delay, Stop, Change to MOD activity. | Threat | Transfer | Supplier |  | Team discussion £150M based on other Projects (BESTLA / ASC) | E - Critical | 3 - Moderate | 22 | 5% |  | 150000000 | £150M | 1. Contractor security checks. 2. Contractor personnel attend security briefings. 3. Physical security measures on site. 4. Data security. | E - Critical | 1 - Very Low | 18 | 2% |  | 10000000 | £10M | 10000000
11 | Residual Risk | Supply Chain Issues | 1. Failure to provide vehicles. 2. Failure to provide clothing/costumes. 3. Failure to provide adjuncts. 4. Failure to provide cassim. | Contractor fails to provide vehicles and clothing etc for the MOD training activities | 1. Delay, Stop, Change to MOD activity. | Threat | Transfer | Supplier |  | Commercial input £10K | C - Major | 2 - Low | 8 | 2% |  |  | £10K | 1. MOD to assist with provision of vehicles. 2. MOD to assist with provision of clothing/costumes. | C - Major | 1 - Very Low | 4 | 0.5% |  |  | £2K | £2K
12 | Residual Risk | Travelling Overseas |  | Travelling overseas - CONDO Defcon (full or half). Medical, crashes etc. when abroad. | To confirm
13 | Residual Risk / DEFCIB 514 Delivery | Service Delivery | 1. Failure to cover overheads to provide capability | Contractor cannot cover their own overheads to provide capability. | To confirm

## DEFCON Definitions+Indemnities
Contractor Liability Policy (Link)
Defcon | Definition
DEFCON 76 | Contractor’s Personnel at Government Establishments;
DEFCON 514 | Material Breach;
DEFCON 611 | Issued Property;
DEFCON 612 | Loss of or Damage to Articles.
A LoCL cap for a fifth head of loss | For all residual risks not covered by the four above heads of loss must be included.
Indemnities Table
Indemnity | Minimum grade/SME to authorise use | Owner
DEFCON 91- Intellectual Property Rights in Software * | Commercial Officer discretion with DIPR advice | Defence Intellectual Property Rights Team
DEFCON 514A – Failure of Performance under Research and Development Contracts | Commercial Officer discretion in accordance with DEFCON guidance | Commercial Policy Team
DEFCON 600 – Guided Weapons Trials and Indemnity | Commercial B2 / Level 4 | Commercial Policy Team
DEFCON 632 – Third Party Intellectual Property – Rights and Restrictions * | Mandated | Defence Intellectual Property Rights Team
DEFCON 638 - Flights Liability and Indemnity | Commercial B2 / Level 4 | Commercial Policy Team
DEFCON 656A – Termination for Convenience * | For contracts under £5M -Commercial Officer discretion in accordance with DEFCON guidance | Commercial Policy
DEFCON 656B – Termination for Convenience * | Mandated for all contracts over £5M | Commercial Policy
DEFCON 661/A – War Risk Indemnity | Commercial B2 / Level 4 | Commercial Policy Team
DEFCON 662 – Salvage and Towing Indemnity | Commercial Officer discretion in accordance with DEFCON guidance | Commercial Policy Team
DEFCON 663 – Shipbuilding Indemnity | Commercial B2 / Level 4 | Commercial Policy Team
DEFCON 684 – Limitation Upon Claims in Respect of Aviation Products | Commercial B2 / Level 4 | Commercial Policy Team
Excessive Profits and Loss Indemnity – QDC contract of £50m and over | Commercial Officer discretion in accordance with Single Source guidance. | Single Source Advisory Team
Must apply by legislation (SSCR Regs 16 & 17).
Excessive Profits and Loss Indemnity – QDC under £50m | Commercial Officer discretion in accordance with Single Source guidance. | Single Source Advisory Team
Above applies unless MOD deactivates with DEFCON 803. MOD discretion in accordance with Single Source guidance
Excessive Profits and Loss Indemnity – non-QDC over £5m | Commercial Officer discretion in accordance with Single Source guidance, using DEFCON 811, in accordance with non-QDC Single Source guidance | Single Source Advisory Team
Nuclear Risks Indemnity | CLS & Commercial Policy | Commercial Policy Team
Transfer of Undertakings (Protection of Employment) TUPE | Commercial Policy Team | Commercial Policy Team