## Understanding the Customer

## Research brief

#### Exploring Business reporting errors and how these can be addressed within software design

July 2016

Background, business objectives and previous research

Making Tax Digital (MTD) was announced at Budget 2015, with more detailed business specific commitments (MTDfB) announced at Autumn Statement 2015 and in the Roadmap https://www.gov.uk/government/publications/making-tax-digital, published in December 2015.  It is a core element of HMRC’s transformation which seeks to deliver greater voluntary compliance, improved HMRC operational efficiencies and enhanced customer experience, by integrating tax into day to day business processes, removing the need for an annual return for many business customers. A collection of consultations around specific elements of the Making Tax Digital reforms was published in August 2016 (https://www.gov.uk/government/collections/making-tax-digital-consultations).

MTD will require businesses to keep their records digitally and to update HMRC on a quarterly basis. Qualitative research and co-design with small unincorporated businesses is needed to develop HMRC’s understanding of the reasons for common, simple and technical errors, and how they might be most effectively addressed within MTD design.

Background: Making Tax Digital for Business (MTDfB)

HMRC's vision is for a personalised service designed around our customers’ specific needs, built on digital tax accounts and making better use of data (including the data HMRC holds). MTDfB will transform HMRC's interaction with customers growing voluntary compliance through the use of digital tools; updating HMRC quarterly rather than completing an annual return, and offering the opportunity to move payment onto a ‘pay as you go’ basis, providing customers with certainty and convenience.

MTDfB will require most business customers (including, self-employed, partnerships, companies and some landlords) to keep their business records digitally (using third party produced software) and to update HMRC quarterly. Through MTDfB, HMRC aims to make tax administration more straightforward and less burdensome for UK businesses by integrating tax into day to day business processes; harnessing the digital tools of today to deliver the tax services of tomorrow.

MTDfB will mean businesses being able to send tax data to us digitally, using the sorts of devices (pc’s, smartphones, tablets) many already use. Third party software or Apps will link securely into HMRC’s systems, allowing taxpayers to submit data to HMRC more easily and information we already hold will no longer need to be re-supplied. In order to achieve this our policy, products and processes will be simplified and aligned across different taxes.

MTDfB will engender voluntary compliance for businesses.  It will deliver significant tax and customer benefits firstly by a move to digital record keeping; and then secondly through the incorporation of prompts and nudges within the third party software that directly addresses the reporting errors/ carelessness at source (e.g. at point of data entry/update). The digital tools will highlight errors made by customers and prompt for information which otherwise might have been overlooked, providing more certainty for businesses that they are reporting what is required of them and have got their tax right.

There are two broad categories of error that third party software has potential to address through the incorporation of nudges and prompts.  These are:

- Simple errors such as transposition; arithmetic and omission from loss of receipts and invoices which will be addressed by keeping records digitally; and

- Technical errors where customer misunderstanding/ lack of knowledge / confidence with the tax rules (e.g. allowable expenses or capital costs) that results in underpaid tax and which will be addressed via ‘nudges and prompts’.

There is a need to demonstrate the effectiveness of our design (via prompts and nudges) in relation to technical errors and more evidence is needed to demonstrate the potential for software to also address at source these technical errors. This research will explore the views of businesses; alternative engagement with agent stakeholders is underway.

By involving customers in the design of prompts and nudges that would be presented to them within the software to address errors at source, insight gained from the co-design research will support:

- Delivery of tax gap benefits through the reduction in errors by the provision of effective error messages and prompts to address the underlying behaviours in real time

- An improvement in business customer experience in managing their tax affairs, through the provision of timely, targeted and supportive messages to address  error behaviours and provide customers with, for example, greater clarity on what is required of them, greater reassurance that they are performing the appropriate actions

- Potentially enhance the role of agents by leveraging their engagement to address potential risks before submission.

This research and planned user research to test developed prototypes

This qualitative research will explore in-depth the underlying causes of an initial, prioritised selection of c.5 error types including both simple and technical errors (see i and ii above). A co-design element of the planned study will explore with businesses how best to design the prompts and nudges to more effectively address the identified underlying causes.

Research Objectives

The aim of this research is to both inform HMRC’s understanding of the reasons common (simple and technical) errors are made by business customers and inform the design of nudges and prompts embedded in third party software to address effectively the underlying error causing behaviours.

More specifically, the objectives for this research are to:

- Explore businesses current reporting behaviours relevant to identified simple and technical errors e.g. record keeping practices, use of accounting software, level of expertise in accounting and tax, how they currently go about reporting to HMRC, use of agent to finalise the return and check data (where appropriate)

- Explore and identify customer behaviours and decisions underlying and resulting in the errors.  This will be considered across a range of business types and sectors, where they are most common and costly in tax yield terms

  - e.g. inadvertent error arising from slip in data entry or memory lapse, rule or knowledge based mistake arising from lack of knowledge or confidence, poor record keeping practices, through to deliberate non-compliance (routine, situational or exceptional)

- Identify where upstream intervention is needed at point of data entry (and potentially on updating HMRC within the Business Tax Account), and how software nudges and prompts might address underlying behaviours and decisions (including, where relevant, how it affects their use of agents in checking data)

- Co-design with customers how software prompts and nudges would be best developed and presented (e.g. wording, timing, approach to delivery) to:

  - most effectively engage customers to address the causes of errors to reduce the likelihood of those errors being made at the point of reporting and

  - enable a positive overall customer experience in using MTD software and minimise any potential negative customer experience impacts (e.g. resulting in disengagement or unintended impacts on contact, trust in the software/HMRC and/or compliance)

- Identify areas where any signposted HMRC guidance would need to be amended in order to maximise the effectiveness of presented nudges and prompts

Proposed Methodology

Methodology and stimulus

To address these objectives, this research will be qualitative in nature incorporating a co-design element. It will include two stages reconvened over a short time frame.

Your expertise will be essential here, and we do not wish to be overly prescriptive in defining the methodology. We expect to work collaboratively with the successful agency following the appointment to further develop and agree the best approach to the work.  However, we envisage the following stages and methods.

Stage 1: Depth interviews. The research will comprise of a series of depth interviews, with an ethnographic element, that explores with businesses their current reporting behaviours in relation to common errors.

Based on the analysis of common errors, interviews will be arranged with types of businesses within particular sectors identified as being more prone to making the errors identified.  The interviews will explore the factors influencing their reporting in relation to those errors. It may be challenging to observe actual reporting behaviour within a real life situation, so it is possible that this could also include scenarios to explore potential areas where businesses may make errors based on lack of technical knowledge and/or may make numerical errors or overlook data that should be entered.  These would need to be as close as possible to the businesses own circumstances and data.

Stage 2: Co-design mini group discussions. After initial exploration with businesses around their current reporting behaviours and the reasons underlying their decisions and behaviours that lead to, or increase the likelihood of making those errors, participants will be reconvened for a second phase of the research undertaken in mini-group discussions.  The mini-discussions will comprise a co-design element, whereby participants (from both the small businesses and agents) will explore with HMRC staff approaches to addressing the factors underlying the errors within software design.

This stage will include the use of stimuli, including early prototypes and possible customer journeys within the software design, where available, and will explore design principles that customers feel will most effectively help them to avoid making errors within their reporting, whilst not negatively impacting on their experience of using the software.

We expect to work closely and collaboratively with the successful agency to develop stimuli that will help prompt discussion and co-design of solutions in a constructive way.

We will be looking for your recommendations on stimulus considerations in your proposal.

Sampling and target audiences

We expect the winning agency to free-find the sample for this work - please advise on any particular challenges associated with this.

The primary target audience is unincorporated small businesses. The research will focus on a small number of agreed error types (up to 5) to include both simple and technical errors. The research will include customer groups from a small number of sectors (c.4).

Within this we would want a good cross-section, where feasible, across the sectors identified, of:

- Business size and type – including small and micro businesses, sole traders and those with secondary income over £10k from self-employment and/or property income (as the focus is unincorporated businesses, this is likely to be slanted heavily to sole traders/micros)

- Taxes engaged with – those in self-assessment alone, as well as those who are also VAT registered.

- Digital capability – including some who are less digitally confident.

- Use of Agents – focussing on unrepresented customers and those customers who are represented, but only use an agent for finalising their tax return (i.e. they do their record keeping in house). The balance of this should be slanted to unrepresented customers (c. 2/3)

While we would like to include some mix of digital confidence and record-keeping practices within the sample, we believe the co-design stage would be more constructive with businesses who do not have substantial barriers to using digital record-keeping tools per se.  We think it is likely that we should separate those customers using Agents for finalising their return from unrepresented customers in any co-design session. .

Geographical location should fall out naturally, due to the spread of business sectors covered. However, the design should ensure a good geographical spread across the country and where feasible a reasonable mix of demographics as relevant to the business sectors sampled.

What we need from you – the deliverables

The Proposal

The proposal submitted should include:

- Understanding of the research brief

- A detailed breakdown of your research design, including sampling proposals and clear rationale for the methods you propose

- Timetable

- Personnel, including background and experience

- Whether any part of the project will be subcontracted, and if so to whom

# The proposal should specify who will be responsible for delivering this project and should provide detail of the input into the project that will be provided by each named person.

We expect to discuss the requirements and the approach in more detail at set up.

Please let us know on receipt of this brief whether you think there will be any conflict of interest in your submitting a proposal.

Project Deliverables

Interim Deliverables/Requirements

- A set up meeting with the project team and key stakeholders

- Detailed implementation plan and timetable for the research

- Progress reports to designated HMRC team (weekly)

- An opportunity for wider stakeholders to view the co-design groups, where facilities allow.

- Interim findings (in Powerpoint),  focussing on the key areas of evidence from Phase 1, with a summary of key findings.

- Project meeting to discuss the findings and inform design of materials for Phase 2

Final Deliverables

- Face to face presentation of the findings in PowerPoint), plus Q&A session

- Full report (slide pack) for internal use with a summary of key findings up front.  This should document analysis, findings and insights in an engaging manner with supporting quotes, providing clear recommendations for future action and implementation (approx 40-50 slides).

- Publication report suitable for publishing on gov.uk (c. 10 pages in MS Word format) to a set publication template to be provided

- A one page, engaging,  stand alone summary of the research including key findings and insights which can be circulated to stakeholders and published on our internal Customer zone.

Our project timeline

The timings below are an estimate and will be reviewed and agreed at the set up meeting.

| Activity | Date | Availabilities |
| --- | --- | --- |
| Brief sent out | By midday 5th July |  |
| Proposal returned | By midday 12th July |  |
| Project set up meeting | w/c 11th July – ideally 13th or 15th July |  |
| Design of Phase 1 fieldwork materials | w/c 11th – 25th July |  |
| Phase 1 qualitative fieldwork | 27th July – 12th August |  |
| Phase 1 analysis | w/c 15th August |  |
| Interim Phase 1 findings | To be sent Monday 22nd August, with working session w/c 22nd August to inform design of Phase 2 |  |
| Design of Phase 2 co-design fieldwork materials | w/c 22nd August – 2nd September |  |
| Phase 2 Fieldwork | w/c 5th September – 15th September |  |
| Phase 2 analysis and prep for debrief presentation | w/c 12th September – 23rd September |  |
| Topline Phase 2 findings issued to HMRC | By 16th September |  |
| Draft Debrief Presentation slides to HMRC | Min 3 working days prior to the debrief presentation |  |
| Debrief Presentation (face-to-face) to HMRC | End w/c 26th September |  |
| Final report delivered | Early October |  |
| Publication report (initial draft delivered to HMRC) | Mid October |  |

Budget

- The maximum budget for this research is £50K (excluding VAT).  Please provide a cost for the project design set out above and set out alternatives if you feel these would better meet the research objectives.

Costs must include, staff day rates, travel and other expenses, broken down separately. Costs should include all fees and expenses but exclude VAT.

Please include any costs for viewing facilities where relevant.

General Terms and conditions

On receipt of a satisfactory proposal, the successful research agency will be awarded a fixed price contract for the project. The Standard Conditions of Contract governing research commissions are laid down by the MR130001 framework agreement and are not negotiable.  HMRC observes the general practice of paying only for work satisfactorily completed. All work should comply with the Code of Conduct of the Market Research Society. The Standard Conditions of Contract are available on request.

Payment terms have been negotiated to split as follows on most projects (however there will always be exceptions – which we will do our best to cater for)

30% on commission

30% on Fieldwork commencement

40% on completion

When costing proposals it would be helpful to ensure we can see these key stages clearly.

Some key elements of our standard terms are below:

Contractual obligations

As a result of government policy to achieve greater transparency in public procurement and help deliver improved value for money, HMRC is obliged to publish tender documents for all contracts with a whole life value of over £10,000.  There is a further obligation to publish all contracts with a whole life value of over £10,000 with effect from January 2011.  It is a condition of bidding for this work that applicants accept these obligations and agree to the subsequent publication of the contract once awarded.

Data handling

In most cases, any data we supply will be encrypted, probably using the highest encryption used by Winzip v9 or above. It is your responsibility to ensure appropriate steps are taken to ensure you are able to receive and decrypt our data.

We also require confirmation at appropriate times of the deletion of customer records from both removable and fixed media within your organisation.

Please note that HMRC does not permit the use of USB sticks and so all electronic versions should be provided on CD.

Once appointed, you should agree with your HMRC contact what security rating any data or documentation you produce should have and how it subsequently should be handled.

As part of our standard data handling requirements, as part of your proposal we will require details of your plan to receive, store and use any data that we may supply to you. In most cases the data we supply to you will contain customers’ personal details and we need to be sure that you will treat this data appropriately.

This should include precise details of the data handling and security procedures you have in place. In particular, please detail how, once we have delivered the data to you, how you will transfer and store it and who in your organisation will be able to access it. You should also detail your processes for archival of and/or destroying the data that has been finished with. As an example this should include, what systems you have that are accessible from the internet, how access to the information is managed, and details of how your data servers are backed-up and maintained.

If you have supplied current information, this does not need to be provided again.

Documentation

HMRC will require the publishable report delivered in both pdf and word formats. The pdf document should include the file size as part of the filename.

In addition, HMRC will require draft copies of all key documents, such as recruitment questionnaires, presentation charts, top line and final report. These are to be submitted in sufficient time for comments to be incorporated into the final version and for our approval to be given for production of the final version to take place.