## Task
Attachement 4 - Pricing Schedule
Provision of Literature Review on Impacts of Infrastructure CCZZ19A86
Please note: Suppliers are asked to provide firm prices for each element of the requirement detailed in Attachment 3 - Statement of Requirements. Cells highlighted in green denote the cells which need to be populated by suppliers. All prices must be in GBP (£) and exclude VAT. Prices must remain valid for thirty (30) days following the bid submission deadline. Any prices not detailed within this Pricing Schedule will be deemed to have been waived.
Supplier Name: | ****Please Insert Name here***
Description |  | Task | Role |  | Cost | Quantity | Total Price (exc VAT)
Number of Days
Project inception meeting with NIC to include: agreed refinements to the scope of the literature review, clarifying approach to be taken by the Potential Provider to the project. w/c 1st of June | [6 empty] | 0
Expert panel input into the literature review scope w/c 1st of June | [6 empty] | 0
Interim summary paper to be provided to the NIC. w/c 22nd of June | [6 empty] | 0
NIC to provide feeback and comments on the interim report, potentially including comments from the expert panel. w/c 22nd of June | [6 empty] | 0
Draft final report to be provided to the NIC. w/c 27th of July | [6 empty] | 0
NIC final comments on draft w/c 3rd of August | [6 empty] | 0
Final draft of final report to be submitted to NIC. w/c 17th of August | [6 empty] | 0
Delivery and Any Additional Costs Associated with the Provision of the above Services
Please insert description here | [6 empty] | 0
Total Price (exc VAT) | [6 empty] | FALSE