## Sheet1
ESTATES
AIR: PROJECT HANDOVER CONTROL SCHEDULE
Project Name/Contract Ref: | [6 empty] | Appendix A
MAXIMO Code:
|  | Required | Responsible Person | Agreed Date for | Sign-off by | Sign-off by | Comment
|  | Y/N | for Sign-off | Production of Information | Responsible Person | Project Manager
PART A | Mandatory items to be signed-off and documentation to
be provided TWO WEEKS PRIOR to Project Handover
A1 | Insurance
a | Lift Installations - Witness Test | [5 empty] | E&F Project Manager to liaise with Duty Holder
b | Insurance Office - Notification of handover & insurance valuation (>£0.1M)
A2 | Manuals & Other Information
a | Draft Health & Safety File | [5 empty] | See Asset Information Requirements, Appendix B for details
b | Draft Operation & Maintenance Manuals | [5 empty] | See Asset Information Requirements, Appendix C for details
c | Draft Building Emergency Folder
PART B | Mandatory items to be signed-off and documentation to
be provided AT Project Handover
B1 | Consents
a | Planning Consent
b | Building Control Certificate
c | Other Statutory Body Approval
d | Copy of Practical Completion Certificate
B2 | Testing and Commissioning Certificates
a | Electrical Test Certificates
b | Fire Alarm Test Certificate / Installation Log Book / Manual (see note 1)
c | Emergency Lighting Test Certificate
d | Security Installations / Access Control
e | Gas Suppression Installations
f | Disabled Alarms
g | Lightning Protection Commissioning Certificates
h | Natural Gas Installation Certificates/Schematic Drawings
i | HV Installations and Sub-stations Manual (see note 2)
j | Chlorination Certificate(s) (dated <4 weeks from handover) | [5 empty] | See Asset Information Requirements, Appendix L for details
k | Air Cooling and Refrigeration Plant
l | Air Handling Units, Boilers and Plant Room Equipment
m | Acoustic Test Certificate(s)
n | Fume Cupboards and Extract Ventilation
o | Building Management System
p | Lift Commissioning Test Certificates & Manual (see note 3)
q | Pressure Systems / Air Receivers
r | Fire Door and Fire Stopping Certificates
s | Building Air Test Results
t | Air Clearance Certificates for Asbestos Stripping
u | Mansafe System Test Certificates
v | Communication Infrastructure Installations Commissioning
w | Data Installation Test Certificates
x | AV Installations Commissioning
y | Energy Certificates - EPC
z | Drainage System Camera Survey
aa | Medium Combustion Plant Directive: Licence & emissions certification
B3 | Drawings
a | Draft Fire Strategy | [5 empty] | See Asset Information Requirements, Appendix D for details
b | Disabled Access Strategy
c | As-Built Drawings - Architectural | [5 empty] | See Asset Information Requirements, Appendix Q for details
d | As-Built Drawings - Structural | [5 empty] | See Asset Information Requirements, Appendix Q for details
e | As-Built Drawings - Engineering Services | [5 empty] | See Asset Information Requirements, Appendix Q for details
f | As-Built Drawings - Specialist Sub-Contractors | [5 empty] | See Asset Information Requirements, Appendix Q for details
B4 | Manuals / Instructions & Other Information
a | Health & Safety File (incl. Schedule of Outstanding Items) | [5 empty] | See Asset Information Requirements, Appendix B for details
b | Operation & Maintenance Manuals (incl. Schedule of Outstanding Items) | [5 empty] | See Asset Information Requirements, Appendix C for details
c | Snagging List (incl. Schedule of Outstanding Items/Remedial Programme)
d | Access and Maintenance Strategy | [5 empty] | (See note 4 below)
e | Cleaning Strategy and Recommendations | [5 empty] | See Asset Information Requirements, Appendix M for details
f | Project Team Contact List
g | Electricity Meter Reading(s) at Handover | [5 empty] | See Asset Information Requirements, Appendix P for details
h | Gas Meter Reading(s) at Handover | [5 empty] | See Asset Information Requirements, Appendix P for details
i | Water Meter Reading(s) at Handover | [5 empty] | See Asset Information Requirements, Appendix P for details
j | Location Specific Risk Assessments: Plant rooms/Accessible Flat Roofs
k | Building Emergency Folder | [5 empty] | See Asset Information Requirements, Section 4.5 for details
l | Legionella Risk Assessment(s) with Schematic Drawings | [5 empty] | See Asset Information Requirements, Appendix L for details
B5 | Maintenance Agreements and Warranties
a | Copies of all Maintenance Agreements effective during DLP
b | Warranties Information - Design and Product | [5 empty] | To be included in Section ? of O&M Files
c | Security System Installation Record | [5 empty] | See Asset Information Requirements, Appendix N for details
B6 | Keys, Spares and the Like
a | Keys and Suiting Schedule / Signed Schedule | [5 empty] | See Asset Information Requirements, Appendix O for details
b | Spares - Parts and Materials / Signed Schedule | [5 empty] | See Asset Information Requirements, Appendix K for details
c | Plant Keys, Tools, Floor Lifters etc. / Signed Schedule
d | Loaned plant room and other access keys returned to E&F
B7 | Training and Demonstrations
a | Fire Alarm Installation
b | Gas Suppression Systems
c | Disabled Alarm Installations
d | Emergency Lighting
e | Security and Access Control Installations
f | Air Cooling Systems and Refrigeration Plant
g | Air Handling Units, Boilers and Plant Room Equipment
h | Fall Prevention and or Fall Arrest Systems (Mansafe or similar)
I | Building Management System
j | Fire and Emergency Evacuation Procedures
k | Familiarisation of Drainage Routes, Guttering Systems, & Kitchens
l | Lifts
m | Specialist Systems
n | Disabled refuge communications equipment under fire conditions
| I certify that the information required at project handover is complete | Sign Off: At Project Handover (Parts A&B)
BAS Project Manager (On behalf of Project Team)
Date:
Name:
Signature:
I certify that the information required at project handover is complete
Chief Engineer (on behalf of Maintenance)
Date:
Name:
Signature:
PART C | Mandatory items to be signed-off and documentation to
WITHIN ONE MONTH of Project Handover
C1 | Estates Records
a | Space Management Information | [5 empty] | See Asset Information Requirements, Appendix E & F for details
b | Update Asbestos Register | [5 empty] | See Asset Information Requirements, Appendix G for details
c | Estates Management Property Terrier Information | [5 empty] | See Asset Information Requirements, Appendix H for details
d | Asset Register (to E&F approved format) | [5 empty] | See Asset Information Requirements, Appendix I for details
e | Life Cycle Cost Data | [5 empty] | See Asset Information Requirements, Appendix J for details
f | Wayfinding Asset Register (to E&F approved format) | [5 empty] | Information provided using WREN data module.
g | Written Schemes of Inspection (for equipment requiring insurance insp.)
C2 | Drawings
a | As-Built Drawings - Architectural | [5 empty] | See Asset Information Requirements, Appendix Q for details
b | As-Built Drawings - Structural | [5 empty] | See Asset Information Requirements, Appendix Q for details
c | As-Built Drawings - Engineering Services | [5 empty] | See Asset Information Requirements, Appendix Q for details
d | As-Built Drawings - Specialist Sub-Contractors | [5 empty] | See Asset Information Requirements, Appendix Q for details
C3 | Building Information Model & COBie Data
a | Building Information Model | [5 empty] | See Asset Information Requirements, Appendix R, S, T & U for details
b | COBie Data | [5 empty] | See Asset Information Requirements, Appendix R, S, T & U for details
C4 | System Configuration (Within Two Weeks of Project Handover)
a | Configuration of alarm system in Security Control Room
b | Configuration of access control systems/doors | [5 empty] | Campus Card Manager to be informed of all new access controlled doors
PART D | Mandatory items to be signed-off and documentation to
WITHIN 18 MONTHS of Project Handover
D1 | Environmental Performance Data
a | BREEAM Report
| I certify that the information required 1 month after handover is complete | Sign Off: One Month After Project Handover (Part C)
BAS Project Manager (On behalf of Project Team)
Date:
Name:
Signature:
I certify that the information required 1 month after handover is complete
Chief Engineer (on behalf of Maintenance)
Date:
Name:
Signature:
Note 1 | Production/Updating of the Fire Alarm Manual must include the following:
Log Book / Commissioning Certification/Emergency Folder
As fitted drawings
Signed maintenance contract detailing number of visits, SLA and 24/7 contact number
CD of setup config files
Note 2 | Production/Updating of the Sub-Station and HV Manual must include the following:
Schematic of the main HV LV Circuit
Test commissioning values
Original manufactures information
Operating instructions
H&S file
Note 3 | Production/Updating of the Lift Manual must include the following:
PAS32 test certificate
EC Design certificate
EN81-1:98 deviation information
List of fault codes and drive parameters
Details of load weighing setup and calibration
Controller wiring diagrams
Schematic of the safety circuit
Schematic of the main power circuit
Declaration of conformity
Log Book
Rope certificates
Lifting beam certificates
Certificates for safety components
Windcrest auto dialler programming information
Signed maintenance contract detailing number of visits, SLA and 24/7 contact number
1 CD of above information
Note 4 | Access and Maintenance Strategy must include the following:
Strategies to include for due consideration for access and egress of ducts, voids, tanks etc. that may be considered confined spaces such that compliance with the Confined Space Regulations 1997 can be achieved
Details and location of permanent/fixed access equipment
Temporary access points
Full design assumptions for mode/means of access
Details of any plant necessary to achieve safe access
| Details of achieving safe means of access and egress including in emergencies | [5 empty] | Draft Date 2nd April 2019