Invitation to tender

Population health care commissioning support tools – atrial fibrillation and falls and fragility fractures

- Introduction

  - The national Healthcare Public Health team in Public Health England (PHE) is leading a project to support the commissioning and provision of health and care services working together as systems in England, using two areas as exemplars, atrial fibrillation (AF) and falls and fragility fractures (FFF). This project will support PHE in delivering its remit of improving population health through sustainable health and care systems. PHE is seeking a provider to support the delivery of this project.

  - This project comprises five core activities – these will have to be undertaken for both AF and FFF. The provider will have to undertake the first three

    - To collect data from national datasets at CCG and national level on between 20 and 30 indicators identified by PHE for both AF and FFF. These will be from all parts of the health and care system including primary and secondary care and local authorities as well as population data.

    - To collate the data collected into datasets

    - To embed the data into commissioning support documents (tools) for every CCG in the country

    - To disseminate these commissioning support tools.

    - To evaluate the impact of the annual reports on commissioning, provision and outcomes.

1.2 The provider will need to ensure that all outputs are framed within the context of the broader arrangements for similar products provided by PHE.

- Background

  - PHE is the expert national public health agency which fulfills the Secretary of State for Health’s statutory duty to protect health and address inequalities, and executes its power to promote the health and wellbeing of the nation.

  - Public health practice takes place over three domains – health improvement, health protection and healthcare public health. PHE carries out activity in all of these domains. Healthcare public health is concerned with the population aspects of health services. It involves assessing interventions, programmes and services in terms of their: meeting current and future demand; clinical and cost effectiveness; equity and variation; quality, safety and patient experience. When possible it takes a systemic approach, looking across the whole pathway and promoting prevention and early diagnosis. PHE’s healthcare public health activity supports partners including the NHS and local authorities in the commissioning and provision of health and care services.

- Context

  - Health and care services are currently commissioned from and assessed in terms of institutions such as hospitals, professional groups such as general practitioners and jurisdictions such as CCGs and general practitioners. Sir Muir Gray, ex Special Advisor to Duncan Selbie, PHE’s Chief Executive, has developed a model and methodology aiming to support commissioning through outcome-based system assessment and improvement. This involves developing systems centered on populations suffering from the same condition e.g. diabetes, symptom e.g. breathlessness or shared characteristic e.g. older people. Each system model has an aim and related outcome objectives with each objective being associated with one or more measurable criteria. Data on the criteria is entered for local systems, enabling the assessment, comparison and tracking of these systems.

  - The Healthcare Public Health team based in the Health and Wellbeing Directorate has piloted this approach using AF and FFF as exemplars.

  - FFF is a complex area given a) the large number of interacting risk factors that result in falls and b) the large number of services that work with or impact on people with falls. A pilot project was carried out between 2013 and 2014 working with local authority public health teams, chosen for their contacts with a range of falls-related local services and also their health intelligence capacity. A ‘pioneer’ cohort of 13 local authority public health teams with around 10% national population coverage collected data on their local systems. Learning from this allowed the FFF annual report indicator set to be revised.

  - The AF programme aims to improve detection and management for people with AF to prevent AF-related stroke and vascular dementia, which is delivered in primary and secondary care. The AF programme was running for a year before it was brought into PHE, a focus group of key stakeholders helped to develop a dashboard with ~15 metrics. In Year 1, five populations were recruited to report against the dashboard to produce annual reports. Due to updated NICE guidance, learning and development in this area we are reviewing the dashboard.

  - For the next stage of the programme, PHE intends to work with external partners to develop data reports for all English CCGs. These will be populated with data identified by PHE and collected and collated by the provider and then embedded in an annual report containing additional commissioning support information. All data will be collected from national datasets. The reports will provide a benchmark against national performance. PHE will also provide: commentary on data quality; how to interpret the data; priorities for local data collection to support effective service commissioning. There will be rapid turnaround for the project – it is likely to be in the region of around 4 weeks.

- Aims and Objectives

  - Aims

The overall aim of the project is to produce AF and FFF profiles for all English CCGs to support the commissioning and provision of local AF and FFF health and care systems and to highlight the advantages of utilising population healthcare approaches.

This project has five objectives, of which the provider will deliver the first three:

4.1.1 To collect data at Clinical Commissioning Group and national levels on not more than 30 atrial fibrillation related indicators. To carry out a similar data collection exercise as above for Falls and Fragility Fractures also at CCG and national levels.

4.1.2 To collate these data into a FFF dataset and an AF dataset for every CCG in England.

4.1.3 To embed these within a pdf document containing additional information thereby creating a commissioning support tool for every CCG in England for both AF and FFF (ie these are separate documents).

4.1.4 To disseminate the commissioning support tools to key stakeholders at CCG level.

    - To evaluate the impact of the tools on local commissioning and provision

  - To collect data at Clinical Commissioning Group and national levels on not more than 30 atrial fibrillation related indicators. To carry out a similar data collection exercise as above for Falls and Fragility Fractures also at CCG and national levels.

    - The provider will collect data at national and Clinical Commissioning Group levels on not more than 30 falls and fracture related indicators with the list of these indicators being supplied by PHE. All datasets will be national or regional - none will be local ie the provider will not have to collect data from individual CCGs. Data sources for FFF potentially include: ONS, HES, PHOF, ePACT, Falls and Fractures Audit Programme, National Reporting and Learning System, Ambulance Trusts. While most of these data can be accessed online, for several indicators, special requests for data collection may be necessary e.g, Ambulance Trusts. Most of the data for AF can be accessed at a national level (some via special request) from the following sources: QOF, SSNAP, NCVIN, GRASP – AF, & warfarin patient safety, TTR (stroke and bleeding risk), social care.

    - Given that data will be being collected from a number of sources a key aspect of this work will be effective working at pace with stakeholders to access data. So for example, this will include contact with the Royal College of Physicians who deliver both the Falls and Fractures Audit Programme and the Sentinal Stroke National Audit Programme, the National Patient Safety Agency who host National Reporting and Learning System data and Ambulance Trusts.

  - To collate these data into a FFF dataset and an AF dataset for every CCG in England.

The provider will collate these data into two datasets, one for FFF and one for AF, with indicators for every CCG in England, and also at a national level. There will be an indication as to how CCG results relate to national levels i.e. similar, or significantly higher or lower.

  - To embed these within a pdf document containing additional information to create a commissioning support tool for every CCG in England for both AF and FFF (ie these are separate documents).

The provider will embed these datasets within a pdf document containing additional information to create a commissioning support tool for every CCG in England for both AF and FFF (ie these are separate documents). The provider will create numerical and visual displays of the data. Additional information on the document may include references to data quality and local sources of data that CCGs and other stakeholders should collect to support effective commissioning. This will be created by PHE.

4.4. To disseminate the commissioning support tools to key stakeholders at CCG level.

In order to achieve maximum impact in the annual commissioning cycle, PHE plans to disseminate the commissioning support tools in June.

4.5 To evaluate the impact of the tools on local commissioning and provision

PHE plans to carry out an evaluation towards the end of 2016/17 to assess the impact that the tools had on commissioning and service provision.

- Standard information for applicants

  - The sections below provide standard information on different aspects of the project and will contain details relevant to your application.

  - Governance Issues

    - Day-to-day management of this project will be by an identified project lead within the provider organisation.

    - A Project Team will be convened of relevant PHE staff to advise the provider organisation as required and to receive and comment on the drafts of the commissioning support tools.

    - The successful provider must adhere to the Data Protection Act (1998) and the Freedom of Information Act (2000). Effective security management, and ensuring personal information and assessment data are kept secure, will be essential. In particular:

  - Risk Issues and Management

    - Providers should submit, as part of their application, a summary explaining what they believe will be the key risks to delivering this project, and what contingencies they will put in place to deal with them.

    - A risk is defined as any factor which may delay, disrupt or prevent the full achievement of a project objective. All risks should be identified. The summary should include an assessment of each risk, together with a rating of the risks likelihood and its impact on a project objective (using a high, medium or low classification for both). The risk assessment should also identify appropriate actions that would reduce or eliminate each risk, or its impact.

- Reporting Arrangements

  - The PHE lead for this project is Dr Allison Streetly, Deputy Director Healthcare Public Health (Health and Wellbeing Directorate) who will liaise with the provider lead and provide day to day support from PHE. Dr Streetly will be supported by a designated project manager from within the Healthcare Public Health team.

  - The provider will be expected to meet with the PHE lead at the initiation, mid-point and end point of the project and to highlight any risks or issues as soon as possible in writing to the PHE lead. Given the rapid turnaround required for this project, the provider will provide the PHE lead with a weekly progress report via email.

- Dissemination

  - The resources developed during the project will be co-branded by Public Health England and the provider and be available for use free of charge.

  - The intellectual copyright to the resources will be shared between PHE and the provider.

- Budget and Timescale

  - The project has a budget of up to £44800 excluding VAT.

  - The first draft of the tools should be presented to the project team by March 21st 2016 and the project must be completed by 28th March 2016.

- PHE Project Team Access

  - PHE will work to maximum 3 working day response to requests for information and approval from the provider to support this project, wherever possible this will be sooner.

  - The PHE project team shall consist of Dr Allison Streetly, Shakti Dookeran, Daniel MacIntyre and Rachel Juffs.  Other individuals will be included in specific aspects of the discussion with the provider as and when further input is required.

10. Application Process and Selection Criteria

10.1. Applications should be submitted electronically via the BRAVO portal.

10.2 Applications will be assessed equally on the following criteria by members of the PHE panel:

- RELEVANCE -Proposed project plan and methodology to achieving the aims and objectives of the project outlined in section 4 and sections 1

- QUALITY ASSURANCE - Quality Assurance for project plan and proposed management arrangements (including risk statement as outlined in section 5.3) to ensure delivery of the aims in section 4 and sections 1

- STRENGTH- Detail the strength of your team, experience, CVs and site reference of past performance. This will be looked at in conjunction with the amount and the quality of the resources (Rate Card) been offered.

- IMPACT of the proposed work to improve CCG commissioning and local service provision

- VALUE for money (justification of the proposed costs), including Total cost of the bid.

10.3. Applications will be reviewed by an internal PHE panel and candidates will be informed electronically of the result.

10.4. If two or more applications are scored identically, or rate strongly, then relevant applicants will be invited to a verbal presentation.

11. Timetable

11.1. It is anticipated that commissioning of this project will occur to the following approximate timetable:

- Issue of invitation to tender 12 January 2016

- Deadline for receipt of applications: 1200 25 January 2016

- Tender interviews (if required): Week commencing 8 February

- Notification of outcome of applications review: Week commencing 8 February

- Award of contract: Week commencing 15 February

- Project completion: 28 March 2016

Questions regarding this tender should be directed through the Bravo portal messaging facility.