# Annex A

| Title of Project | Effective communications on environmental resilience and security in a changing climate through biodiversity conservation in the UK Overseas Territories |
| --- | --- |
| Date and Time for Return of Bids | Wednesday 19 January 2022 @ 09:00 hours |
| Contract Reference Number | C21-0482-1625 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO ABBIE DOSELL AND SHELLY CANT OR DORA IANTOSCA VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below:- |
| Contacts for Technical Information relating to this Project Specification | Joint Nature Conservation Committee Name: Abbie Dosell Email: Abbie.Dosell@JNCC.gov.uk Tel: 01733 866930 OR Name: Shelley Cant Email: Shelley.Cant@JNCC.gov.uk Tel: 01733 866956 |
| Contact for Queries Regarding the Procurement Procedure | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk or contractqueries@jncc.gov.uk Telephone: 01733 866894 |
| Proposed Start Date | 26 January 2021 |
| Proposed End Date | 21 March 2022 |

Title of Project

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	3

5.	Project Objectives: Detailed Tasks	3

6.	Potential Follow-On Work	3

7.	Outputs	4

8.	Dissemination	4

9.	Timescale	4

10.	Health and Safety	4

11.	Product Specification	4

12.	Project Management	5

13.	Instructions for Bid Submission	5

14.	Evaluation Criteria	6

15.	Payment	7

16.	Additional Requirements	7

17.	References	7

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

The UK’s Overseas Territories (UKOT’s) are highly dependent on the natural environment for their economic and social wellbeing.  They are also reliant on limited infrastructure.  In the Caribbean in particular, this infrastructure, and human life, are vulnerable to both natural and anthropogenic hazards.  The natural environment is itself susceptible to damage from human activities – resulting in loss of value to the economy and reducing its ability to protect assets and human well-being.

Building upon work to date, carried out under Joint Nature Conservation Committee’s (JNCC) Natural Capital in the Overseas Territories programme, and the current Conflict, Stability & Security Fund (CSSF) Disaster Resilience Project and Implementing Coral Reef Action Plans Project this project aims to: develop and disseminate, targeted messages and communications materials to inform key stakeholders of i. the role and value of the natural environment in providing environmental resilience; ii. the pressures upon the natural environment; and iii. the role stakeholders can play in protecting the natural environment.

This project will be executed on six (6) UKOTs within the Caribbean, namely within the Turks and Caicos Islands (TCI), British Virgin Islands (BVI) Cayman Islands (CI), Montserrat, Bermuda and Anguilla.

## Project Background

Climate change poses a serious threat to biodiversity and over the next few decades, may even surpass habitat destruction to become the leading global threat to life on earth (Bellard et al, 2012). The UKOT’s are considered to be particularly vulnerable to the impacts of climate change as they are Small Island Developing States (SIDS), often very low-lying islands and have over 80% of their populations living in the hurricane prone Caribbean and Western Atlantic. It was estimated that in 2017 severe weather generating extreme winds, inland flooding from intense rainfall and storm surge resulted in damages estimated at £2 billion in the three most affected Territories.

Healthy ecosystems provide services that help to minimise the impacts of climate change and especially from severe weather. Coral reefs and coastal mangrove forests buffer the storm waves; inland vegetation and associated habitats reduce surface water flows and facilitates absorption of flooding waters; and all of these habitats combined continue to offer other benefits that sustain biodiversity and livelihoods. It is these natural features and the services they provide that is often referred to as the ‘natural capital’ of an area. However, significant habitat loss, geomorphological modification, pollution, invasive species and diseases like Stony Coral Tissue Loss Disease (SCTLD) have weakened and, in many cases, completely removed these naturally resilient and adaptive systems; resulting in chronic flooding, damages to property and loss of human life (Martinez et al., 2017; Beck et al., 2018; Beck et al., 2020). The flood protection role and economic value of these natural environments is not fully realised within policy making and planning institutions, nor at the community level within the OTs.  More effective management measures at national and local levels, are needed to ensure this protective role is retained.

To help meet these needs, the JNCC has obtained funding through the CSSF, and other funding sources, to assist the UKOT Government’s in:

- Identifying communities at risk from flooding and key habitats that reduce risks – maps of high-risk areas, and of the habitats that provide protection, will be used to communicate results to local communities and relevant government agencies;

- Demonstrating the economic (monetary) value of the natural environment in mitigating flood risk to all sectors of society;

- Training local communities and national agencies to gather and use data in computer-based modelling to support national and local disaster preparations to update risk assessments and economic valuations.

- Implementing coral reef action plans developed by the UKOTs to restore and protect coral reefs through training, coral reef monitoring and reducing pressures including from SCTLD.

However, there remains a lot of misunderstanding and misinformation on climate change and climate resilience; the role that healthy, native ecosystems play in climate resilience and adaptation; and what people can do to combat these issues as an individual, or as a nation. Therefore, this work will need to be accompanied by an effective communications programme. This programme will be executed across six (6) UKOTs where disaster resilience planning and coral reef work is being undertaken and shall seek to:

- Highlight the disaster resilience and implementation of coral reef action plan work occurring across the Territories; and

- Develop and disseminate nationally relevant and targeted communications materials.

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are to:

- Set up and run Project Steering Group(s) (PSG) in the relevant UKOTs consisting of the relevant government agencies, key on-island stakeholders, JNCC and contractor.

- In collaboration with UKOT stakeholders, develop a Communications Action Plan specific to the following UKOTs:

  - Turks and Caicos Islands (TCI);

  - British Virgin Islands (BVI);

  - Cayman Islands (CI);

  - Montserrat;

  - Bermuda; and

  - Anguilla.

- Execute the Communications Action Plan across the UKOTs.

- Analyse the effectiveness of the communications executed to enable reporting and provide recommendations for future engagement planning.

## Project Objectives: Detailed Tasks

- Set up and run Project Steering Group(s) (PSG) in the relevant UKOTs by:

  - First PSG meeting to be held within a week of contract confirmation.

  - Meetings to be held (via remote systems) as agreed by the PSG.

- Develop a Communications Action Plan by;

  - Conducting a gaps analysis of previous climate resilience and coral reef conservation education work on the UKOT’s by reviewing literature, reports and interviewing key stakeholders;

  - Developing a stakeholder matrix to maximise partnership opportunities;

  - Identifying target audiences, strategic messaging, and channels of communication in each of the UKOTs;

  - Developing a monitoring and evaluation plan with indicators determined;

  - Consult on, and refine, the action plan based on input from the PSG and key stakeholders.

- Execute the Communications Action Plan by:

  - Developing communications materials, individualised for each territory (inclusive of but not limited to posters, video, handouts, social media content). For each output three quotes obtained, contractors selected, products drafted, and finalised through the PSG;

  - Distributing materials as determined in the action plan and in liaison with JNCC, OTGs and their communications teams;

  - Taking advantage of opportunities on-island to show-case the project, distribute messaging to target audiences, or highlight local climate champions in the media.

- Produce a Final Report:

  - Report on materials developed, methods of dissemination and an analysis of their effectiveness;

  - Summarise challenges and recommendations for future work; and

  - Draft report circulated to PSG and finalised.

## Potential Follow-On Work

There is no follow-on work expected from this contract.

## Outputs

- A Communication Action Plan highlighting disaster resilience work and coral reef action plans implementation work in six UKOTs, including:

  - A synthesis of the previous work done to date on climate resilience communications and gaps analysis;

  - A collation of materials already produced to be included into the plan;

  - Development of a stakeholder matrix for each Territory based on a template provided by JNCC;

  - Development of key messaging and results from testing the messaging in the communities;

  - Materials and activities to be produced/undertaken outlined;

  - Budget and timelines for the strategy produced; and

  - Monitoring and evaluation indicators are described.

- Products identified in the Action Plan and approved by the PSG are produced.

- Final report is produced.

  - Reporting on all project activities and materials that were produced and distributed;

  - Financial report produced; and

  - Challenges and Recommendations for future education and outreach needs.

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style and use the CSSF template which will be provided.  All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.  All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

## Dissemination

The products/outputs produced under this contract will be joint owned by the JNCC and relevant Overseas Territory.  Products/outputs shall not be published or disseminated without the written permission of JNCC and relevant Overseas Territory.  The various outputs will be distributed on a variety of platforms and venues to promote JNCC’s work and all material supplied as part of this contract shall remain copyright of JNCC and relevant Overseas Territory.  The products/outputs will also be made available to UK Overseas Territories (UKOT and UK Overseas Territories Association (UKOTA) for use.  The findings from this contract will also be made available to staff within JNCC, the UK country nature conservation bodies, the UKs Overseas Territories, Defra and the FCDO.

All footage and documentation delivered by JNCC, UKOTs and UKOTA to the contractor for inclusion in the video or products, in the course of this work, which is then not used, should be treated as commercial-in-confidence, the contractor should seek JNCC permission before distributing any footage or graphics to any third parties.

All documentation delivered by JNCC to the contractor regarding specification for the new system should be treated as commercial-in-confidence, the contractor should seek JNCC permission before distributing the documentation to any third parties.

Any information delivered to the contractor should not be used for any purposes outside the scope of this contract and should be destroyed on completion of the contract.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (UK) | 26 January 2022 |
| Action plan is submitted and approved | 07 February 2022 |
| Key messages for each OT and communications ‘products’ required agreed | 21 February 2022 |
| Draft communication ‘products’ produced and sent to OTs and JNCC for approval | 07 March 2022 |
| Communications products signed off by each OT and JNCC | 16 March 2022 |
| Communications outputs received by OTs and JNCC | 21 March 2022 |
| Final report is drafted, circulated to the PSG and approved. | 21 March 2022 |
| Project sign off and certification | 28 March 2022 |

In agreeing exact dates, please note that the potential for work under this contract to be funded into 2022/23 is subject to availability of funds.

## Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Abbie Dosell

Joint Nature Conservation Committee

Email: Abbie.Dosell@JNCC.gov.uk

Tel: +44 (0)1 1733 866930

Shelley Cant

Joint Nature Conservation Committee

Email: Shelley.Cant@JNCC.gov.uk

Tel: +44 (0)1 1733 866956

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed:

Details of the bidder’s own internal Quality Management System;

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project;

Availability of the Project Team for a start-up meeting to be held virtually.

Overall quote for the contract to include:

  - Day rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates).

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments; and

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 14.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC staff.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal particularly work programme and deliverables | 10 |  |
|  | Understanding of, and relevance to, the requirements in particular the adequacy of outputs and understanding of stakeholder engagement and communications principles, Caribbean biodiversity, and challenges to conservation. | 10 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Realism and measurability of outputs | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Total | 50 |  |
| 2. Details of Contractor (20% of the total for the three assessment categories) |  |  |  |
|  | Expertise, experience, and balance of team | 9 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors if any | 6 |  |
|  | Sub Total | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation what does presentation mean here in relation to cost? | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 8 |  |
|  | Sub Total | 30 |  |
| Total Score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

i.	On satisfactory completion of draft action plan, expected to be 24 January 2022.

ii.	On satisfactory completion of the final report, expected 21 March 2022.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## References

Beck, M. W., Losada, I. J., Menéndez, P., Reguero, B. G., Díaz-Simal, P. and Fernández, F. (2018) 'The global flood protection savings provided by coral reefs', Nature communications, 9(1), pp. 1-9.

Beck, M. W., Torres-Ortega, S., Losada, I., Narayan, S. and Menéndez, P. (2020) 'the Global flood protection Benefits of Mangroves'.

Bellard, C., Bertelsmeier, C., Leadley, P., Thuiller, W. & Courchamp, F. 2012. Impacts of climate change on the future of biodiversity. Ecology letters, 15, 365-377.

Brown, N. 2008. Climate change in the UK Overseas Territories: An Overview of the Science, Policy and You. Peterborough,UK: Joint Nature Conservation Committee

Martinez, M. L., Silva, R., Lithgow, D., Mendoza, E., Flores, P., Martínez, R. and Cruz, C. (2017) 'Human impact on coastal resilience along the coast of Veracruz, Mexico', Journal of Coastal Research, (77), pp. 143-153.