SCHEDULE 8.3

CHANGE CONTROL PROCEDURE

Change Control Procedure

## DEFINITIONS

In this Schedule, the following definitions shall apply:

| “Authority Change Manager” | the person appointed to that position by the Authority from time to time and notified in writing to the Supplier or, if no person is notified, the Authority Representative; |
| --- | --- |
| “Change Request” | a written request for a Contract Change which shall be substantially in the form of Annex 1; |
| “Change Communication” | any Change Request, Impact Assessment, Change Authorisation Note or other communication sent or required to be sent pursuant to this Schedule; |
| “Fast-track Change” | any Contract Change which the Parties agree to expedite in accordance with Paragraph 8; |
| “Impact Assessment” | an assessment of a Change Request in accordance with Paragraph 5; |
| “Impact Assessment Estimate” | has the meaning given in Paragraph 4.3; |
| “Receiving Party” | the Party which receives a proposed Contract Change; and |
| “Supplier Change Manager” | the person appointed to that position by the Supplier from time to time as identified in Schedule 9.2 (Key Personnel) or otherwise notified in writing to the Authority or, if no person is notified, the Supplier Representative. |

## GENERAL PRINCIPLES OF CHANGE CONTROL PROCEDURE

### This Schedule sets out the procedure for dealing with Contract Changes.

### Operational Changes shall be processed in accordance with Paragraph 9.  If either Party is in doubt about whether a change falls within the definition of an Operational Change, then it must be processed as a Contract Change.

### The Parties shall deal with Contract Change as follows:

#### either Party may request a Contract Change which they shall initiate by issuing a Change Request in accordance with Paragraph 4;

#### unless this Agreement otherwise requires, the Supplier shall assess and document the potential impact of a proposed Contract Change in accordance with Paragraph 5 before the Contract Change can be either approved or implemented;

#### the Authority shall have the right to request amendments to a Change Request, approve it or reject it in the manner set out in Paragraph 6;

#### the Supplier shall have the right to reject a Change Request solely in the manner set out in Paragraph 7;

#### save as otherwise provided in this Agreement, no proposed Contract Change shall be implemented by the Supplier until a Change Authorisation Note has been signed and issued by the Authority in accordance with Paragraph 6.2; and

#### a proposed Contract Change is a Fast-track Change, it shall be processed in accordance with Paragraph 8.

### To the extent that any Contract Change requires testing and/or a programme for mobilisation, then the Parties shall follow the procedures set out in Schedule 6.2 (Testing Procedures), and, where appropriate, the Change Authorisation Note relating to such a Contract Change shall specify Milestones and/or a Key Milestone and Milestone Date(s) in respect of such Contract Change for the purposes of such procedures.

### Until a Change Authorisation Note has been signed and issued by the Authority in accordance with Paragraph 6.2, then:

#### unless the Authority expressly agrees (or requires) otherwise in writing, the Supplier shall continue to supply the Services in accordance with the existing terms of this Agreement as if the proposed Contract Change did not apply; and

#### any discussions, negotiations or other communications which may take place between the Authority and the Supplier in connection with any proposed Contract Change, including the submission of any Change Communications, shall be without prejudice to each Party’s other rights under this Agreement.

### The Supplier shall:

#### within ten (10) Working Days of the Authority’s signature and issue of a Change Authorisation Note, deliver to the Authority a copy of this Agreement updated to reflect all Contract Changes agreed in the relevant Change Authorisation Note and annotated with a reference to the Change Authorisation Note pursuant to which the relevant Contract Changes were agreed; and

#### thereafter provide to the Authority such further copies of the updated Agreement as the Authority may from time to time request.

## COSTS

### Subject to Paragraph 3.3:

#### the costs of preparing each Change Request shall be borne by the Party making the Change Request; and

#### the costs incurred by the Supplier in undertaking an Impact Assessment shall be borne by the Party making the Change Request provided that the Authority shall not be required to pay any such costs if:

##### such costs are below

##### the Supplier is able to undertake the Impact Assessment by using resources already deployed in the provision of the Services; or

##### such costs exceed those in the accepted Impact Assessment Estimate.

### The cost of any Contract Change shall be calculated and charged in accordance with the principles and day rates or day costs (as applicable) set out in Schedule 7.1 (Charges and Invoicing) and Paragraph 10 (Changes to Charges) below. The Supplier shall be entitled to increase the Charges only if it can demonstrate in the Impact Assessment that the proposed Contract Change requires additional resources and, in any event, any change to the Charges resulting from a Contract Change (whether the change will cause an increase or a decrease in the Charges) will be strictly proportionate to the increase or decrease in the level of resources required for the provision of the Services as amended by the Contract Change.

### Both Parties' costs incurred in respect of any use of this Change Control Procedure as a result of any error or Default by the Supplier shall be paid for by the Supplier.

## CHANGE REQUEST

### Either Party may issue a Change Request to the other Party at any time during the Term.  A Change Request shall be substantially in the form of Annex 1 and state whether the Party issuing the Change Request considers the proposed Contract Change to be a Fast-track Change.

### If the Supplier issues the Change Request, then it shall also provide an Impact Assessment to the Authority as soon as is reasonably practicable but in any event within ten (10) Working Days of the date of issuing the Change Request.

### If the Authority issues the Change Request, then the Supplier shall provide as soon as reasonably practical and in any event within ten (10) working days of the date of receiving the Change Request an estimate (“Impact Assessment Estimate”) of the cost of preparing an Impact Assessment and the timetable for preparing it. The timetable shall provide for the completed Impact Assessment to be received by the Authority within ten (10) Working Days of acceptance of the Impact Assessment Estimate or within any longer time period agreed by the Authority.

### If the Authority accepts an Impact Assessment Estimate then following receipt of notice of such acceptance the Supplier shall provide the completed Impact Assessment to the Authority as soon as is reasonably practicable and in any event within the period agreed in the Impact Assessment Estimate. If the Supplier requires any clarification in relation to the Change Request before it can deliver the Impact Assessment, then it shall promptly make a request for clarification to the Authority and provided that sufficient information is received by the Authority to fully understand:

    - the nature of the request for clarification; and

    - the reasonable justification for the request;

the time period to complete the Impact Assessment shall be extended by the time taken by the Authority to provide that clarification.  The Authority shall respond to the request for clarification as soon as is reasonably practicable.

## IMPACT ASSESSMENT

### Each Impact Assessment shall be completed in good faith and shall include:

#### details of the proposed Contract Change including the reason for the Contract Change;

#### details of the impact of the proposed Contract Change on the Services, the Optional Services (if any) and the Supplier's ability to meet its other obligations under this Agreement;

#### any variation to the terms of this Agreement that will be required as a result of that impact, including changes to:

##### the Services Description, the KPIs and/or the Target Performance Levels;

##### the format of Authority Data, as set out in the Services Description;

##### the Milestones, Mobilisation Plan or Project Plan and any other timetable previously agreed by the Parties; and/or

##### other services provided by third party contractors to the Authority, including any changes required by the proposed Contract Change to the Authority's IT infrastructure;

#### details of the cost of implementing the proposed Contract Change;

#### details of the ongoing costs required by the proposed Contract Change when implemented, including any increase or decrease in the Charges, any alteration in the resources and/or expenditure required by either Party and any alteration to the working practices of either Party;

#### a timetable for the mobilisation, together with any proposals for the testing of the Contract Change;

#### details of how the proposed Contract Change will ensure compliance with any applicable Change in Law; and

#### such other information as the Authority may reasonably request in (or in response to) the Change Request.

### If the Contract Change involves the processing or transfer of any Personal Data outside the European Economic Area, the preparation of the Impact Assessment shall also be subject to Schedule 2.8 (Data Processing and List of Sub-processors).

### Subject to the provisions of Paragraph 5.4, the Authority shall review the Impact Assessment and respond to the Supplier in accordance with Paragraph 6 within 15 Working Days of receiving the Impact Assessment.

### If the Authority is the Receiving Party and the Authority reasonably considers that it requires further information regarding the proposed Contract Change so that it may properly evaluate the Change Request and the Impact Assessment, then within five (5) Working Days of receiving the Impact Assessment, it shall notify the Supplier of this fact and detail the further information that it requires.  The Supplier shall then re-issue the relevant Impact Assessment to the Authority within ten (10) Working Days of receiving such notification.  The Supplier shall ensure that the reissued Impact Assessment will contain the information requested by the Authority. At the Authority's discretion, the Parties may repeat the process described in this Paragraph 5.4 until the Authority is satisfied that it has sufficient information to properly evaluate the Change Request and Impact Assessment.

### The calculation of costs for the purposes of Paragraphs 5.1(d) and 5.1(e) shall:

#### be based on the Models;

#### be in accordance with Paragraph 10 (Changes to Charges) below;

#### include estimated volumes of each type of resource to be employed and the applicable rate card;

#### include full disclosure of any assumptions underlying such Impact Assessment;

#### include evidence of the cost of any assets required for the Contract Change; and

#### include details of any new Sub-contracts necessary to accomplish the Contract Change.

### The Authority may request that any Impact Assessment presents Charges without indexation for the purposes of comparison.

## AUTHORITY’S RIGHT OF APPROVAL

### Within fifteen (15) Working Days of receiving the Impact Assessment from the Supplier or within ten (10) Working Days of receiving the further information that it may request pursuant to Paragraph 5.4, the Authority shall evaluate the Change Request and the Impact Assessment and shall do one of the following:

#### approve the proposed Contract Change, in which case the Parties shall follow the procedure set out in Paragraph 6.2;

#### in its absolute discretion reject the Contract Change, in which case it shall notify the Supplier of the rejection.  The Authority shall not reject any proposed Contract Change to the extent that the Contract Change is necessary for the Supplier or the Services to comply with any Changes in Law.  If the Authority does reject a Contract Change, then it shall explain its reasons in writing to the Supplier as soon as is reasonably practicable following such rejection; or

#### in the event that it reasonably believes that a Change Request or Impact Assessment contains errors or omissions, require the Supplier to modify the relevant document accordingly, in which event the Supplier shall make such modifications within five (5) Working Days of such request. Subject to Paragraph 5.4, on receiving the modified Change Request and/or Impact Assessment, the Authority shall approve or reject the proposed Contract Change within ten (10) Working Days.

### If the Authority approves the proposed Contract Change pursuant to Paragraph 6.1 and it has not been rejected by the Supplier in accordance with Paragraph 7, then it shall inform the Supplier and the Supplier shall prepare two (2) copies of a Change Authorisation Note which it shall sign and deliver to the Authority for its signature.  Following receipt by the Authority of the Change Authorisation Note, it shall sign both copies and return one copy to the Supplier.  On the Authority's signature the Change Authorisation Note shall constitute (or, where the Authority has agreed to or required the implementation of a Change prior to signature of a Change Authorisation Note,  shall constitute confirmation of) a binding variation to this Agreement.

### If the Authority does not sign the Change Authorisation Note within ten (10) Working Days, then the Supplier shall have the right to notify the Authority and if the Authority does not sign the Change Authorisation Note within five (5) Working Days of such notification, then the Supplier may refer the matter to the Expedited Dispute Timetable pursuant to the Dispute Resolution Procedure.

## SUPPLIER’S RIGHT OF REJECTION

### Following an Impact Assessment, if:

#### the Supplier reasonably believes that any proposed Contract Change which is requested by the Authority would:

##### materially and adversely affect the risks to the health and safety of any person; and/or

##### require the Services to be performed in a way that infringes any Law; and/or

#### the Supplier demonstrates to the Authority's reasonable satisfaction that the proposed Contract Change is technically impossible to implement and neither the Supplier Solution nor the Services Description state that the Supplier does have the technical capacity and flexibility required to implement the proposed Contract Change,

### then the Supplier shall be entitled to reject the proposed Contract Change and shall notify the Authority of its reasons for doing so within five (5) Working Days after the date on which it is obliged to deliver the Impact Assessment pursuant to Paragraph 4.3.

## FAST-TRACK CHANGES

### The Parties acknowledge that to ensure operational efficiency there may be circumstances where it is desirable to expedite the processes set out above.

### If:

#### the total number of Contract Changes in relation to which this Fast-track Change procedure has been applied does not exceed four (4) in any twelve (12) month period; and

#### both Parties agree the value of the proposed Contract Change over the remaining Term and any period for which Termination Services may be required does not exceed  and the proposed Contract Change is not significant (as determined by the Authority acting reasonably),

then the Parties shall confirm to each other in writing that they shall use the process set out in Paragraphs 4, 5, 6 and 7 but with reduced timescales, such that any period of fifteen (15) Working Days is reduced to five (5) Working Days, any period of ten (10) Working Days is reduced to two (2) Working Days and any period of five (5) Working Days is reduced to one (1) Working Day.

### The Parties may agree in writing to revise the parameters set out in Paragraph 8.2 from time to time or that the Fast-track Change procedure shall be used in relation to a particular Contract Change notwithstanding that the total number of Contract Changes to which such procedure is applied will then exceed four (4) in a twelve (12) month period.

## OPERATIONAL CHANGE PROCEDURE

### Any Operational Changes identified by the Supplier to improve operational efficiency of the Services may be implemented by the Supplier without following the Change Control Procedure for proposed Contract Changes provided they do not:

#### have an impact on the business of the Authority;

#### require a change to this Agreement;

#### have a direct impact on use of the Services; or

#### involve the Authority in paying any additional Charges or other costs.

### The Authority may request an Operational Change by submitting a written request for Operational Change (“RFOC”) to the Supplier Representative.

### The RFOC shall include the following details:

#### the proposed Operational Change; and

#### the timescale for completion of the Operational Change.

### The Supplier shall inform the Authority of any impact on the Services that may arise from the proposed Operational Change.

### The Supplier shall complete the Operational Change by the timescale specified for completion of the Operational Change in the RFOC, and shall promptly notify the Authority when the Operational Change is completed.

## CHANGES TO CHARGES

### “The Supplier may request a review into the prices included within Call-Off Schedule 5 Pricing Details Schedule 7.1 Charges and Invoicing where they can provide conclusive evidence to HMRC, as defined at clause 2 below, that the following conditions have been met:

#### There has been a reduction in the Supplier’s profit margin, as anticipated within the Supplier’s tender proposal submission and which is expressly restricted to profit margin achieved through delivery under this contract, to below the specified threshold (in %) agreed between the two parties during the Mobilisation period, and;

#### The driver of the reduction in the Supplier’s profit margin, specific to the delivery of this contract, is as a result of external market factors beyond their control.

### Conclusive evidence is defined as including, as a minimum, a detailed, clear and accurate breakdown of the pricing factors influencing the Supplier’s profit margin achieved through delivery of this contract, the external market drivers influencing these factors, and the scope and scale to which these drivers are causing the Supplier’s profit margin under this contract to fall below the specified threshold (in £ or % as appropriate). The Supplier must include sufficient detail and transparency so that HMRC can interpret and understand how the Supplier has calculated the changes to its profit margins specific to this contract and identified relevant drivers. The Supplier must use the cost breakdown submitted as part of their tender proposal as the benchmark for any changes calculated to their profit margin.

### HMRC will review the evidence submitted by the Supplier and will either approve or reject the request. The decision to approve or reject the request will be based solely on whether HMRC agrees that the criteria specified within clause 1 has been met. HMRC will not unreasonably withhold approval to a request under clause 1.

### Where a price review request is accepted and the Supplier requests a price amendment during the review, the Supplier will be required to demonstrate that any new proposed prices constitute good value as defined within Schedule 7.3 (Value for Money) – Part C Benchmarking.  The cost to compile evidence for a price review shall be borne solely by the Supplier.

### The Parties agree that any agreed changes required to this Contract identified in the price review will be implemented at the direction of the Relevant Authority in accordance with Schedule 8.3 (Change Control Procedure).

### The Supplier will not be permitted to request a price review within 12 months of the service go-live date. The Supplier will not permitted to request a price review within 12 months of a previous price review where HMRC subsequently agrees to price amendments.

### Where indexation applies, indexation will only be applied to elements of their Goods and/or Services are applicable to indexation. Justifcations using the Retail Price Index and Government fuel index are allowable under this contract.

### In order to provide a meaningful benchmark for any potential price increase requests, tenderers will be required the submit the following information in addition to their tender responses:

#### A firm figure (in %) for their expected profit margin in relation to delivering HMRC’s contract at the outset, and;

#### A breakdown demonstrating how their profit margin, specific to delivery of this contract, has been calculated, including a breakdown of costs (in %) across different sub-categories such as cost breakdown per Goods, Services, Overheads, Profit and/or Implementation as appropriate. The Supplier must include sufficient detail and transparency so that HMRC can interpret and understand how the Supplier has calculated its profit margins.

#### To enable HMRC to review indexation related requests the Supplier must provide a breakdown of which elements of their Goods and/or Services are applicable to indexation. This breakdown should be (in %) terms at line item level.

### Tenderers must submit this information as a separate attachment (word, PDF, or excel as preferred) within the Bid Section of their submission. For the avoidance of doubt, this information will not be used as part of HMRC’s evaluation of bids, however HMRC may seek further clarification on the document if required.

### Any change to the Charges shall be developed and agreed by the Parties on the basis that:

    - such changes to the Charges shall be calculated in accordance with the underlying principles in the Cost Model which make up the Charges prior to the Contract Change;

    - notwithstanding any other provision of this Schedule, the Supplier Profit Margin on such Charges shall:

      - be no greater than the Supplier Profit Margin applying to Charges using the same pricing mechanism as set out in the Models as at the Effective Date; and

      - in no event exceed the Anticipated Contract Life Profit Margin plus 5%;

    - as part of the Change Control Procedure, the Supplier shall promptly prepare a complete revised copy of each Model (or if agreed otherwise by the Parties, an updated copy of the extract of each Model that has changed) to:

enable the Parties to evaluate the impact of the Contract Change, including sufficient information to allow the Authority to understand any Charges, Costs, anticipated Supplier Profit, anticipated Supplier Profit Margin and Anticipated Contract Life Profit Margin set out in the Model (as applicable); and/or

document any changes to the Charges agreed in accordance with the Change Control Procedure;

    - the Supplier shall prepare each iteration of the Models in accordance with Clause 10.28 (The Models) and, if such Part is used, Part D (Cost Model) of Schedule 7.1 (Charges and Invoicing).

    - any amendment which is made in order to evaluate or reflect the impact of a Contract Change shall relate only to the impact of that Contract Change; and

    - no amendment to the Charges shall affect, in any way whatsoever, the performance of the Services, except where expressly agreed in accordance with the Change Control Procedure.

### The version of the Models agreed by the Authority in accordance with the Change Control Procedure shall become the current approved version of the Models for the purposes of this Agreement with effect from the date of signature of the Change Authorisation Notice.

### If there is a Dispute regarding the correct version of any Model, the Authority's copy of the relevant Model shall be authoritative.

## CHANGES TO CHARGES FOR ANY EXTENSION PERIOD

### The Parties may agree to vary the Charges, in accordance with the Change Control Procedure, with effect from the commencement of any Extension Period. In the absence of any such agreement, the relevant Extension Period will take effect on the terms of this Agreement that subsist immediately prior to the Extension Period taking effect.

## INDEXATION

### For the avoidance of doubt, the Supplier may not vary Charges to take account of Indexation at any time.

## COMMUNICATIONS

### For any Change Communication to be valid under this Schedule, it must be sent to either the Authority Change Manager or the Supplier Change Manager, as applicable. The provisions of Clause 44 (Notices) shall apply to a Change Communication as if it were a notice.

# ANNEX 1: Change Request Form

| CR NO.: | TITLE: |  |  | TYPE OF CHANGE: |
| --- | --- | --- | --- | --- |
| CONTRACT: |  |  | REQUIRED BY DATE: |  |
| ACTION: |  | NAME: |  | DATE: |
| RAISED BY: |  |  |  |  |
| AREA(S) IMPACTED (OPTIONAL FIELD): |  |  |  |  |
| ASSIGNED FOR IMPACT ASSESSMENT BY: |  |  |  |  |
| ASSIGNED FOR IMPACT ASSESSMENT TO: |  |  |  |  |
| SUPPLIER REFERENCE NO.: |  |  |  |  |
| FULL DESCRIPTION OF REQUESTED CONTRACT CHANGE (INCLUDING PROPOSED CHANGES TO THE WORDING OF THE CONTRACT): |  |  |  |  |
| DETAILS OF ANY PROPOSED ALTERNATIVE SCENARIOS: |  |  |  |  |
| REASONS FOR AND BENEFITS AND DISADVANTAGES OF REQUESTED CONTRACT CHANGE: |  |  |  |  |
| SIGNATURE OF REQUESTING CHANGE OWNER: |  |  |  |  |
| DATE OF REQUEST: |  |  |  |  |

# ANNEX 2: Change Authorisation Note

| CR NO.: | TITLE: |  | DATE RAISED: |
| --- | --- | --- | --- |
| CONTRACT: | TYPE OF CHANGE: |  | REQUIRED BY DATE: |
| [KEY MILESTONE DATE: [if any] ] |  |  |  |
| DETAILED DESCRIPTION OF CONTRACT CHANGE FOR WHICH IMPACT ASSESSMENT IS BEING PREPARED AND WORDING OF RELATED CHANGES TO THE CONTRACT: |  |  |  |
| PROPOSED ADJUSTMENT TO THE CHARGES RESULTING FROM THE CONTRACT CHANGE: |  |  |  |
| DETAILS OF PROPOSED ONE-OFF ADDITIONAL CHARGES AND MEANS FOR DETERMINING THESE (E.G. FIXED PRICE BASIS): |  |  |  |
| SIGNED ON BEHALF OF THE AUTHORITY: |  | SIGNED ON BEHALF OF THE SUPPLIER: |  |
| Signature:_____________________ |  | Signature:_____________________ |  |
| Name:________________________ |  | Name:________________________ |  |
| Position:______________________ |  | Position:______________________ |  |
| Date:________________________ |  | Date:_________________________ |  |