## Introduction
BIM Tasks for Landscape Architects
The Landscape Institute (LI) has worked with partners to develop a Landscape Digital Plan of Works that will be used as a template for landscape schemes. This work has been led for the LI by Anna Dekker CMLI (Technical Information Research Manager, NBS)
The Landscape Institute Technical Committee and BIM Working Group have produced a Scope of Services for activities which may be carried out by Landscape Architects on a wide range of projects. The Scopes of Service which are available here are particularly relevant for construction related projects, in particular digital information and BIM. The information is based on a combination of the LI Scopes of Service (2013) and RIBA template tasks in the BIM Toolkit. This does not replace the Landscape Consultants Appointment but provides a range of BIM level 2 tasks that may be relevant for construction projects.
If you need access to LI Scopes of Service which reference non-construction projects, such as the production of Environmental Impact Assessments and Landscape Character Assessments, you can find them within the Landscape Consultant’s Appointment, on the Members section of the LI website.
This spreadsheet includes the information requirements specific to Landscape Architects on a BIM Level 2 construction project. There are 4 tabs in total:
· Introduction (you are reading it)
· Landscape Institute Scopes of Service and RIBA Plan of Work Overlay. This relates the LI's 'Areas and Elements of Practice' to the RIBA Plan of Works. Construction-related activities are simple to align, but much landscape work can stand outside of construction projects (e.g. landscape character assessment, landscape management). These activities may, however, inform the planning, design and construction process and may usefully be considered as prerequisites to construction projects. Equally, landscape management can occur, at any scale, for years, decades or centuries, and will continue long after the short-term intervention of any construction project.
· Landscape Digital Plan of Works (tasks) BIM Level 2 Tasks - see below
· Further sources of information
The BIM Level 2 Tasks include 5 columns:
· reference number
· a task/ scope of service summary
· further detail
· ‘Plain Language Questions’ (PLQs)
· Relevant document in the Employer’s Information Requirements
The template tasks represent a typical landscape project. An example might include:
· task: Evaluate landscape effects and visual impact effects of development.
· further detail: Refer to “Guidelines for Landscape and Visual Impact Assessment”, 3rd edition.
· ‘plain language question’: Have landscape and visual impacts been evaluated to understand their effect on the development?
· Employer’s Information Requirements: Landscape Impact and Visual Impact Assessment
The format allows a Landscape Architect to amend and add to the given list.
This template is version 1.0 and feedback is welcome. This feedback will inform future updates.
This is one of the tools to help Landscape Architects to achieve BIM Level 2 and is released on the basis that it can be adapted by others to suit their purposes. The NBS has already adopted this work and an interactive version of this information will also be available on the NBS BIM Toolkit:
NBS BIM Toolkit
Issued under CC-BY licence
Please note that this document is supplied under Creative Commons with Attribution (CC-BY) so that users can use, adapt, and supply this document as part of their work so long as attribution is given to the Landscape Institute. Users should satisfy themselves of the suitability of this document or as adapted in meeting their purposes, particularly in relation to any use for contracts since it is supplied as-is and no warranty is given as to its suitability.

## LI RIBA overlay
The RIBA Plan of Work 2013 organises the process of briefing, designing, constructing, maintaining, operating and using building projects into a number of key work stages. The content of work stages may vary or overlap to suit specific project requirements. The RIBA Plan of Work 2013 should be used solely as guidance for the preparation of detailed professional services contracts and building contracts.
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Strategic Definition | Preparation and Brief | Concept Design | Developed Design | Technical Design | Construction | Handover and Close Out | In Use
Core Objectives | Identify client's Business Case and Strategic Brief and other core project requirements. | Develop Project Objectives, including Quality Objectives and Project Outcomes, Sustainability Aspirations, Project Budget, other parameters or constraints and develop the Initial Project Brief. Undertake Feasibility Studies and review of Site Information. | Prepare the Concept Design, including outline proposals for structural design, building services systems, outline specifications and preliminary Cost Information along with relevant Project Strategies in accordance with the Design Programme. Agree alterations to brief and issue Final Project Brief. | Prepare the Developed Design, including coordinated and updated proposals for structural design, building services systems, outline specifications, Cost Information and Project Strategies in accordance with the Design Programme. | Prepare the Technical Design in accordance with the Design Responsibility Matrix and Project Strategies to include all architectural, structural and building services information, specialist subcontractor design and specifications, in accordance with the Design Programme. | Offsite manufacturing and onsite Construction in accordance with the Construction Programme and resolution of Design Queries from site as they arise. | Handover of building and conclusion of the Building Contract. | Undertake In Use services in accordance with Schedule of Services.
Procurement | Initial considerations for assembling the project team. | Prepare Project Roles Table and Contractual Tree and continue assembling project team. | The Procurement Strategy does not fundamentally alter the progression of the design or the level of detail prepared at a given stage. However, Information Exchanges will vary depending on the selected procurement route and Building Contract. A bespoke RIBA Plan of Work 2013 will set out the specific tendering and procurement activities that will occur at each stage in relation to the chosen procurement route. |  |  | Administration of Building Contract, including regular site inspections and review of progress. | Conclude administration of the Building Contract.
Programme | Establish the Project Programme. | Review the Project Programme. | Review the Project Programme. | The procurement route may dictate the Project Programme and may result in certain stages overlapping or being undertaken concurrently. A bespoke practice- or project-specific RIBA Plan of Work 2013 will clarify the strategic stage overlaps. The Project Programme will set out the specific stage dates and detailed programme durations.
(Town) Planning | Pre-application discussions. | Pre-application discussions. | Planning applications are typically made using the Stage 3 output. A bespoke project- or practice-specific RIBA Plan of Work 2013 will identify when the planning application is to be made.
Suggested Key Support Tasks | Review Feedback from previous projects. | Prepare Handover Strategy and Risk Assessments. Agree Schedule of Services, Design Responsibility Matrix and Information Exchanges and prepare Project Execution Plan including Technology and Communication Strategies and consideration of Common Standards to be used. | Prepare Sustainability Strategy, Maintenance and Operational Strategy and review Handover Strategy and Risk Assessments. Undertake third party consultations as required and any Research and Development aspects. Review and update Project Execution Plan. Consider the Construction Strategy, including offsite fabrication, and develop the Health and Safety Strategy. | Review and update Sustainability, Maintenance and Operational and Handover Strategies and Risk Assessments. Undertake third party consultations as required and conclude Research and Development aspects. Review and update Project Execution Plan, including the Change Control Procedures. Review and update the Construction and Health and Safety Strategies. | Review and update Sustainability, Maintenance and Operational and Handover Strategies and Risk Assessments. Prepare and submit Building Regulations submission or any other third party submissions requiring consent. Review and update Project Execution Plan. Review the Construction Strategy, including sequencing, and update the Health and Safety Strategy. | Review and update the Sustainability Strategy and implement the Handover Strategy, including agreement of information required for commissioning, training, handover, asset management, future monitoring and maintenance and ongoing compilation of 'As- constructed' Information. Update the Construction and Health and Safety Strategies. | Carry out activities listed in the Handover Strategy including Feedback for use during the future life of the building or on future projects. Updating of Project Information as required. | Conclude activities listed in the Handover Strategy including Post- occupancy Evaluation, review of Project Performance, Project Outcomes and Research and Development aspects. Updating of Project Information, as required, in response to ongoing client Feedback until the end of the building's life.
Sustainability Checkpoints | Sustainability Checkpoint 0 | Sustainability Checkpoint 1 | Sustainability Checkpoint 2 | Sustainability Checkpoint 3 | Sustainability Checkpoint 4 | Sustainability Checkpoint 5 | Sustainability Checkpoint 6 | Sustainability Checkpoint 7
Information Exchanges (at stage Completion) | The Strategic Brief. | The Initial Project Brief. | The Concept Design including outline structural and building services design, associated Project Strategies, preliminary Cost Information and Final Project Brief. | The Developed Design, including the coordinated architectural, structural and building services design and updated Cost Information. | The completed Technical Design of the project. |  | 'As-constructed' Information. | 'As-constructed' Information updated in response to ongoing client Feedback and maintenance or operational developments.
UK Government Information Exchanges | Not required. | Required. | Required. | Required. | Not required. | Not required. | Required. | As required.
Landscape | Site selection / identify constraints. Landscape character, LVIA process / alternatives | Landscape Appraisal: topography, geology, archaeology, ecology/habitat, vegetation, water sensitive design, landscape context | Landscape and ecology strategy: - zoning - water sensitive design - masterplan/concept - circulation - management strategy | Spatial arrangement, materials palette, planting character | Hard and soft detailing, specification, tender docs/process for construction and maintenance | Construction, design queries, site inspection, progress | Maintenance contract | Maintenance, site management
LI S1 Design & Admin | S1A: Scope of Services - Base info, brief, programme, finance, site visit, scope, BIM, CDM | S1B: Feasibility and Design Brief - topo, tree, eco surveys, site appraisal/feasibility, alternatives, stat requirements, final brief, procurement, programme, other consultants. | S1C: Concept Proposals - confirm brief/procurement, concept design, approx costs, design team. | S1D: Design Development - develop concept, outline spec and schedules, stat auths, info for costing, liaise, BREEAM/HS etc. | S1E: Technical Design / Detailed Proposals - detailed design, info for costing, stat applications, liaise, BREEAM/HS etc. S1F: Production Information - production drawings spec and schedules, info for costing, review and coordinate design. S1G: Tender Docs - provide info for BQ prep by others, prepare schedule of work. S1H: Tender Action - advise on contractors/list, collate info, invite tenders, provide info, appraise tenders, review costs. | S1J: Contract Prep - client appoint contractor, responsibilities, formalise, provide info to contractor. S1K: Construction Operations - administer contract, site inspection, coordinate, valuations/ financial reports, review programme, info to CDM-C. | S1L: Completion and Establishment - site inspection, defects, contract completion.
LI S2 Design - as S1 but no CA responsibility | ditto | ditto | ditto | ditto | ditto | ditto | ditto
LI S3 Masterplanning | S3A Scope of Services; S3B Preparation; | S3C Baseline Information, Survey and Appraisal; S3D Strategic Framework; | S3E Preparation of Design and Written Report; S3F Implementation Strategy.
LI S4 LVIA | S4A Scope of Services; | S4B Baseline Studies; | S4C Identification of Impacts; S4D Evaluation of Effects; | S4E Mitigation; S4F Stakeholder Engagement; S4G Report.
Iterative process - EIA / LVIA may determine site location; LV effects will be determined by design; design / mitigation will be influenced by EIA / LVIA
LI S5 Landscape Planning | S5A Landscape/ Townscape/ Seascape Character Assessment; S5B Sensitivity/ Capacity Studies; S5C Green Infrastructure Strategies. |  | S5D Pre-Planning L&V Feasibility | S5F LVIA Audit; S5H Expert Witness.
S5G EIA Co-ordination
LI S6: Landscape Management Plan | S6A Scope | S6B Prep; S6C Baseline, Survey and Appraisal; | S6D Management Plan.
LI S7: Stakeholder Engagement | S7A Scope | S7B Preparation | S7C Communication and Consultation Process; S7D Completion
LI S8: Landscape Maintenance Contract Services | S8A Scope; |  |  |  | S8B Tender Documentation; S8C Tender Action; | S8D Contract Preparation; S8E Mobilisation; | S8F Maintenance Contract Duties

## Landscape DPoW (tasks)
| Ref | Task | Further info | PLQ | Deliverable
Strategic Definition | 0.010 | Identify Business Case requirements. | The Business Case for a project is the rationale behind the initiation of a new building project. It may consist solely of a reasoned argument. It may contain supporting information, financial appraisals or other background information. It should also highlight initial considerations for the Project Outcomes. In summary, it is a combination of objective and subjective considerations. The Business Case might be prepared in relation to, for example, appraising a number of sites or in relation to assessing a refurbishment against a new build option. | What are the political, technical, environmental and financial issues that are to be addressed? | Business Case
| 0.020 | Undertake an appraisal of the project against national and local planning policy | Planning/policy will shape the design of the project, any further technical studies and the consents strategy: | Has this project been appraised against national and local planning policy? | Planning/ policy overview or briefing or a consents strategy
| 0.030 | Identify end users/stakeholders and undertake a review of grant funding sources | This can further shape the design brief of the project through identification of stakeholders/users and potentially strategic partnerships to facilitate and fund the project. This should occur early in the process so that any stakeholders are included in baseline characterisation work. | Have end users and stakeholders been identified? | Grant funding programme/ strategy
| 0.040 | Identify Strategic Brief | The brief prepared to enable the Strategic Definition of the project. Strategic considerations might include considering different sites, whether to extend, refurbish or build new and the key Project Outcomes as well as initial considerations for the Project Programme and assembling the project team. | Have the problem, business requirements, time constraints, costs and benefits been identified and met? | Strategic Brief
| 0.050 | Contribute to preparation of Strategic Brief | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Have all the members of the project team had input into the strategic brief? | Strategic Brief
| 0.060 | Identify Core Project Requirements. | The Core Project Requirements include any specific Project Outcomes and Project Objectives essential for the successful completion of the project. | Have the technical, environmental and financial outcomes for the project been answered? | Core Requirements Report
| 0.070 | Agree scope of services | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | What services are required? | Scope of services
| 0.080 | Establish Project Programme | The overall period for the briefing, design, construction and postcompletion activities of a project. | Does the programme realistically reflect the milestones, main tasks and resources required for this project? | Project Programme
| 0.090 | Identify Project Team | The Team must be appropriate to the nature and scale of the project, but should include the Client, and identify who is sponsoring the project, who will be the Senior User and GSL champion. | Who is sponsoring the project, can the senior user and GSL commit resources to the project and has the project team been identified? | Project Team Directory
| 0.100 | Project Team Meeting | Regular meeting with project team to discuss progress | Is there a mechanism for meeting with project team? | Meeting minutes
| 0.110 | Design Team Meeting | Regular meeting with project team to discuss design | Is there a mechanism for meeting with design team? | Meeting minutes
| 0.120 | Collate Feedback from previous projects | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Have lessons learnt from previous projects been shared with the team? | Lessons Learnt Feedback Report
| 0.130 | Determine Site Boundaries | Identify the boundaries of the site and identification of the technical information required to assess the site conditions such as, topographic surveys, geotechnical surveys or OS data mapping. Site visit? | What are the areas of study and have these been identified on surveys? | Topographic Survey Report
| 0.140 | Determine whether project requires an SEA and/ or Environmental Impact Assessment | Not all projects require SEA or EIA. The latter depends on whether the project is Schedule 1, 2 or 3 in the EIA Regs. If Schedule 1 EIA is mandatory. If Schedule 2, EIA may be required depending on threshold and site specifics. | is the project likely to require EIA/ SEA? | EIA/ SEA briefing
| 0.150 | Carry out a Landscape Character Assessment to inform the baseline | Assess the characteristics of the landscape such as the topographic features, flora, fauna, history and land use. This will ultimately inform the design of the project. Refer to relevant assessment guidance and any published assessments, e.g. in England refer to “An Approach to Landscape Character Assessment”. | Has the associated Landscape Character Assessment been considered in the strategy? | Landscape Character Assessment
| 0.160 | Carry out a Townscape Character Assessment to inform the baseline. | Assess the characteristics of the local area such as village design statements, urban character and conservation area appraisals. This will ultimately inform the design of the project. Refer to relevant assessment guidance and any published assessments, e.g. in England refer to “An Approach to Landscape Character Assessment”. | Has the associated Landscape Townscape Character Assessment been considered in the strategy? | Townscape Character Assessment
| 0.170 | Carry out Seascape Character Assessment | Assess the characteristics of the seascape such as the coastal features, human use, atmospheric conditions and coastal processes. This will ultimately inform the design of the project. Refer to relevant assessment guidance and any published assessments, e.g. in England refer to “An Approach to Seascape Character Assessment” | Has the associated Seascape Character Assessment been considered in the strategy? | Seascape Character Assessment
| 0.180 | Identify landscape and visual constraints. | Identify landscape and visual constraints at the site which would inform design. | Has the associated Landscape Impact and Visual Assessment been considered in the strategy? | Landscape and Visual Constraints Plan
| 0.190 | Coordinate and input into Strategic Environmental Assessment | Refer to EIA Directive. | Have the environmental and sustainability aspects been considered in the strategy? | Strategic Environmental Assessment
| 0.200 | Discuss project with appropriate planning authority | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Have initial discussions taken place? | Planning Application
| 0.210 | Identify any existing green infrastructure strategies, policies or plans | The strategy for green infrastructure will inform many other parts of the project. Any existing green infrastructure having a bearing on design will be identified in the planning and policy overview. | Has Green Infrastructure Strategy been developed? | Outline green infrastructure strategy
| 0.220 | Prepare for stakeholder engagement | Consider who might be included as a stakehlder - end users, client, facilities managers etc | Have all the stakeholders been consulted on the initial assessment, the project mandate, and the outcomes of the plan? | Stakeholder engagement plan
| 0.230 | Review published Sensitivity / Capacity Studies | These studies will be carried out to inform a decision regarding the need to undertake such a study for the project. | Are the studies complete? | Sensitivty / Capacity report
| 0.240 | Comment on project Programme | The overall period for the briefing, design, construction and postcompletion activities of a project. | Have the project delivery team had a chance to comment on the proposals? | Programme Feedback Report
| 0.250 | Test the robustness of the Strategic Brief | This will establish how well the Strategic Brief meets the Business Case and the Core Project Requirements. Actual testing will vary depending on particular circumstances of the project. | Has there been a review of the strategic brief to ensure that it is robust and meets the business needs before moving on to the next stage? | Strategic Brief Review Report
| 0.260 | Review feedback from previous projects | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Have lessons learnt from previous projects been shared with the team? | Lesson Learnt Feedback Report
| 0.270 | Ensure that a strategic sustainability review of client needs and potential sites has been carried out, including reuse of existing facilities, building components or materials. | Ensure that a strategic sustainability review of client needs and potential sites has been carried out, including reuse of existing facilities, building components or materials. The precise nature of the review will depend on the definition and method chosen for measuring sustainability. | Have all the environmental opportunities been identified for the project and is there a risk rating attached to this project/programme? | Environmental Review Report
| 0.280 | Strategic Brief Information Exchange | Methods and protocol for information exchange will depend on the nature and complexity of the project. | Has the project brief been distributed? | Project Brief
Preparation and Brief | 1.010 | Contribute to development of Initial Project Brief including Project Objectives, Quality Objectives, Project Outcomes, Sustainability Aspirations, Project Budget and other parameters or constraints. | The Initial Project Brief is prepared following discussions with the Client to ascertain the Project Objectives, the Client’s Business Case and, in certain instances, in response to site Feasibility Studies. | Has the employer had an input into all the project objectives? | Project Brief
| 1.020 | Develop Initial Project Brief with project team including Project Objectives, Quality Objectives, Project Outcomes, Sustainability Aspirations, Project Budget and other parameters or constraints. | The Initial Project Brief is prepared following discussions with the Client to ascertain the Project Objectives, the Client’s Business Case and, in certain instances, in response to site Feasibility Studies. | Has the employer had the opportunity to input into the project execution plan? | Project Brief
| 1.030 | Project Team Meeting | Regular meeting with project team to discuss progress | Is there a mechanism for meeting with the project team? | Meeting minutes
| 1.040 | Collate comments and facilitate workshops to develop Initial Project Brief | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has a workshop taken place to ensure that the project team has input on the project brief? | Workshop Output Report
| 1.050 | Prepare Project Roles Table and Contractual Tree and continue assembling and appointing project team members. | The Project Team must be appropriate to the nature and scale of the project, and the agreed method of delivery of the Core Objectives. | Have all the project roles and responsibilities been identified and agreed? | Project Team Directory
| 1.060 | Prepare Schedule of Services and develop Design Responsibility Matrix including Information Exchanges with Lead designer. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Have the schedule of service and design responsibilities been identified and agreed? | Design Responsibility Matrix
| 1.070 | Prepare Landscape Appraisal: topography, geology, archaeology, ecology/habitat, vegetation, water sensitive design, landscape context | The findings of the Landscape Character Assessment and site survey etc. should influence the design of the project. All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the site amd its context been reviewed and information provided? | Landscape Appraisal Report
| 1.080 | Review Project Programme and Feasibility Studies. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the employer's project manager reviewed the programme and feasibility studies to give the project go-ahead? | Project Programme
| 1.090 | Prepare Risk Assessments. | The Risk Assessment considers the various design and other risks on a project and how each risk will be managed and the party responsible for managing each risk. | Have the project risks been identified and the appropriate assessment collated? | Risk Assessments
| 1.100 | Provide information for and contribute to contents of Project Execution Plan as required. | The Project Execution Plan is produced in collaboration between the Project Lead and Lead designer, with contributions from other designers and members of the project team. The Project Execution Plan sets out the processes and protocols to be used to develop the design. It is sometimes referred to as a project quality plan. | Does the project manager have the information required to compile the project execution plan? | Project Execution Plan
| 1.110 | Prepare Handover Strategy. | The strategy for handing over a project, including the requirements for phased handovers, commissioning, training of staff or other factors crucial to the successful occupation of a building. On some projects, the Building Services Research and Information Association (BSRIA) Soft Landings process is used as the basis for formulating the strategy and undertaking a Post-occupancy Evaluation ( https​://ww​w.bsr​ia.co​.uk/s​ervic​es/de​sign/​soft-​landi​ngs/ ). | Does the project manager have all the information required to prepare the handover strategy? | Handover Strategy
| 1.120 | Monitor and review progress and performance of project team. | This will be carried out and measured against agreed targets. | Is the team monitored on performance? | Progress Monitor
| 1.130 | Provide information for and contribute to contents of Project Execution Plan as required. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the consultants had the opportunity to input into the project execution plan? | Project Execution Plan
| 1.140 | Agree Schedule of services | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the schedule of services been agreed? | Schedule of Services
| 1.150 | Agree Design responsibility matrix | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Have the design responsibilities been agreed? | Design Responsibility Matrix
| 1.160 | Agree sustainability targets. | Confirm that formal sustainability targets are stated in the Initial Project Brief. | Have the environmental targets been agreed? | Environmental Target Report
| 1.170 | Agree environmental requirements. | Confirm that environmental requirements, building lifespan and future climate parameters are stated in the Initial Project Brief. | Have the environmental requirements been agreed? | Environmental Report
| 1.180 | Carry out early stage surveys and/ or monitoring. | Confirm that these have been arranged to meet sustainability criteria or assessment procedures. | Have the early stage surveys taken place? | Early Stage Survey Report
| 1.190 | Assess statutory requirements | Check that the statutory requirements are considered at the outset of the project. | Have the statutory requirements been reviewed and acknowledged? | Statutory requirements summary
| 1.200 | Gather baseline Information | This will include site, ecological, arboricultural information. | Has baseline information been gathered? | Baseline information
| 1.210 | Site Waste Management Plan | Confirm that the Site Waste Management Plan has been implemented. (this may be required as part of an environmental accreditation programme). | Has the waste management plan been agreed? | Waste Management plan
| 1.220 | Design team meeting | Regular meeting with project team to discuss design | Is there a mechanism for meeting with design team? | Meeting minutes
| 1.230 | Finalise design brief | Confirm that all areas of the brief are accounted for. | Has the employer had an input into all the design objectives? | Design Brief
| 1.240 | Exchange initial project brief. | Information exchanged at stage completion. | Has the project brief been distributed? | Project Brief
| 1.250 | Prepare Outline/ Performance Specification | This will include high level specification requirements and will probably be descriptive at this stage | Have early stage specification requirements been noted? | Outline Specification
| 1.260 | Confirm Handover strategy | Check that the principles of the Handover Strategy and post-completion services are included in each party’s Schedule of Services. | Has the handover strategy been reviewed and agreed? | Handover Strategy
Concept Design | 2.010 | Develop concept design. | This should be carried out in accordance with the Initial Project Brief, Design Responsibility Matrix incorporating Information Exchanges and Design Programme. | Has the conceptual design been prepared? | Concept Design
| 2.020 | Monitor progress of Concept Design. | This should me measured in accordance with the Design Programme. | Is the concept design monitored? | Concept Design Progress Monitor
| 2.030 | Prepare and issue Final Project Brief. | This will result from collating and agreeing alterations to the initial project brief. | Has the final project brief been issued? | Project Brief
| 2.040 | Project Team Meeting | Regular meeting with project team to discuss progress | Is there a mechanism for meeting with the project team at this stage of the project? | Meeting minutes
| 2.050 | Review Risk Assessments with project team. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the risk assessment been reviewed and agreed? | Risk Assessment
| 2.060 | Review Handover Strategy with project team. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the handover strategy been reviewed and agreed? | Handover Strategy
| 2.070 | Review and update Project Execution Plan. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the project execution plan been reviewed? | Project Execution Plan
| 2.080 | Review Project Programme and agree any changes with project team. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Have the programme and any associated changes been reviewed and agreed? | Project Programme
| 2.090 | Comment on stage Design Programme. | The Project lead must have the opportunity to comment as the proposals develop and progress. | Has the design programme been reviewed? | Design Programme
| 2.100 | Comment on Cost Information. | The Project lead must have the opportunity to comment as the proposals develop and progress. | Has the cost information been reviewed? | Handover strategy
| 2.110 | Prepare Sustainability Strategy. | This will be carried out with input from project team as required. | Has the proposed sustainability been commented on? | Sustainability strategy
| 2.120 | Develop green infrastructure strategy | The strategy for green infrastructure will inform many other parts of the project. | Has Green Infrastructure Strategy been developed? | Green infrastructure strategy
| 2.130 | Prepare Management Plan. | This will be carried out with input from project team as required. | Have maintenance and operational requirements been considered? | Outline Landscape Management Plan
| 2.140 | Prepare stage Design Programme. | This will be carried out with input from project team as required. | Has the design programme been reviewed? | Design Programme
| 2.150 | Monitor and review progress and performance of design team. | This should me measured in accordance with the Design Programme. | Has the performance of the project team been monitored? | Project Team Report
| 2.160 | Liaise with planning authorities. | As required to progress and develop the design. | Has there been liaison with the planning authorities? | Planning Application
| 2.170 | Stakeholder Engagement | Stakeholder Engagment should be carried out to ensure that end users and those maintaining the site have an opportunity to comment and contribute to the outcomes. | Have all the stakeholders been consulted on the concept design, the project strategies, and the outcomes of the plan? | Stakeholder Engagement Report
| 2.180 | Undertake third party consultations. | Consult with end users and other interested parties, who may be usig or managing the site. | Have all third parties been consulted as part of the project? | Third Party Consultation Report
| 2.190 | Assist Lead designer with preparation of Stage Design Programme. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has there been team input in the preparation of the stage design programme? | Stage Design Programme
| 2.200 | Provide information for preparation of Cost Information. | This will be as requested from the Cost consultant or Project lead respectively. | Has there been team input in the preparation of the cost information? | Cost Information Report
| 2.210 | Prepare Construction Strategy. | Based on Project Strategy. | Has there been team input on the construction strategy? | Construction Strategy
| 2.220 | Develop Health and Safety Strategy. | Respond to statutory requirements. | Have the statutory requirements for Health and safety been met? | Health and Safety Strategy
| 2.230 | Formal sustainability pre-assessment and identification of key areas of design focus. | Confirm that formal sustainability pre-assessment and identification of key areas of design focus have been undertaken and that any deviation from the Sustainability Aspirations has been reported and agreed. | Have the sustainability requirements been met? | Sustainability Checklist
| 2.240 | Initial energy assessment. | Confirm that the initial energy assessment has been carried out. This may be a statutory requirement. | Have the energy assessments been met? | Initial Energy Report
| 2.250 | Environmental impact check. | Confirm that the environmental impact of key materials and the Construction Strategy has been checked. | Has there been an assessment of the environmental impact of the materials used on site? | Environmental Impact Report
| 2.260 | Evaluate landscape effects and visual impact effects of development. | Refer to “Guidelines for Landscape and Visual Impact Assessment”, 3rd edition. | Have landscape and visual impacts been evlauated to understand their effect on the development? | Landscape Impact and Visual Impact Assessment
| 2.270 | Climate change check. | Confirm consideration of resilience to future changes in climate. | Have the future climate changes been considered and reported? | Climate Change Report
| 2.280 | Develop landscape and ecology strategy | Develop landscape and ecology strategy: zoning, water sensitive design, management strategy | Has landscape and ecology strategy been developed? | Landscape and ecology strategy
| 2.290 | Design Team Meeting | Regular meeting with project team to discuss design | Is there a mechanism for meeting with the design team at this stage of the project? | Meeting minutes
| 2.300 | Carry out design/ technical review | These reviews may be internal, peer reviews or formal external reviews e.g. Architecture & Design Scotland, as appropriate for the stage of the project. | Have all design and technical issues been considered? | Design and technical review
| 2.310 | Prepare Masterplan. | Develop masterplan: zoning, water sensitive design, masterplan/concept, circulation | Has Masterplan been developed? | Masterplan and report
| 2.320 | Produce implementation strategy for masterplan. | Consider zoning, phasing etc | Has Masterplan Implementation Strategy been developed? | Masterplan Implemetation Strategy
| 2.330 | Develop Outline/ Performance Specification | This will include high level specification requirements and will probably be descriptive at this stage | Have early stage specification requirements been noted? | Outline Specification
| 2.340 | Exchange Concept Design. | Concept Design including outline structural and building services design, associated Project Strategies, preliminary Cost Information and Final Project Brief. | Have all the requirements been considered as part of the concept brief? | Concept Design
Developed Design | 3.010 | Monitor progress of Developing Design. | This should be measured in accordance with the Design Programme. | Is the developing design being monitored? | Developed Design
| 3.020 | Review Handover Strategy and Risk Assessments with project team. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Have the handover strategies and risk assessments been updated? | Handover Strategy and Risk Assessment
| 3.030 | Review and update Project Execution Plan. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the project execution plan been updated? | Project Execution Plan
| 3.040 | Project Team Meeting | Regular meeting with project team to discuss progress | Is there a mechanism for meeting with the project team at this stage of the project? | Meeting minutes
| 3.050 | Review Project Programme and agree any changes with project team. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the project programme been updated? | Project Programme
| 3.060 | Comment on stage Design Programme and Cost Information. | The Project lead must have the opportunity to comment as the proposals develop and progress. | Has the design programme been reviewed? | Design Programme and Cost Forecast Report
| 3.070 | Co-ordinate and comment on design proposals and Project Strategies as they progress. | The Project lead must have the opportunity to comment as the proposals develop and progress. | Have the project strategies been updated? | Project Strategies
| 3.080 | Update Sustainability Strategy and Maintenance and Operational Strategy. | This will be carried out with input from project team as required. | Has the sustainability strategy been updated? | Sustainability Strategy
| 3.090 | Prepare stage Design Programme in conjunction with other design team members. | This will be carried out with input from project team as required. | Has the project programme been updated? | Project Programme
| 3.100 | Prepare Developed Landscape Design. | This should be carried out in accordance with the Initial Project Brief, Design Responsibility Matrix incorporating Information Exchanges and Design Programme and co-ordination comments from lead designer. | Has the team had an input into the developed design and does it meet the project requiremetnts? | Developed Landscape Design
| 3.110 | Develop Detailed Specification | Liaise with other team members if required in the preparation of the specification information. This will include developed specification requirements for systems, materials and products at this stage. | Have detailed specification requirements been documented? | Developed Specification
| 3.120 | Liaise with planning authorities. | As required to progress and develop the design. | Have discussions taken place with the planning authority? | Planning Application
| 3.130 | Prepare Landscape Management Plan. | Consider strategic objectives, including maintenance, for the landscape over a stated time frame. | Has Landscape Management Plan been prepared? | Landscape Management Plan
| 3.140 | Develop Planting Strategy | Review spatial arrangement, materials palette and planting character. | Has there been team input on the Planting Strategy? | Planting Strategy
| 3.150 | Submit Planning Application. | Include all relevant documentation such as Design and Access Plans. | Has the planning application been submitted to the appropriate authorities? | Planning Application
| 3.160 | Undertake third party consultations. | This will include any Research and Development aspects as required. | Has all research and consultation taken place to allow the project to move on to the next phase? | Third Party Consultation Report
| 3.170 | Provide information for preparation of Cost Information and Project Strategies. | This will be as requested from the Cost consultant or Project lead respectively. | Has the team been consulted and provided information? | Cost Information Report
| 3.180 | Interim energy assessment | Have an interim energy assessment and a design stage carbon/ energy declaration been undertaken. This may be a statutory requirement. | Has the assessment taken place and the carbon declaration been complied ? | Energy Assessment
| 3.190 | Resource and Waste minimisation design review. | Has the design been reviewed to identify opportunities to reduce resource use and waste and the results recorded in the Site Waste Management Plan? | Has there been a review of opportunities to reduce waste on site and with resources? | Site Waste Management Plan
| 3.200 | Stakeholder Engagement | Stakeholder Engagment should be carried out to ensure that end users and those maintaining the site have an opportunity to comment and contribute to the outcomes. | Have all the stakeholders been consulted on the developed designn, the project strategies, and the outcomes of the plan? | Stakeholder Engagement Report
| 3.210 | Design Team Meeting | Regular meeting with project team to discuss design | Is there a mechanism for meeting with the design team at this stage of the project? | Meeting minutes
| 3.220 | Carry out design/ technical review | These reviews may be internal, peer reviews or formal external reviews e.g. Architecture & Design Scotland, as appropriate for the stage of the project. | Have all design and technical issues been considered? | Design and technical review
| 3.230 | Exchange Developed Design. | Concept Design including outline structural and building services design, associated Project Strategies, preliminary Cost Information and Final Project Brief. | Have all the requirements been considered as part of the concept brief? | Developed Design
| 3.240 | Prepare mitigation proposals informed by the LVIA | Has the design been reviewed against the LVIA to identify opportunities to mitigate against proposals? | Have LVIA considerations been incorporated into the mitigation proposals? | Mitigiation Proposals
Technical Design | 4.010 | Monitor progress of developing design. | This should me measured in accordance with the Design Programme. | Has the design been monitored and reviewed through its development stage? | Design
| 4.020 | Review updated Handover Strategy, Project Strategies and Risk Assessments with project team. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Have all of the handover strategies and project strategies been reviewed by the team and updated? | Handover Strategy, Project Strategy and Risk Assessments
| 4.030 | Project Team Meeting | Regular meeting with project team to discuss progress | Is there a mechanism for meeting with the project team at this stage of the project? | Meeting minutes
| 4.040 | Review and update Project Execution Plan. | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the plan been reviewed and updated? | Project Execution Plan
| 4.050 | Comment on stage Design Programme. | The Project lead must have the opportunity to comment as the proposals develop and progress. | Has the programme been reviewed and updated? | Stage design Programme
| 4.060 | Manage Change Control process. | Change Control Procedures should be implemented to ensure that any changes to the Concept Design are properly considered and signed off, regardless of how they are instigated. | How is the change control managed? | Change Control Process
| 4.070 | Monitor and review progress and performance of project team. | This should be measured in accordance with the Project Programme. | Is the project team being monitored and reviewed? | Progress and Performance Report
| 4.080 | Prepare stage Design Programme in conjunction with other design team members | This will be carried out with input from project team as required. | Has the team had the opportunity to review and comment on the design programme? | Design Programme
| 4.090 | Monitor and review progress and performance of design team | This should be measured in accordance with the Design Programme. | Is the project team being monitored and reviewed? | Progress and Performance Report
| 4.100 | Liaise with specialist subcontractors. | As necessary. | Has there been the opportunity to liaise with specialist subcontractors? | Subcontractors Update report
| 4.110 | Prepare landscape Technical Design. | Develop hard and soft landscape detailing, in accordance the Design Responsibility Matrix incorporating Information Exchanges, Design Programme and comments from Lead designer. | Has the team had the opportunity to review and comment on the landscape technical design? | Landscape Technical Design
| 4.120 | Submit Building Regulations Submission (Building Warrant in Scotland) | Has the appropriate building submission or warrant been submitted? | Has the appropriate building submission or warrant been submitted? | Building Regulations Submission
| 4.130 | Undertake third party consultations. | This will include the conclusion of any Research and Development aspects. | Has all research and consultation taken place to allow the project to move on to the next phase? | Third Party Consultation Report
| 4.140 | Assist Lead designer with preparation of stage Design Programme | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the team been consulted on the programme? | Stage Design programme
| 4.150 | Update Construction Strategy | Based on Project Strategy. | Has the team updated the construction strategy? | Construction Strategy
| 4.160 | Assist in preparation of Landscape Contract, agree with contractor and arrange completion | Tender Docs - provide info for BQ prep by others, prepare schedule of work. Tender Action - advise on contractors/list, collate info, invite tenders, provide info, appraise tenders, review costs. | Has the landscape contract been agreed and prepared? | Landscape Contract
| 4.170 | Check Sustainability assessment. | Is the formal sustainability assessment substantially complete? | Has the team been consulted and provided information to update the documents? | Health and Safety Strategy
| 4.180 | Check energy assessment. | Has the energy assessment submission been made and the design stage carbon/ energy declaration been updated and the future climate impact assessment prepared? This may be a statutory requirement. | Has the assessment taken place and the carbon declaration been updated? | Energy Assessment
| 4.190 | Check user guide | Has a non-technical user guide been drafted and agreed? | Has there been a user guide complied for non-technical users? | Non-Technical User Guide
| 4.200 | Check outstanding deign stage information | Has all outstanding design stage sustainability assessment information been submitted? | Has the team been consulted on the programme and any missing information added? | Stage Design Programme
| 4.210 | Check monitoring technologies | Are Landscape Handover Strategy and monitoring technologies specified? | Have the monitoring technologies for the building handover been agreed and reviewed? | Handover Strategy
| 4.220 | Check review of changes | Have the implications of changes to the specification or design been reviewed against agreed sustainability criteria? | What changes have occurred on the project and have they been compared against the agreed sustainability criteria? | Change Control Process
| 4.230 | Check sustainability compliance | Has compliance of agreed sustainability criteria for contributions by specialist subcontractors been demonstrated? | Have the subcontractors demonstrated that they comply to the agreed sustainability criteria? | Sustainability Strategy
| 4.240 | Co-ordinate design proposals and Project Strategies as they progress. | Technical Design / Detailed Proposals - detailed design, info for costing, stat applications, liaise, BREEAM/HS etc. | Have design proposals and project strategies been produced? | Design Proposals
| 4.250 | Design Team Meeting | Regular meeting with project team to discuss design | Is there a mechanism for meeting with the design team at this stage of the project? | Meeting minutes
| 4.260 | Carry out design/ technical review | These reviews may be internal, peer reviews or formal external reviews e.g. Architecture & Design Scotland, as appropriate for the stage of the project. | Have all design and technical issues been considered? | Design and technical review
| 4.270 | Develop Technical Specification | Liaise with other team members if required in the preparation of the specification information. Production Information - production drawings spec and schedules, info for costing, review and coordinate design. This will include technical specification requirements for systems, materials and products at this stage. | Have detailed specification requirements been documented? | Technical Specification
| 4.280 | Exchange technical design. | Technical Design including outline structural and building services design, associated Project Strategies, preliminary Cost Information and Final Project Brief. | Have all the requirements been considered as part of the concept brief? | Technical Design
Construction | 5.010 | Manage implementation of Handover Strategy | Includes agreement of information required for commissioning, training, handover, asset management, future monitoring and maintenance and ongoing compilation of ‘As-constructed’ Information. | Has the handover strategy been implemented? | Handover Strategy
| 5.020 | Project Team Meeting | Regular meeting with project team to discuss progress | Is there a mechanism for meeting with the project team at this stage of the project? | Meeting minutes
| 5.030 | Review and update Project Execution Plan | All members of the Project Team will have an input, but one member takes responsibility for organising the process and coordinating the results. | Has the project execution plan been updated? | Project Execution Plan
| 5.040 | Pre-Start Meeting | Meeting with construction team to discuss roles, lines of communication, confirm programme etc. | Has a project team meeting (ncluding contractor's representatives) been held in advance of works starting on site? | Meeting minutes
| 5.050 | Comment on Construction Programme | The Project lead must have the opportunity to comment as the proposals develop and progress. | Has the construction programme been commented on? | Construction Programme
| 5.060 | Site progress meetings | Meeting with construction team to discuss monitor progress, review desing against construction etc. | Have regular meetings been held to review progress of the works? | Meeting minutes
| 5.070 | Monitor and review progress and performance of project team | This should be measured in accordance with the Project Programme. | Is the project team being monitored and reviewed? | Project Team Progress Report
| 5.080 | Carry out site inspections and review. | Review against specification and construction programme. | Have site inspections been carried out? | Site Inspection Report
| 5.090 | Respond to site queries related to co-ordination or integration | Responses will assist design team members. | Have responses been provided to all site queries? | Site Coordination Report
| 5.100 | Carry out site inspections and review. | Review against specification and construction programme. | Have site inspections been carried out? | Site Inspection Report
| 5.110 | Respond to site queries. | Responses will be needed as they arise in conjunction with the Contract Administrator. | Have responses been provided to all site queries? | Site Coordination Report
| 5.120 | Respond to design queries, | Responses will be required as they arise in conjunction with Design Team. | Have responses been provided to all design queries? | Site Coordination Report
| 5.130 | Prepare 'As Constructed' Information | Support tasks are now focused on health and safety on site and ensuring that the project handover and post-occupancy activities, determined earlier, are properly facilitated. | Has the 'As Constructed' information been prepared? | As Constructed Information
| 5.140 | Update Construction Strategy. | Based on Project Strategy. | Have the valuations been prepared? | Valuation Report
| 5.150 | Co-ordinate site inspections. | In conjunction with the Contract Administrator. | Have site inspections been carried out? | Site Inspection Report
| 5.160 | Monitor construction progress. | Construction Operations - administer contract, site inspection, coordinate, valuations/ financial reports, review programme, info to CDM-C. | Is the progress on target? | Construction Progress Report
| 5.170 | Check design sustainability assessment. | Has the design stage sustainability assessment been certified? | Has the assessment been certified? | Sustainability Assessment
| 5.180 | Check sustainability procedures. | Have sustainability procedures been developed with the contractor and included in the Construction Strategy? | Have all the procedures and protocol been agreed in conjunction with the contractor? | Sustainability Assessment
| 5.190 | Review handover strategy. | Has the detailed commissioning and Handover Strategy programme been reviewed? | Has the handover strategy been reviewed and implemented? | Handover Strategy
| 5.200 | Check non technical user guide. | Is the non-technical user guide complete and the aftercare service set up? | Has there been a user guide complied for non-technical users? | Non-Technical User Guide
| 5.210 | Design Team Meeting | Regular meeting with project team to discuss design | Is there a mechanism for meeting with the design team at this stage of the project? | Meeting minutes
| 5.220 | Carry out design/ technical review | These reviews may be internal, peer reviews or formal external reviews e.g. Architecture & Design Scotland, as appropriate for the stage of the project. | Have all design and technical issues been considered? | Design and technical review
| 5.230 | Undertake final site inspection | Review against design and specification. | Has final site inspection been carried out? | Site Inspection Report
| 5.240 | Prepare 'as constructed' information | Has the ‘As-constructed’ Information been prepared for post-construction sustainability certification. | Has the 'As Constructed' information been prepared? | As Constructed Information
| 5.250 | Prepare defects report | Document End of Defects Liability Period Inspection information | Has the defects report been prepared? | Defects Report
| 5.260 | Check 'as-constructed' information. | Has the ‘As-constructed’ Information been issued for post-construction sustainability certification. | Has the 'As Constructed' information been issued? | As Constructed Information
| 5.270 | Exchange 'As constructed' information. | As-constructed' Information updated in response to ongoing client Feedback and maintenance or operational developments. | Has the 'As Constructed' information been issued and updated post feedback? | As Constructed Information
Handover and Closeout | 6.010 | Manage tasks listed in Handover Strategy. | Support tasks are now focused on health and safety on site and ensuring that the project handover and post-occupancy activities, determined earlier, are properly facilitated. | Have the handover tasks been updated? | Handover Strategy
| 6.020 | Manage updating of 'As Constructed' Information. | Support tasks are now focused on health and safety on site and ensuring that the project handover and post-occupancy activities, determined earlier, are properly facilitated. | Has the 'As Constructed' information been provided? | As Constructed Information
| 6.030 | Project Team Meeting | Regular meeting with project team to discuss progress | Is there a mechanism for meeting with the project team at this stage of the project? | Meeting minutes
| 6.040 | Monitor and review progress and performance of project team. | This should be measured in accordance with the Project Programme. | Has the project team's progress been monitored? | Project Team Performance Report
| 6.050 | Undertake tasks listed in Handover Strategy. | Including Feedback for use during the future life of the site or on future projects. | Have the handover tasks been updated? | Handover Strategy
| 6.060 | Review protection of protected habitats and species (and other statutory protections such as TPO) and invasive species. | A key risk to construction projects during design and implementation is protected habitats and species (and other statutory protections such as TPO) and invasive species. These risks require a proactive approach to their mitigation. | Have risks to protected species/ TPOs etc been mitigated?
| 6.070 | Design Team Meeting | Regular meeting with project team to discuss design | Is there a mechanism for meeting with the design team at this stage of the project? | Meeting minutes
| 6.080 | Carry out design/ technical review | These reviews may be internal, peer reviews or formal external reviews e.g. Architecture & Design Scotland, as appropriate for the stage of the project. | Have all design and technical issues been considered? | Design and technical review
| 6.090 | Update 'As Constructed' Information. | In accordance with Design Responsibility Matrix incorporating Information Exchanges. | Has the 'As Constructed' information been provided? | As Constructed Information
| 6.100 | Review updated 'As Constructed' Information. | Support tasks are now focused on health and safety on site and ensuring that the project handover and post-occupancy activities, determined earlier, are properly facilitated. | Has the 'As Constructed' information been provided? | As Constructed Information
| 6.110 | Manage preparation and issue of 'As Constructed' Information by specialist subcontractors. | In accordance with Design Responsibility Matrix incorporating Information Exchanges. | Has the 'As Constructed' information been provided? | As Constructed Information
| 6.120 | Advise on the resolution of defects. | In accordance with Building Contract. Procedures may vary depending on the form of contract used. | Have the defects been identified? | Defects Report
| 6.130 | Conclude administration of Landscape Contract. | In accordance with Building Contract. Procedures may vary depending on the form of contract used. | Has the building contract been concluded? | Contract Administration Report
| 6.140 | Review Project Information. | Support tasks are now focused on health and safety on site and ensuring that the project handover and post-occupancy activities, determined earlier, are properly facilitated. | Has all the required project information been passed on? | Project Information Report
| 6.150 | Check as constructed information. | Has assistance with the collation of post-completion information for final sustainability certification been provided? | Has the 'As Constructed' information been provided? | As Constructed Information
| 6.160 | Exchange updated 'As constructed' information. | As-constructed' Information updated in response to ongoing client Feedback and maintenance or operational developments. | Has the 'As Constructed' information been provided? | As Constructed Information
| 6.170 | Undertake End of Defects Inspection | Document End of Defects Liability Period Inspection information | Has the End of Defects Inspection Report been prepared? | End of Defects Insection Report
| 6.180 | Handover Health and Safety File | Hand over Health and safety file | Has Health and Safety File been handed over? | Health and Safety File
| 6.190 | Completion and Establishment | Completion and Establishment - site inspection, defects, contract completion. | Has completion inspection been carried out? | Completion and establishment report
| 6.200 | Contract Preparation for Landscape Maintenance | This will be carried out with input from project team as required. | Has Landscape maintenance contract been prepared? | Maintenance Contract
In Use | 7.010 | Manage completion of tasks in Handover Strategy | Conclude activities listed in Handover Strategy including Post-occupancy Evaluation, review of Project Performance, Project Outcomes and Research and Development aspects. | Has the handover strategy been completed? | Handover Strategy
| 7.020 | Manage updating of Project Information. | Updating of Project Information, as required, in response to ongoing client Feedback until the end of the project's life. | Has the project information been updated? | Project Information Checklist
| 7.030 | Carry out site inspection | Frequency of site inspections will vary with management approach. | Does site require inspection? | Management Plan
| 7.040 | Carry out site survey | Frequency of site surveys will vary with management approach and type of monitoring required. | Does site require inspection? | Management Plan
| 7.050 | Project Team Meeting | Regular meeting with project team to discuss progress | Is there a mechanism for meeting with the project team at this stage of the project? | Meeting minutes
| 7.060 | Undertake tasks listed in Handover Strategy. | Conclude activities listed in Handover Strategy including Post-occupancy Evaluation, review of Project Performance, Project Outcomes and Research and Development aspects. | Has the handover strategy been completed? | Handover Strategy
| 7.070 | Design Team Meeting | Regular meeting with project team to discuss design | Is there a mechanism for meeting with the design team at this stage of the project? | Meeting minutes
| 7.080 | Carry out design/ technical review | These reviews may be internal, peer reviews or formal external reviews e.g. Architecture & Design Scotland, as appropriate for the stage of the project. | Have all design and technical issues been considered? | Design and technical review
| 7.090 | Review updated Project Information. | Updating of Project Information, as required, in response to ongoing client Feedback until the end of the building’s life. | Has the project information been reviewed? | Project Information Checklist
| 7.100 | Declare carbon performance. | Has the energy/carbon performance been declared? | Has the carbon report been handed over? | Carbon Performance Report
| 7.110 | Exchange updated 'As constructed' information. | As-constructed' Information updated in response to ongoing client Feedback and maintenance or operational developments. | Has the 'As Constructed' information been provided? | As Constructed Information
| 7.120 | Manage maintenance operations | Administer contract, site inspection, coordinate, valuations/ financial reports, review programme, info to CDM-C. | Is the progress on target? | Landscape Management Plan

## Sources of info
LI Building Information Modeling (BIM) Resources
The LI is promoting and enabling the uptake of BIM by its members. You can find information on the
LI BIM pages:
· An Introduction to BIM: Webinar by Mike Shilton
· What is BIM?
· Publication ‘BIM for Landscape’
· Technical Guidance Notes:
- TGN 01/13 Implications of BIM on PII
- TGN 02/13 Software Considerations
- TGN 03/13 BIM Implementation Plans
- TGN 04/13 BIM Execution Plans
· Dictionary of terms used in BIM
· BIM FAQ
· Product Data Template (PDT) store
· General Practice Note on Software for BIM Projects