## Itemised Costs
MFF 98 2019-20 Wessenden Valley Rhododendron Removal
Contractor name:
Package | Shape | Area (Ha) | Attributes |  |  | Funding | Deadline | Priority (1 high- 3 low) | Package Total £ | Regrowth Rate (Funding dependant) |  |  | Regrowth Total | Treatment of disturbed ground
|  |  | Density | Slope | Plant height |  |  |  |  | Year 1 per ha | Year 2 per ha | Year 3 per ha |  | Gorse Rate per ha | Gorse Total | Geotextiles Rate per ha | Geotextiles Total
1 | 2: Butt A1 | 0.9 | Dense | Rope Access | Small (S)/ Medium (M) | MoorLife 2020 (ML2020) Moors for the Future Partnership | 31.03.2020 | 1 | [5 empty] | N/A | N/A | N/A | N/A
1 | 2: Butt A2 | 0.6 | Dense | Rope Access | S/M | ML2020 | 31.03.2020 | 1 | [5 empty] | N/A | N/A | N/A | N/A
1 | 2: Butt B1 | 4.6 | Scattererd | Less steep | S/M | ML2020 | 31.03.2020 | 1 | [5 empty] | N/A | N/A | N/A | N/A
1 | 2: Butt B2 | 1.5 | Less dense | Rope Access | S/M | ML2020 | 31.03.2020 | 1 | [5 empty] | N/A | N/A | N/A | N/A
1 | 2: Butt B3 | 1.8 | Less dense | Steep and some rope access | S/M | ML2020 | 31.03.2020 | 1 | [5 empty] | N/A | N/A | N/A | N/A
1 | 2: Butt B4 | 0.2 | Less dense | Steep and some rope access | S/M | ML2020 | 31.03.2020 | 1 | [5 empty] | N/A | N/A | N/A | N/A
2 | 4 | 31.6 | Scattered | Flat | M | ML2020 | 18.12.2020 | 2 | [5 empty] | N/A | N/A | NA | N/A
3 | 1 | 3.1 | Very dense | Steep and some rope access | L | Growing Resilience (GR) National Trust | 31.03.2020 | 1
3 | 3 | 4.4 | Dense | Mixed and some rope access | L | GR | 31.03.2020 | 1
3 | 12 | 0.3 | Very Dense | Steep and some rope access | L | GR | 01.12.2020 | 1
4 | 8 | 1 | Scattered | Steep | S | ML2020 | 18.12.2020 | 2 | [5 empty] | N/A | N/A | N/A | N/A
4 | 9 | 0.6 | Scattered | Steep | M | ML2020 | 18.12.2020 | 2 | [5 empty] | N/A | N/A | N/A | N/A
4 | 11 | 1.6 | Scattered | Steep with unstable shale banks | S | ML2020 | 18.12.2020 | 2 | [5 empty] | N/A | N/A | N/A | N/A

## Program of works
Contractor Name: | [12 empty] | Documentation to provide (please tick if provided)
Package | Shape | Area (Ha) | Attributes |  |  | Funding | Deadline | Priority (1 high- 3 low) | Start Date | Finish Date | Total Days to complete | Machinery to be used | Public Liability and Employers Liability Insurance Certificates | NPTC Pesticides qualification PA1 and PA6 | Site specific method statement | Site specific RA | Schedule of Rates for all aspects of work
|  |  | Density | Slope | Plant height | [8 empty] | NPTC Pesticides qualification, with a minimum of PA1 and PA6
1 | 2: Butt A1 | 0.9 | Dense | Rope Access | Small (S)/ Medium (M) | MoorLife 2020 (ML2020) | 31.03.2020 | 1
1 | 2: Butt A2 | 0.6 | Dense | Rope Access | S/M | ML2020 | 31.03.2020 | 1
1 | 2: Butt B1 | 4.6 | Scattererd | Less steep | S/M | ML2020 | 31.03.2020 | 1
1 | 2: Butt B2 | 1.5 | Less dense | Rope Access | S/M | ML2020 | 31.03.2020 | 1
1 | 2: Butt B3 | 1.8 | Less dense | Steep and some rope access | S/M | ML2020 | 31.03.2020 | 1
1 | 2: Butt B4 | 0.2 | Less dense | Steep and some rope access | S/M | ML2020 | 31.03.2020 | 1
2 | 4 | 31.6 | Scattered | Flat | M | ML2020 | 18.12.2020 | 2
3 | 1 | 3.1 | Very dense | Steep and some rope access | L | Growing Resilience (GR) | 31.03.2020 | 1
3 | 3 | 4.4 | Dense | Mixed and some rope access | L | GR | 31.03.2020 | 1
3 | 12 | 0.3 | Very Dense | Steep and some rope access | L | GR | 01.12.2020 | 1
4 | 8 | 1 | Scattered | Steep | S | ML2020 | 18.12.2020 | 2
4 | 9 | 0.6 | Scattered | Steep | M | ML2020 | 18.12.2020 | 2
4 | 11 | 1.6 | Scattered | Steep with unstable shale banks | S | ML2020 | 18.12.2020 | 2