## SOW Compliance
Paragraph Numbers | Title | Compliant | Compliance Rationale (free text)
1 | Introduction
1.1 | General
1.1.1 | This Statement of Work (SOW) of Contract (JSENs00154) defines the Authority’s scope of work required of BAE (Operations) Ltd to meet the requirements for the In-Service sustainment of the Ground Based Air Defence Battlefield Information System Application (GBAD BISA) capability by the provision of a Support Contract.
1.2 | Definitions
1.2.1 | For the purposes of the SOW;
1.2.1.1 | The word “shall” is used exclusively to indicate that the requirement is mandatory.
1.2.1.2 | The word “should” is used to indicate that the requirement is desirable but not mandatory.
1.2.1.3 | The words “will”, “is” and “are” indicate that the associated statement is explanatory material provided in support of the stated requirements.
1.3 | Performance Measurement
1.3.1 | The Support delivered under this contract is subject to a number of Key Performance Indicators (KPI) in accordance with Support Terms and Conditions. The performance management mechanism is designed to monitor and incentivise the Contractor’s performance. The Contractor shall therefore be responsible for the achievement of those KPIs.
2 | Scope
2.1 | General
2.1.1 | The Contractor shall have responsibility for the support of GBAD BISA, as defined by this Statement of Work and the associate Terms and Conditions of this Contract. For the purposes of this statement of work, the GBAD BISA Support consists of;
2.1.1.1 | Fielded Version of GBAD BISA (currently version (Redacted) on Bowman Common Battlefield Applications Toolset (ComBAT) Infrastructure Platform (BCIP) 5.6),
2.1.1.2 | Stand Alone Edition (SAE) (currently version (Redacted)),
2.1.1.3 | Alternative Messaging Software (Alt MS),
2.1.1.4 | Local Network Software (LNS),
2.1.1.5 | The updated versions of GBAD BISA, SAE, Alt MS and LNS (addressed under obsolescence),
2.1.1.6 | Classroom Based Training Equipment,
2.1.1.7 | Reference and Development Rigs.
2.1.2 | The Contractor shall comply with the Authority’s Security Aspects Letter (SAL) of the Contract (JSENS/00154).
3 | CORE – In-Service Support
3.1 | Resourcing
3.1.1 | The Contractor shall provide the resources and materials to successfully deliver all its obligations under the Contract.
3.1.2 | The Contractor shall assign suitably qualified and experienced personnel for the project and inform the Authority of Key Personnel.
3.2 | Design Authority
3.2.1 | The Contractor shall provide on-going Design Authority services for the GBAD BISA capability including the Portable Classroom Based Training (PCBT) systems.
3.3 | Configuration Management
3.3.1 | The Contractor shall conduct Configuration Management in accordance with the requirements of DEF STAN 05-57 “Configuration Management of Defence Material”.
3.3.2 | The Contractor shall maintain the GBAD BISA configuration, build standard, design documentation and online help files for;
3.3.2.1 | Field Version of GBAD BISA (currently v(Redacted)),
3.3.2.2 | SAE of GBAD BISA (currently v(Redacted)),
3.3.2.3 | The obsolescence versions of GBAD BISA, SAE, Alt MS and LNS configured and stored within BAE Systems’ development environment, ready to be used as a baseline for future capability updates.
3.3.2.4 | Alt MS software required to provide the required quality of service for GBAD BISA,
3.3.2.5 | LNS software required for the use on training and development rigs for networking of GBAD BISA where Bowman is not present.
3.4 | Quality Management
3.4.1 | The Contractor shall maintain, throughout the duration of this Contract, it’s appropriately scoped certificated ISO 9001 QMS, which should be certificated by a Certification Body that is accredited by UKAS, or equivalent.
3.4.2 | The Contractor shall manage on site Contractor personnel in accordance with Def Stan 05-61 Part 4, Issue 3 - Quality Assurance Procedural Requirements - Contractor Working Parties.
3.5 | Government Furnished Assets Management
3.5.1 | The Contractor shall manage any Government Furnished Assets (GFA) provided in accordance with Def Stan 05-099 Part 1 and the Terms and Conditions of this Contract.
3.6 | Software Defects
3.6.1 | The Contractor shall maintain a list of software defects identified for the fielded version (v4.4.7) and SAE version (v2.0) of GBAD BISA which shall be reviewed at the Quarterly Project Meetings (QPM).
3.7 | Software Enhancements
3.7.1 | The Contractor shall maintain a list of potential software enhancements for future versions of GBAD BISA (Fielded or SAE versions) based on enhancements put forward by either the Contractor or the Authority to include the Military End User which, shall be reviewed at the QPM.
3.8 | Activity Register
3.8.1 | The Contractor shall maintain an activity register used to status of non-core and ad-hoc tasking which shall be reviewed at the QPM.
3.9 | KPI Reporting
3.9.1 | The Contractor shall provide to the Authority an Excel spreadsheet at the end of each month which records the status of the KPIs.
3.1 | Risk Management
3.10.1 | The Contractor shall operate a risk management process to ensure that risks are mitigated and managed, or the probability of occurrence and impact are minimised.
3.10.2 | The Contractor shall maintain a risk register of risks for the fielded and SAE versions of GBAD BISA which shall be reviewed at the QPM and GBAD Stakeholder Meetings.
3.11 | Safety and Environment Management
3.11.1 | The Contractor shall support the Authority in conducting Safety Management in accordance with DEF STAN 00-056 (Safety Management Requirements for Defence Systems), DEF STAN 00-051 (Environmental Management Requirements for Defence Systems) and Acquisition Safety and Environmental Management Systems (ASEMS) Project Oriented Safety Management System (POSMS) and Project Oriented Environmental Management System (POEMS).
3.11.2 | The Contractor shall monitor and maintain product safety status for the fielded and SAE versions of GBAD BISA and will notify the Authority immediately if it identifies or becomes aware of any decrease to the safety of personnel due to the operation of the GBAD BISA application.
3.12 | Security Management
3.12.1 | The Contractor shall monitor and maintain product security (including security and anti-virus updates/patches) for the fielded version of GBAD BISA (including the CBT classrooms) and will notify the Authority immediately if it identifies or becomes aware of any impact to the security accreditation of GBAD BISA (including the CBT classrooms).
3.13 | Incident Report Investigation
3.13.1 | The Contractor shall investigate technical issues arising from in-service Incident Reports raised by the Users on the current fielded version of GBAD BISA and provide advice in terms of recommended courses of action(s) back to the User within 5 working days.
3.13.2 | The Contractor shall maintain the Incident Report Database and enter onto the database new software Incident Reports / JAMES Component Reports as they arise, this shall be reviewed at the Quarterly Progress Meeting (QPM).
3.14 | In-Service Meetings
3.14.1 | The Contractor shall convene a QPM chaired by the Authority between the Contractor and the Authority to brief (via a presentation) the Authority on completed and on-going activities. The meeting will be convened at 7 Air Defence (AD) Group (Redacted).
3.14.2 | The Contractor shall invite the following attendees to the QPM;
3.14.2.1 | 7 AD Group,
3.14.2.2 | Joint Sensor And Engagement Networks Delivery Team (JSENS DT),
3.14.2.3 | Army HQ (GBAD Through Life Support),
3.14.2.4 | Joint System Integration Body (JSIB),
3.14.2.5 | Royal Artillery Trials and Development Unit (RATDU).
3.14.3 | The following shall be the minimum agenda items:
3.14.3.1 | Configuration Control (including CCBs),
3.14.3.2 | Safety Management,
3.14.3.3 | Security Management,
3.14.3.4 | In-Service Review (to include Incident and JAMES CR status),
3.14.3.5 | Capability Uplift(s) Review,
3.14.3.6 | Activity Register Review,
3.14.3.7 | Risk Register Review,
3.14.3.8 | Additional agenda items may be included in a QPM at the request, or by agreement, of the Authority.
3.14.4 | The Contractor shall provide minutes (and the accompanying presentation) for each QPM accurately recording the discussions between the parties and any decisions and actions agreed during the meeting. The minutes (and presentation) shall be provided to the Authority’s Project Manager within twenty (20) working days of the meeting being held.
3.14.5 | The Contractor shall attend and provide Design Authority support to the quarterly GBAD (BISA) Stakeholder Meeting chaired by 7 AD Group to be held at 7 AD Group premises (Redacted).
3.14.6 | The Contractor shall attend and provide Design Authority support to the bi-annual Joint Stakeholder Forum for the BOWMAN stakeholder community chaired by the JSIB and convened at (Redacted).
3.14.7 | The Contractor shall attend and provide Design Authority support to an Annual GBAD BISA Safety Panel chaired by the Authority to be held at 7 AD Group premises (Redacted).
3.15 | Development Test Rigs
3.15.1 | The Contractor shall maintain the two development test rigs at the following premises; (Redacted)l used throughout the length of the Contract for both assurance of;
3.15.1.1 | 3rd and 4th line in-service support to the military end user, and
3.15.1.2 | Maintain a level of regression testing for the Bowman (BCIP) Capability Uplift programme.
4 | CORE - Software Licences
4.1.1 | The Contractor shall provide on-going provision and support of software licences required for GBAD BISA operation and training throughout the length of the Contract;
4.1.1.1 | Alt MS required to achieve the quality of service required for GBAD BISA on Bowman, and
4.1.1.2 | LNS required for use on training and development rigs for networking of GBAD BISA where Bowman is not present.
5 | CORE - Field Support Engineer
5.1.1 | The Contractor shall provide a full-time Field Support Engineer (FSE) throughout the length of the Contract, who shall be embedded with the (Redacted).
5.1.2 | The Contractor FSE shall assist and provide technical engineering support and assistance to the following units;
5.1.2.1 | 7 AD Group,
5.1.2.2 | RHQ Royal Artillery (RHQ RA),
5.1.2.3 | Royal School of Artillery (RSA),
5.1.2.4 | Royal Artillery Trials Development Unit (RATDU),
5.1.2.5 | Royal Artillery Regiments,
5.1.2.4.1 | 12 Regt RA,
5.1.2.4.2 | 16 Regt RA,
5.1.2.4.3 | 106 Regt RA.
5.1.2.6 | Royal Marine Air Defence Troop (RM AD Group),
5.1.2.7 | 259 (Global Information Service) Signal Squadron, 13 Signals Regiment,
5.1.3 | The Contractor FSE shall provide technical assistance and engineering support to RATDU and the GBAD community for;
5.1.3.1 | Fielded Version of GBAD BISA,
5.1.3.2 | Stand Alone Edition of GBAD BISA,
5.1.3.3 | Alt MS,
5.1.3.4 | LNS,
5.1.3.5 | Trials and Testing,
5.1.3.6 | Trend analysis,
5.1.3.7 | Integration and Interoperability,
5.1.3.8 | Training,
5.1.3.9 | Field exercises,
5.1.3.10 | Security patching and anti-virus updates.
5.1.4 | The Contractor FSE shall support, maintain and coordinate the Virus patching of GBAD BISA training systems at the user locations;
5.1.4.1 | 12 Regiment RA – Based at Thorney Island,
5.1.4.2 | 16 Regiment RA – Based at Thorney Island,
5.1.4.3 | 106 Regiment RA (Reservists) – Based at Southampton, Portsmouth and Grove Park, London,
5.1.4.4 | Royal Marine Air Defence Troop – Based at Stonehouse Barracks Plymouth,
5.1.4.5 | RATDU laptops – Based at Larkhill,
5.1.4.6 | GBAD Section RSA – Based at Larkhill,
5.1.4.7 | YOs Branch RSA – based at Larkhill,
5.1.4.8 | 7 AD Group Laptop – Based at Thorney Island.
5.1.5 | The Contractor FSE shall provide the theatre focal point for all software fault collation raised by the User community.
5.1.6 | The Contractor FSE shall assist RATDU in devising, testing and advising on Restriction Orders (RO) and work round procedures where faults have operational or training implications.
5.1.7 | The Contractor FSE shall assist RATDU in devising and advising on Standing Operating Procedures (SOP).
5.1.8 | The Contractor FSE shall produce a written summary report of any meetings, conference, presentation or visit undertaken within 5 working days of the activity being held.
6 | CORE - Capability Uplifts - Background
6.1 | Overview
6.1.1 | The Battlefield and Tactical Communications & Information Systems (BATCIS) Design Service Contract[1] (DSC) programme of work is a 5 year programme to provide support to the in service BCIP tactical communications system. Its purpose is to ensure that the safety, security, performance, integrity and configuration of the BCIP system is maintained.
6.1.2 | To maintain a safe and secure system, General Dynamic Mission Systems UK (GDMS-UK) are required to provide an annual uplift. These changes are known as Capability Uplifts (CU), and changes to the system will include an agreed set of Microsoft Operating System (OS) patches and updates associated with other Commercial off The Shelf (COTS) software that forms part of the baseline (e.g. Microsoft Office). This is done through the delivery of a Software Update Package (SUP) that can be installed by the User in the field onto all User Data Terminals (UDTs).
6.1.3 | The current proposed programme will consist of four (4) CUs. The first of these known as CU1 has gone straight to shelf. The follow on CUs will be fielded and the current planned programme (CU2 is currently ongoing), figure 6-1.
6.1.4 | All BISAs are required to analyse the proposed changes, undertake regression testing in order that the changes introduced by the CU have not caused the BISA to regress in any way and that it continues to function correctly, safely and securely and if required; make the required changes in order it remains so.
6.1.5 | GDMS-UK will provide a BDE, which is fully representative of the target environment. This will be supplied in a series of 3 drops per CU and include all Microsoft Patches and changes to the required baseline as follows;
6.1.5.1 | De-risk BDE (this will not include all the changes),
6.1.5.2 | Platform BDE (this will include all the changes),
6.1.5.3 | Final BDE.
7 | CORE - Capability Uplift 2
7.1 | General
7.1.1 | Capability Uplift 2 (CU 2) began in April 2020 with the release of a series of Technical Letters which outlined the proposed changes to be considered for CU 2.
7.1.2 | The Contractor under taskings on the JSENS/00128 contract has already undertaken 2 activities as follows;
7.1.2.1 | (Redacted)
7.1.2.2 | (Redacted)
7.2 | BDE Testing
7.2.1 | The Contractor shall take delivery of two (2) further BDEs from the JSIB and undertake regression testing and provide feedback in the form of a report to the Authority on the impact or otherwise on the fielded GBAD BISA baseline;
7.2.1.1 | Platform BDE (January 2021),
7.2.1.2 | Final BDE (March 2021).
7.3 | CU 2 Meetings
7.3.1 | The Contractor shall attend three (3) CU 2 GBAD BISA Progress Review Meetings (PRM). The Meetings will be convened at the (Redacted). Note: if deemed adequate by the parties (i.e. JSIB, BISA developer, Authority, User) a dial-in-telecom maybe sufficient to meet the needs of the PRM.
7.3.2 | The Contractor shall attend CU 2 System Integration Readiness Gates (SIRG) 2/3, 4/5, 7a and 7 meetings to support the CU 2 programme interface between GBAD BISA and the BCIP and cover issues such as but, not limited to interoperability and system integration. The Meetings will be convened at the (Redacted)). Note: if deemed adequate by the parties (i.e. JSIB, BISA developer, Authority, User) a dial-in-telecom maybe sufficient to meet the needs of the SIRG.
7.3.3 | The Contractor shall attend three (3) Pre-Disposition Boards (PDB); to sentence System Problem Reports raised during the System Integration process. The Meetings will be convened at the (Redacted)). Note: if deemed adequate by the parties (i.e. JSIB, BISA developer, Authority, User) a dial-in-telecom maybe sufficient to meet the needs of the PDB.
7.4 | JSIB Integration CU 2 Support
7.4.1 | The Contractor shall support the JSIB integration activities of GBAD BISA version 4.4.7 software build for the Capability Uplift implementation by the provision of Subject Matter Expertise (SME) technical advice, ten (10) working days of effort.
7.5 | CU 2 GBAD BISA Documentation
7.5.1 | The Contractor shall review the JSIB Reference Baseline Document (formerly known as the Interface Control Document) and provide feedback to the Authority and JSIB.
7.5.2 | The Contractor shall review, update and deliver as appropriate if required the GBAD BISA Software Safety Case Report and Hazard Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 2 baseline to support the SIRG 7.
7.5.3 | The Contractor shall produce and deliver a GBAD BISA Security Impact Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 2 baseline to support the SIRG 7.
8 | CORE - Capability Uplift 3
8.1 | General
8.1.1 | Capability Uplift 3 (CU 3) is scheduled to begin in (Redacted) with the release of a series of Technical Letters which will outline the proposed changes to be considered as part of the CU 3.
8.2 | CU 3 Technical Letters
8.2.1 | The Contractor shall analyse the technical letters (three (3) letters) released for CU 3 and provide a paper based assessment on the impact or otherwise on the fielded GBAD BISA baseline.
8.3 | CU 3 Meetings
8.3.1 | The Contractor shall support the Configuration Change Board (CCB) in late May 2021 where the proposed changes to be undertaken as part of CU 3 are formalised. The Meeting will be convened at the (Redacted)). Note: if deemed adequate by the parties (i.e. JSIB, BISA developer, Authority, User) a dial-in-telecom maybe sufficient to meet the needs of the CCB.
8.3.2 | The Contractor shall attend four (4) CU 3 GBAD BISA Progress Review Meetings. The Meetings will be convened at the (Redacted). Note: if deemed adequate by the parties (i.e. JSIB, BISA developer, Authority, User) a dial-in-telecom maybe sufficient to meet the needs of the PRM.
8.3.3 | The Contractor shall attend CU 3 System Integration Readiness Gates (SIRG) 0, 1, 2, 3, 4, 5 and 7 meetings to support the CU 3 programme interface between GBAD BISA and the BCIP and cover issues such as but, not limited to interoperability and system integration. The Meetings will be convened at the (Redacted)). Note: if deemed adequate by the parties (i.e. JSIB, BISA developer, Authority, User) a dial-in-telecom maybe sufficient to meet the needs of the SIRG.
8.3.4 | The Contractor shall attend four (4) Pre-Disposition Boards (PDB); to sentence System Problem Reports raised during the System Integration process. The Meetings will be convened at the (Redacted). Note: if deemed adequate by the parties (i.e. JSIB, BISA developer, Authority, User) a dial-in-telecom maybe sufficient to meet the needs of the PDB.
8.4 | JSIB Integration CU 3 Support
8.4.1 | The Contractor shall support the JSIB integration activities of GBAD BISA software build for the CU implementation by the provision of SME technical advice, ten (10) working days of effort.
8.5 | CU 3 BDE Testing
8.5.1 | The Contractor shall take delivery of three (3) BDEs from the JSIB and undertake regression testing and provide feedback in the form of a report to the Authority on the impact or otherwise on the fielded GBAD BISA baseline;
8.5.1.1 | De-risk BDE (August 2021),
8.5.1.2 | Platform BDE (January 2022),
8.5.1.3 | Final BDE (March 2022).
8.6 | CU 3 GBAD BISA Documentation
8.6.1 | The Contractor shall review the JSIB Reference Baseline Document (formerly known as the Interface Control Document) and provide feedback to the Authority and JSIB.
8.6.2 | The Contractor shall review, update and deliver as appropriate if required the GBAD BISA Software Safety Case Report and Hazard Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 3 baseline to support the SIRG 7.
8.6.3 | The Contractor shall produce and deliver a GBAD BISA Security Impact Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 3 baseline to support the SIRG 7.
9 | CORE - Capability Uplift 4
9.1 | General
9.1.1 | Capability Uplift 4 (CU 4) is scheduled to begin in (Redacted) with the release of a series of Technical Letters which will outline the proposed changes to be considered as part of the CU 4.
9.2 | CU 4 Technical Letters
9.2.1 | The Contractor shall analyse the technical letters (three (3) letters) released for CU 4 and provide a paper based assessment on the impact or otherwise on the fielded GBAD BISA baseline.
9.3 | CU 4 Meetings
9.3.1 | The Contractor shall support the Configuration Change Board (CCB) in late May 2022 where the proposed changes to be undertaken as part of CU 4 are formalised. The Meeting will be convened at the (Redacted)). Note: if deemed adequate by the parties (i.e. JSIB, BISA developer, Authority, User) a dial-in-telecom maybe sufficient to meet the needs of the CCB.
9.3.2 | The Contractor shall attend four (4) CU 4 GBAD BISA Progress Review Meetings. The Meetings will be convened at the (Redacted). Note: if deemed adequate by the parties (i.e. JSIB, BISA developer, Authority, User) a dial-in-telecom maybe sufficient to meet the needs of the PRM.
9.3.3 | The Contractor shall attend CU 4 System Integration Readiness Gates (SIRG) 0, 1, 2, 3, 4, 5 and 7 meetings to support the CU4 programme interface between GBAD BISA and the BCIP and cover issues such as but, not limited to interoperability and system integration. The Meetings will be convened at the (Redacted)). Note: if deemed adequate by the parties (i.e. JSIB, BISA developer, Authority, User) a dial-in-telecom maybe sufficient to meet the needs of the SIRG.
9.3.4 | The Contractor shall attend four (4) Pre-Disposition Boards (PDB); to sentence System Problem Reports raised during the System Integration process. The Meetings will be convened at the (Redacted)). Note: if deemed adequate by the parties (i.e. JSIB, BISA developer, Authority, User) a dial-in-telecom maybe sufficient to meet the needs of the PDB.
9.4 | JSIB Integration CU 4 Support
9.4.1 | The Contractor shall support the JSIB integration activities of GBAD BISA software build for the CU implementation by the provision of SME technical advice, ten (10) working days of effort.
9.5 | CU 4 BDE Testing
9.5.1 | The Contractor shall take delivery of three (3) BDEs from the JSIB and undertake regression testing and provide feedback to the Authority in the form of a report on the impact or otherwise on the fielded GBAD BISA baseline;
9.5.1.1 | De-risk BDE (August 2022),
9.5.1.2 | Platform BDE (January 2023),
9.5.1.3 | Final BDE (March 2023).
9.6 | CU 4 GBAD BISA Documentation
9.6.1 | The Contractor shall review the JSIB Reference Baseline Document (formerly known as the Interface Control Document) and provide feedback to the Authority and JSIB.
9.6.2 | The Contractor shall review, update and deliver as appropriate if required the GBAD BISA Software Safety Case Report and Hazard Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 4 baseline to support the SIRG 7.
9.6.3 | The Contractor shall produce and deliver a GBAD BISA Security Impact Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 4 baseline to support the SIRG 7.
10 | NON CORE – Taskings
10.1 | Introduction
10.1.1 | This section sets out the Post Design Services (PDS) work the Contractor shall deliver for the sustainment of the GBAD BISA as and when separately tasked to do so.
10.2 | Post Design Service
10.2.1 | The Contractor shall conduct PDS) tasks as authorised by the Authority and agreed by the Contractor.
10.2.2 | All individual tasks shall be firm priced. The Contractor shall prepare and submit a quotation containing the following details:
10.2.2.1 | Estimate of Engineering and other relevant Department activities and with a detailed breakdown of materials for the task;
10.2.2.2 | An assurance that Engineering and other relevant Departmental internal and external resources are available including timescales for completion of the task;
10.2.2.3 | Detail the content of the task to be performed against the contract.
10.3 | Other Contract Technical and Management Meetings
10.3.1 | Tasks may include other occasional meetings on other issues or Ad-Hoc meetings which may be required by the Authority. The Contractor shall ensure adequate representation.
10.4 | GBAD BISA Baseline Changes
10.4.1 | The Contractor regression testing against the capability uplift changes may result in issues that require the GBAD BISA software baseline to be investigated and issues addressed.
10.4.2 | The Contractor shall investigate the defects or product behavioural observations that relate to requirements or the delivered GBAD BISA system design that have emerged from undertaking regression testing with the supplied BDE baseline.
10.4.3 | The Contractor shall implement software changes to address the defects or product behavioural observations that have emerged from the investigations following regression testing.
10.4.4 | The Contractor shall rebuild the GBAD BISA Software Baseline and undertake System Testing to ensure the software changes have been implemented appropriately.
10.4.5 | The Contractor shall undertake a regression test of the new GBAD BISA Software Baseline against the CU BDE baseline to confirm the changes required have corrected the issues.
10.4.6 | The Contractor shall document and provide to the Authority and the JSIB the changes that have been implemented to correct the defects or product behavioural observations that have emerged.
10.4.7 | The Contractor shall provide an Engineering Release build of the GBAD BISA software to the JSIB in order for risk reduction integration activities to be undertaken by the JSIB organisation. It is recognised these Engineering Releases will be in advance of formal testing and acceptance and hence may be incomplete.
10.4.8 | The Contractor shall provide a build for the JSIB to undertake SIRG 5 Systems Integration.
10.4.9 | The Contractor shall provide the final stable build (gold disk) for the JSIB to undertake SIRG 7 Formal Systems Integration activities.
10.4.10 | The Contractor shall ensure that all appropriate GBAD BISA documentation (including Help files) is updated to capture the nature of any change to ensure its ongoing support through the In-Service Support Contract.
10.4.11 | The Contractor shall provide a Certificate of Design for the new GBAD BISA release.
11 | DELIVERABLES / MILESTONES
11.1 | The following Core items shall be deliverable to the Authority
11.1.1 | A KPI status spreadsheet – to be published at the end of each month,
11.1.2 | A formal Quarterly Project Meeting (QPM)– to be held quarterly,
11.1.3 | A formal set of QPM minutes in Microsoft Word or PDF – to be published within 20 working days of each QPM,
11.1.4 | A QPM Presentation in Power Point or PDF to be published alongside the formal set of QPM minutes - to be published within 20 working days of each QPM,
11.1.5 | A Prioritised bug / enhancement list to support the QPM in Microsoft Excel format – to be provided at each QPM,
11.1.6 | An updated Risk Register to support the QPM in Microsoft Excel or PDF format - to be provided at each QPM,
11.1.7 | An updated Activity Register to support the QPM in Microsoft Word or PDF – to be provided at each QPM,
11.1.8 | An FSE summary report in Microsoft Word or PDF format following any meeting, conference, presentation or visit within 5 working days.
11.1.2 | The following CU 2 items shall be deliverable to the Authority/JSIB:
11.1.2.1 | A CU 2 BDE regression testing report(s) in Microsoft Word or PDF format of the impact or otherwise of the proposed CU 2 changes,
11.1.2.2 | Comments and feedback on the JSIB CU 2 Reference Baseline Documentation.
11.1.2.3 | An updated GBAD BISA Software Safety Case Report and Hazard Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 2 baseline.
11.1.2.4 | An updated Security Impact Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 2 baseline.
11.1.3 | The following CU 3 items shall be deliverable to the Authority/JSIB
11.1.3.1 | A CU 3 summary report in Microsoft Word or PDF format of the impact or otherwise of the proposed CU3 changes (technical Letters) on the GBAD BISA,
11.1.3.2 | A CU 3 BDE regression testing report(s) in Microsoft Word or PDF format of the impact or otherwise of the proposed CU 3 changes,
11.1.3.3 | Comments and feedback on the JSIB CU 3 Reference Baseline Documentation.
11.1.3.4 | An updated GBAD BISA Software Safety Case Report and Hazard Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 3 baseline.
11.1.3.5 | An updated Security Impact Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 3 baseline.
11.1.4 | The following CU 4 items shall be deliverable to the Authority/JSIB:
11.1.4.1 | A CU 4 summary report in Microsoft Word or PDF format of the impact or otherwise of the proposed CU 4 changes (technical Letters) on the GBAD BISA,
11.1.4.2 | A CU 4 BDE regression testing report(s) in Microsoft Word or PDF format of the impact or otherwise of the proposed CU 4 changes,
11.1.4.3 | Comments and feedback on the JSIB CU 4 Reference Baseline Documentation.
11.1.4.4 | An updated GBAD BISA Software Safety Case Report and Hazard Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 4 baseline.
11.1.4.5 | An updated Security Impact Analysis for the implementation of GBAD BISA software build on the BCIP 5.6 CU 4 baseline.

## List
YES
NO