DPS FRAMEWORK SCHEDULE 4: LETTER OF APPOINTMENT AND CONTRACT TERMS

  - Letter of Appointment

Cordis Bright Ltd

23-24 Smithfield Street,

London,

EC1A 9LF

Dear Sirs

Letter of Appointment

This letter of Appointment dated 01/02/2021, is issued in accordance with the provisions of the DPS Agreement (RM6018) between CCS and the Supplier.

Capitalised terms and expressions used in this letter have the same meanings as in the Contract Terms unless the context otherwise requires.

| Order Number: | To be provided post-award |
| --- | --- |
| From: | Ministry of Housing, Communities & Local Government ("Customer") |
| To: | Cordis Bright Ltd ("Supplier") |

| Effective Date: | 1st February 2021 |
| --- | --- |
| Expiry Date: | End date of Initial Period: 31st July 2021 End date of Maximum Extension Period: 31st January 2022 |

| Services required: | Set out in Section 2, Part B (Specification) of the DPS Agreement and refined by: the Supplier’s Proposal attached at Annex B. |
| --- | --- |

| Key Individuals: | Customer REDACTED, Principal Research Officer, Ministry of Housing, Communities and Local Government Suppliers REDACTED, Senior Consultant REDACTED, Director REDACTED, Senior Consultant |
| --- | --- |
| [Guarantor(s)] | Not Applicable |

| Contract Charges (including any applicable discount(s), but excluding VAT): | Set out in Schedule 6: Contract Charges of the DPS Agreement. For the avoidance of doubt this contract shall not exceed the amount of 49,913.00 GBP excluding VAT and extension options. |
| --- | --- |
| Insurance Requirements | Product liability insurance cover all risks in the provision of Deliverables under the Contract, with a minimum limit of £1 million for each individual claim. |
| Liability Requirements | Suppliers limitation of Liability (Clause 18.2 of the Contract Terms). |
| Customer billing address for invoicing: | All invoices are to be submitted to: CP2P Team, MHCLG, 4th Floor, High Trees, Hillfield Road, Hemel Hempstead, HP2 4XN. Email address: REDACTED |

| GDPR | Contract Terms Schedule 7 (Processing, Personal Data and Data Subjects. |
| --- | --- |
| Alternative and/or additional provisions (including Schedule 8(Additional clauses)): | Not applicable. |

FORMATION OF CONTRACT

BY SIGNING AND RETURNING THIS LETTER OF APPOINTMENT (which may be done by electronic means) the Supplier agrees to enter a Contract with the Customer to provide the Services in accordance with the terms of this letter and the Contract Terms.

The Parties hereby acknowledge and agree that they have read this letter and the Contract Terms.

The Parties hereby acknowledge and agree that this Contract shall be formed when the Customer acknowledges (which may be done by electronic means) the receipt of the signed copy of this letter from the Supplier within two (2) Working Days from such receipt

For and on behalf of the Supplier:                            For and on behalf of the Customer:

Name and Title: REDACTED                                       Name and Title: REDACTED

Signature: REDACTED                                                Signature: REDACTED

Date: 8th February 2021                                               Date: 2nd February 2021

Annex A

Customer Project Specification

CONTRACT REFERENCE: CCZZ20A86 MULTIPLE COMPLEX NEEDS FEASIBILITY STUDY

# PURPOSE

## The purpose of this commission is to procure a short feasibility study to advise MHCLG and its partner Departments on an appropriate and effective evaluation design for the Multiple Complex Needs (MCN) programme.

## Project tasks and responsibilities will include a review of the existing literature on MCN, qualitative research with expert evaluators and data managers to gather views on appropriate approaches and sound out concerns to the design of the evaluation.

## This study will also help inform the programme design as well, with a particular focus on the data requirements for managing the programme.

## The supplier will provide advice to MHCLG and its partners, analyse the data, provide a presentation of key findings and recommendations and an accompanying report.

# BACKGROUND TO THE CONTRACTING AUTHORITY

## The Ministry of Housing, Communities and Local Government (hereafter referred to as ‘the Customer’) aims to help create great places to live and work right across the country and to back communities to come together and thrive. We strive to:

## Deliver the homes the country needs

## Make the vision of the place you call home a reality

## Support local government to deliver high quality services with sustainable finances

## Create strong communities, socially, economically and a sense of place

## Secure effective support for those effected by the Grenfell Tower disaster, delivering the changes this tragedy demands and ensuring people are safe and feel safe within their homes

## Support a smooth exit from the European Union

## Our Single Departmental Plan can be found on the GOV.UK website.

# BACKGROUND TO REQUIREMENT / OVERVIEW OF REQUIREMENT

## The Multiple Complex Needs (MCN) programme was announced on 11 March 2020 at Budget with £46m of funding from the Shared Outcomes Fund.

## MHCLG is leading this cross-government programme to better support adults who face multiple disadvantages. Other government departments with an interest in this programme include Ministry of Justice, Department for Work and Pensions, HM Treasury, Home Office, Department for Health and Social Care, Department for Culture, Media and Sport, Public Health England, NHS England.

## The MCN programme will undertake a three-year pilot to support around 8-15 local areas to deliver new interventions and systems change to better support up to thousands of individuals with multiple complex needs. This is defined as a combination of: offending, substance misuse, homelessness, domestic abuse / violence and poor mental health.

## MHCLG plans to publish a prospectus later in the year with more details on the programme design and area selection process for the pilots.

## A key part of the programme will be the design of an appropriate and effective evaluation to assess programme outcomes. This will influence the corresponding data system and data requirements for the programme, as well as the programme design.

# DEFINITIONS

| ## Expression or Acronym | ## Definition |
| --- | --- |
| ## MHCLG | ## The Ministry of Housing, Communities and Local Government. |
| ## MCN | ## The Multiple Complex Needs programme. |

# SCOPE OF REQUIREMENT

## The purpose of the feasibility study is to establish an appropriate evaluation design which will generate insights which will enable us to understand whether the MCN pilot programme is effective.

## The table below sets out the range of sources that will be included in the exercise. It sets out the Customer’s vision for how responsibility will be assigned:

| ## Owner | ## Activity |
| --- | --- |
| ## Customer | ## Provide suggestions for suitable candidates for interviews; support supplier in making contact with potential interviewees, providing assurances for the project. ## Share any reports and findings that have been gathered to support desk-based research and development of research materials. ## Support the supplier with advice and knowledge on the programme and methodological expertise. |
| ## Supplier | ## Management of recruitment and fulfilling sampling quotas with support from MHCLG. ## Work with MHCLG to agree and finalise the design of the research to be undertaken, including data collection method and analysis strategy. ## Preparation of research materials such as interview guides and stimulus. ## Conduct research to address the research questions set out in section 3, which will include: ## Interviews with evaluation experts who can provide advice and guidance regarding the study design and methodology, with particular consideration to the MCN client group of interest. ## Interviews with data and information governance managers in local authorities and/or Government Departments to establish current data collection and management practices. Interviews with this group will also cover feasibility of setting up new data collection exercises to support the delivery of the programme and the evaluation. ## Regular meetings held via video conference or telephone and written updates detailing recently completed tasks, upcoming activities and notifying MHCLG of important developments on the project. ## Present findings to MHCLG, outline and explain key insights. Use quotes and examples from participants to illustrate findings. Respond to questions from MHCLG, providing clarifications. ## Produce a final report that takes account of findings from this research project and findings from previous research and reports conducted by MHCLG. |

## The supplier will provide a presentation of key findings to MHCLG after the fieldwork period has ended. MHCLG is working to a tight timeframe and requires an informal debrief of topline findings by 28 December 2020. A presentation of full key findings is to be given no later than week commencing 11 January 2021 in order to feed findings into the development of the programme prospectus.

## The supplier will produce a final report that takes account of the diverse information that has been collected and clearly synthesises the key findings. The final, signed-off version of the report will need to be submitted to MHCLG by week commencing 1 February 2021.

## The supplier will be expected to respect social distancing rules set by the government to stop the spread of Covid-19 throughout the project management and research process. The successful supplier will be free to adjust their methods, in line with national and local restrictions.

## The project will be overseen by policy officials and analysts. The supplier will be expected to have regular Project sessions with MHCLG to discuss progress and expectations. The supplier will have access to expert knowledge of the programme and it is expected this will be utilised. MHCLG will provide necessary information to the supplier relating to previous findings and methodology.

# THE REQUIREMENT

## Research objectives

## The primary objective of this feasibility study is to establish an appropriate evaluation design that will generate insights to help us understand whether the MCN pilot programme is effective The study will therefore inform the programme design to ensure it delivers an evaluation with high standards of evidence.

## The evaluation will seek to establish the impact of the programme against a number of outcomes, relevant to the experience of the MCN client group. The selection of the outcomes to be used in the evaluation will be informed by findings from the feasibility study. At this stage, we intend to look at individual, service and system level metrics.

## Findings from the impact analysis will be used to conduct a Cost Benefit Analysis to assess whether the MCN programme represents value for money and provides financial and economic benefits against the programme costs.

## The evaluation will also comprise a process evaluation, to understand how the programme is being delivered in local settings, how it has been adapted, and what changes can be made to the programme to improve outcomes for individuals and service providers.

## Key research questions for the feasibility study include:

## What real-world outcomes should the programme seek to influence, for clients who engage with the programme?

## What data is available which can be used as metrics to measure the effect of the programme on the aforementioned real-world outcomes?

## One aim of the programme is to affect a systemic change, joining up local services to work together, sharing information. What evaluative approaches can be taken to measure this outcome?

## What other data will need to be collected to support the evaluation and the programme, and what data systems will need to be in place in Local Authorities to facilitate this?

## What challenges exist in designing an impact evaluation with this client group, in particular with consideration to selecting a treatment and comparison group, and how can these challenges be overcome?

## Project overview

## The supplier will conduct a small-scale research project in order to answer the above questions. In summary, the supplier will:

## Conduct desk-based research and produce a literature review of existing evidence

## Design research materials

## Recruit and manage the research sample

## Conduct qualitative research

## Analyse data and produce key findings

## Present key findings and recommendations to MHCLG

## Synthesise key findings from the literature review and interviews, write up into short report for MHCLG

## The project is working to a tight timescale; therefore the supplier will need to work at pace to design, develop and deliver this project.

## We are happy for the supplier to suggest their own approach to conducting this feasibility study. However, we would anticipate that the supplier will conduct desk-based research to gather relevant studies, findings and information to form the literature review.

## We also anticipate the supplier will conduct interviews with experts to gather the required data and information to answer the key research questions.

## Bidders are welcome to suggest alternative approaches, providing a rationale for the proposed approach and methodology, and a demonstration of how they will ensure their approach can be delivered within the project timeline and budget.

# KEY MILESTONES AND DELIVERABLES

## Tasks and deliverables the supplier is expected to complete:

### Desk based research of the existing MCN and evaluation literature to inform the design of the proposed evaluation for the MCN programme;

### A set of structured and semi-structured sessions with the supplier across the duration of the feasibility study to develop their understanding of the evaluation issues, and advise on emerging programme development and evaluation proposals;

### Development and writing of research materials, primarily interview guides, for use in interviews with data managers and evaluation experts;

### Recruit interviewees and manage sample through fieldwork;

### Conduct all qualitative fieldwork;

### Analyse data collected from fieldwork;

### Synthesise findings from desk-based research and qualitative research to produce:

### A presentation delivered to MHCLG outlining key findings and recommendations;

### A short report written in Microsoft Word/PDF format covering the activities undertaken within in the feasibility study, and key findings and recommendations from the desk-based research and qualitative research

## The following deliverables are critical to the fulfilment of the Contract should Potential Bidders choose to frame their bids using a case study approach. Any necessary adjustments to the timeline will be agreed in advance between the Customer and the Supplier.

| ### Deliverable | ### Description | ### Timeframe/Delivery Date |
| --- | --- | --- |
| ### 1 | ### Project set up; start literature review; write research materials; start recruitment. | ### 22 January 2021 |
| ### 2 | ### Completion of literature review; sign-off of research materials; start of fieldwork | ### 5 February 2021 |
| ### 3 | ### Completion of fieldwork and interviews; delivery of top line findings debrief. | ### 26 February 2021 |
| ### 4 | ### Deliver presentation of key findings and recommendations; drafting final report | ### w/c 15 March 2021 |
| ### 5 | ### Deliver final report | ### w/c 29 March 2021 |

# MANAGEMENT INFORMATION/REPORTING

## Throughout the Contract, regular progress meetings will be required between the Supplier and the Customer, plus other meetings as necessary. Meetings will be conducted in accordance with social distancing rules at that time; using video conferencing or telephone when required. The Supplier will be expected to take on board feedback from the Customer and other experts feeding into the project.

# VOLUMES

## The contract will terminate upon completion of the final report and sign-off from the Project Lead/Minister.

# CONTINUOUS IMPROVEMENT

## The Supplier should present new ways of working to the Customer during Contract review meetings should they identify an opportunity to improve project delivery.

## Changes to the way in which the Services are to be delivered must be brought to the Customer’s attention and agreed prior to any changes being implemented.

# SUSTAINABILITY

## There are no sustainability considerations that Potential Bidders need to include in their submissions.

# QUALITY

## The research should be conducted in line with the Ministry’s objectives and the ethical standards set out in the Government Social Research code. Research should be analytically robust, and ethically conducted.

## All contractible deliverables must be of publishable quality under the Customer’s name. The Customer will work with the Supplier to analysis and interpret the data to form the final deliverables.

# PRICE

## Prices are to be submitted via the e-Sourcing Suite Attachment 4 – Price Schedule excluding VAT and including all other expenses relating to Contract delivery.

## The Total Contract Value (excluding VAT) is £50,000.

## Potential Bidders are asked to submit their most competitive Day rates which will be evaluated and used to price for the ad-hoc requirements. Day rates submitted will remain firm throughout the life of the Contract. The Customer cannot guarantee any spend amount on this Call-off element.

## Potential Bidders are asked to submit their most competitive capped costs to deliver the requirement within the budget.

# STAFF AND CUSTOMER SERVICE

## The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service.

## The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard.

## The Supplier shall ensure that staff understand the Customer’s vision and objectives and will provide excellent customer service to the Customer throughout the duration of the Contract.

# SERVICE LEVELS AND PERFORMANCE

## The Customer will measure the quality of the Supplier’s delivery by:

| ## KPI/SLA | ## Service Area | ## KPI/SLA description | ## Target |
| --- | --- | --- | --- |
| ## 1 | ## Delivery timescales | ## The Supplier shall adhere to the timescales/project plans unless otherwise agreed by the Customer. | ## 100% |
| ## 2 | ## Service provision | ## The Supplier shall ensure that the services provided meet the requirements in section 7. | ## 100% |
| ## 3 | ## Quality | ## The Supplier shall use suitable quality assurance processes throughout the contract as agreed with the Customer at the start of the contract. | ## 100% |
| ## 4 | ## Adhering to guidance | ## The Supplier shall adhere to the Customer’s branding, data security and other guidance, (to be provided to the successful Supplier upon appointment). | ## 100% |
| ## 5 | ## Reporting | ### The Supplier shall provide spend data and other reporting in a format agreed by the Customer. | ## Within 5 working days of request. |
| ## 6 | ## Meetings | ### The Supplier shall meet remotely with the Customer within 5 working days of a request and be available via telephone/email. Suitable materials and/or presentations shall be prepared for the meetings. Meeting notes shall be provided no later than 3 working days after the meeting. | ## 95% |

## Each of the deliverables will need to pass a Project Steering Group convened by the Ministry before moving onto the next stage. Poor performance against these SLAs will be assessed and managed by the steering group who will assess whether the products meet the required standard/quality as set out in the statement of requirement.

## If any of the deliverables fail to meet the agreed quality service levels and performance we reserve the right to consider early termination of the contract.

# SECURITY AND CONFIDENTIALITY REQUIREMENTS

## The research will take place offsite. In the event that social distancing measures are relaxed it should be noted that the Supplier may need to attend meetings at REDACTED.

## The Customer will remain as data controller and will own the Intellectual Property and Publishing Rights for the research outputs. At the end of the project, and when requested throughout its duration, any additional project materials must be shared with the Customer. Project materials might include, for example, anonymised transcripts or data.

# payment AND INVOICING

## The payment method for this Call-Off Contract is by bank transfer. The Authority will pay the Supplier within 30 days of receipt of a valid invoice

## Payment can only be made following satisfactory delivery of pre-agreed certified products and deliverables. These products and deliverables shall be agreed between the Customer and the Supplier as part of contract discussions once a preferred supplier has been appointed.

## Before payment can be considered, each invoice must include a detailed elemental breakdown of work completed and the associated costs.

## Invoices should be submitted to:

CP2P Team, MHCLG, 4th Floor, 
High Trees, Hillfield Road, 
Hemel Hempstead, HP2 4XN.

## Email address: REDACTED

## All invoices must be specific to charges agreed at the end of each month/milestone. Other information such as: Purchase Order number, project reference, period of work, and number of days worked, invoiced amount, VAT shall also be included on each invoice.

# CONTRACT MANAGEMENT

## The Supplier and Customer will convene at least fortnightly (or as required) to assess progress. The Supplier will be expected to attend the meetings at each agreed review point, or if there are particular issues that need to be addressed.

## At each review point, the Customer will assess whether outputs meet satisfactory standards before the work can proceed to the next stage. The dates of these meetings will be set and agreed between the Customer and the Supplier once in post.

## There will be a final review once all outputs have been completed, at which the Customer will assess overall progress including the final report.

## Attendance at meetings with the Customer shall be at the Supplier’s own expense. They may be conducted over phone/teleconference if preferred.

# LOCATION

## The location of the Services will be carried out at case study locations as well as the Supplier’s address.

Annex B

Supplier Proposal

REDACTED

  - Contract Terms