Order Schedule 20 (Order Specification)

- PURPOSE

  - As announced by the Chancellor of the Exchequer in his Autumn Statement on Wednesday 22 November, HM Government is exploring options for a retail offer of NatWest Group shares as part of plans to return its remaining stake to private ownership. UK Government Investments, operating on behalf of HM Treasury (the Buyer), wishes the Service Provider to plan, design and deliver market research into public attitudes and interest around this proposal to assist the Buyer in planning for the sale process.

# BACKGROUND TO THE Buyer

  - HM Treasury (HMT) is a ministerial department, supported by 16 agencies and public bodies.

  - HMT is the government’s economic and finance ministry, maintaining control over public spending, setting the direction of the UK’s economic policy and working to achieve strong and sustainable economic growth.

  - HMT is responsible for:

    - Public spending: including departmental spending, public sector pay and pensions, annually managed expenditure (AME) and welfare policy, and capital investment.

    - Financial services policy: including banking and financial services regulation, financial stability, and ensuring competitiveness in the City.

    - Strategic oversight of the UK tax system: including direct, indirect, business, property, personal and corporation tax.

    - The delivery of infrastructure projects across the public sector and facilitating private sector investment into UK infrastructure.

    - Ensuring the economy is growing sustainably.

  - Since the 2008 financial crisis HMT has been a shareholder of NatWest Group. HMT’s NatWest shareholding is managed by UK Government Investments (UKGI), which is an Arms’ Length Body of HMT.  UKGI is leading the work to explore the retail offer, including managing this research contract (where this tender references Buyer, please note that UKGI is acting on behalf of the Buyer).

  - The purpose of this ITT is to establish a contract with a Service Provider that specialises in the provision of Market Research Services. The Buyer wishes the Service Provider to plan, design and deliver market research, including undertaking a public-attitudes survey towards Government privatisations by existing and new potential retail investors in relation to HMG’s shareholdings in NatWest, individual interest in such a scheme, and brand recognition and perception of NatWest and its potential implication on the first two areas.

# Background to requirement/OVERVIEW of requirement

  - The work required is detailed, specialist and complex. The services will include the planning, design, preparation and undertaking of the research, in an ethical and compliant manner, as well as the interpretation and presentation of the results to the Buyer.

  - We expect the initial work to be done within 6 months. However, to retain optionality the contract will have options to extend for up to a further 24 months.

  - The engagement of a Market Research Service Provider is required to provide services primarily to plan, design and conduct qualitative and quantitative research in line with the Buyer’s objectives as set out in paragraph 1.1 above and in line with its mandate and shall include, but not be limited to:

    - lead the strategy, planning and preparations for conducting quantitative and qualitative research into:

      - Attitudes towards shares, a NWG share offering and incentives

      - Influencing factors of the decision to invest, likelihood of investing, size of investment (expressed in £ per person) and preferred ways to apply for shares in the offer

      - Demand indications (estimation of total £bn demand, based on £ per person and scaled up to the general population), including indications of whether this demand is new or additional to existing interest in share investments

    - Lead the design of the questionnaire, and any materials required for the focus group discussions as part of the qualitative research;

    - Conduct and, where appropriate, manage the various market research streams during implementation;

    - Conduct an analysis and interpretation of the results from the research;

    - Present the findings of the research in the appropriate format with the agreement of the Buyer.

### Agency matrix

    - We are procuring agencies to provide communications planning/PR, creative services, public relations media planning and research (this tender) and evaluation services. Media buying will be handled under the existing Government contract.

    - It is essential that all firms appointed work closely together and with all relevant government departments and agencies to ensure an integrated development and delivery programme.

# scope of requirement

  - Market Research Service Provider will be expected to provide a dedicated team with sufficient knowledge, experience and seniority to deliver the detailed preparation, implementation and analysis in the following phases.

  - Preparation Phase

    - Work closely with the Buyer to plan and design the most effective market research programme for achieving the Buyer’s objectives;

    - Develop the questionnaires and other relevant materials for quantitative and qualitative research work streams to meet the Buyer’s objectives;

    - Draw up detailed timing and implementation process plans.

  - Implementation Phase

    - Oversee, project manage and undertake the implementation logistics of carrying out the quantitative and qualitative research, such that it is representative of the general UK adult population, and coordinate all the activities between work streams;

    - Quality check the results throughout the market research process to ensure the market research has been carried out as agreed with the Buyer to the required standards as detailed by the MRS code of conduct and other applicable industry guidance;

    - Collect the results of the market research.

  - Analysis phase

    - Undertake an analysis and interpretation of the research results;

    - Present the results of the analysis both verbally and through a written report to the Buyer and any other audience as requested;

    - Any other tasks as agreed with the Buyer to successfully implement the required market research.

  - Milestones and Authority commitments

    - The Service Provider will commence the implementation stage only once the Buyer) has approved the work completed in the preparation phase.

    - The Buyer will provide timing and deadline guidance within reason at each stage of the project.

    - The Buyer will have a designated contract manager to engage with a counterpart from the Service Provider to monitor progress and address any issues throughout the duration of the Contract via bi-weekly meetings, or as deemed appropriate and agreed.

# The requirement

## Specific Services and Deliverables Required:

  - The Provider will be required to undertake the following Services and produce the following deliverables:

## Deliverables:

  - A quantitative survey about public attitudes, such that it is representative of the general UK adult population, towards an HMG privatisation of NatWest through a sale to retail investors;

  - Survey to be conducted nationwide and include a diverse pool of respondents reflecting the nation;

  - Survey to be conducted online and/or via telephone;

  - Qualitative market research through 6 - 8 focus groups to ascertain more detail on public attitudes as set out above;

  - Provide the analysis and interpretation of all the results of the research to best meet the objectives of the Buyer;

  - Present the results of the analysis in the format agreed with the Buyer;

  - Any subsequent surveys or focus groups as requested by the Buyer; and

  - Any additional research or clarification requirements as reasonably requested by the Buyer (after consulting with the Provider).

Deliverables will include:

  - The final deliverable will be a written report presenting the results of the analysis and interpretation of the results from all of the market research.  The format of the report is at the discretion of the Service Provider. This may also include some engagement with the Buyer which reserves the right to challenge conclusions, interpretations and ask for further information to be provided;

  - In addition to the above the Buyer may also require interim outputs and reports. All reports or presentations produced for the Buyer may be subject to public scrutiny;

  - The Buyer may require hard and soft copies of work products;

  - Service provider must be available for in-person meetings as required by the Buyer; and updates by telephone/Teams as required by the Buyer;

  - The results of research must be delivered within deadlines;

  - The provider to deliver any additional requirements as reasonably requested by the Buyer (after consulting with the Provider).

# key milestones and Deliverables

  - The following Contract milestones/deliverables shall apply:

| ### Milestone/Deliverable | ### Description | ### Timeframe or Delivery Date |
| --- | --- | --- |
| ### Preparation Phase |  |  |
|  | ### Kick-off meeting | ### By w/c 8th January 2024 |
|  | ### Research strategy |  |
|  | ### Questionnaires, other relevant research materials and detailed timing and implementation process plans. | ### By 16th January 2024 |
|  | ### Detailed timing and implementation process plans | ### By 16th January 2024 |
| ### Implementation Phase |  |  |
|  | ### Launch research | ### By 17th January 2024 |
|  | ### Collect final results of research | ### By 31st January 2024 |
| ### Analysis Phase |  |  |
|  | ### Presentation and draft analysis report | ### By 2nd February 2024 |
|  | ### Presentation and final analysis report | ### By 9th February 2024 |

# MANAGEMENT INFORMATION/reporting

  - The Supplier shall provide regular quantitative and qualitative updates on the progress of research throughout the implementation phase.

# volumes

  - Based on past experience in a similar project, we expect:

    - At least one quantitative survey on the order of 100 possible questions, to around 2,000 adults

    - Qualitative research via 6-8 focus groups

# continuous improvement

  - The Supplier will be expected to continually improve the way in which the required Services are to be delivered throughout the Contract duration.

  - The Supplier should present new ways of working to the Buyer during monthly Contract review meetings.

  - Changes to the way in which the Services are to be delivered must be brought to the Buyer’s attention and agreed prior to any changes being implemented.

# PRICE

  - Prices are to be submitted via the e-Sourcing Suite Attachment 4 – Price Schedule excluding VAT and including all other expenses relating to Contract delivery.

# STAFF AND BUYER SERVICE

  - The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service.

  - The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard.

  - The Supplier shall ensure that staff understand the Buyer’s vision and objectives and will provide excellent Buyer service to the Buyer throughout the duration of the Contract.

# service levels and performance

  - The Buyer will measure the quality of the Supplier’s delivery by:

| ## KPI/SLA | ## Service Area | ## KPI/SLA description | ## Target |
| --- | --- | --- | --- |
| ## 1 | ## Service delivery | ## All deliverables to be delivered to the Buyer by the agreed dates | ## 100% |

# Security and CONFIDENTIALITY requirements

  - Suppliers must be able to demonstrate compliance with the Government Security Policy Framework and that they have appropriate IT, physical, personnel and procedural security measures in place to prevent any unauthorised access to, or leakage of, data collected as part of this contract, and to prevent it being shared with any unauthorised third parties. Such security measures should comply with the requirements of the ISO27001 standard as a minimum and the Buyer would wish to see evidence of that compliance, e.g., in the form of current ISO 27001 certification.

  - Any IT systems used by Suppliers to meet the Buyer’s requirement must comply with National Cyber Security Centre (NCSC)’s 10 Steps to Cyber Security and with the NCSC’s Cloud Security Principles. The Supplier should also hold NCSC’s Cyber Essentials certification and provide the Buyer with evidence of this.

  - Suppliers are expected to demonstrate they have appropriate physical security measures in place in any premises used to store/process the Buyer’s data. As above such physical security measures should comply with the requirements of ISO27001 as a minimum. Any data centres used by the Supplier to meet the Buyer’s requirement must hold current ISO27001 certification and be UK based.

  - Buyer data should be handled by Supplier staff and subcontractors on a need-to-know basis.

  - Suppliers shall ensure that any suspected or actual security breaches related to Buyer’s data/information are reported to the Buyer immediately. Where any actual security breaches have been identified, Suppliers shall, as soon as reasonably practicable, provide to the Buyer a report setting out the details of the security breach, including an impact assessment, a root cause analysis and of the steps taken to address the breach.

  - Full compliance with the Data Protection Act (DPA) 2018 and the General Data Protection Regulation (GDPR) is essential.

# payment AND INVOICING

  - Payment can only be made following satisfactory delivery of pre-agreed certified products and deliverables.

  - Before payment can be considered, each invoice must include a detailed elemental breakdown of work completed and the associated costs.

  - Invoices should be submitted to: REDACTED TEXT under FOIA Section 40, Personal Information

  - An invoicing schedule will be agreed with the successful tenderer.

# CONTRACT MANAGEMENT

  - Attendance at Contract Review meetings shall be at the Supplier’s own expense.

# Location

  - The location of the Services will be carried out at the Supplier’s premises except as agreed with the Buyer.