Joint Schedule 2 (Variation Form)

This form is to be used in order to change a contract in accordance with Clause 24 (Changing the Contract)

| Contract Details |  |  |
| --- | --- | --- |
| This variation is between: | Cabinet Office (“the Buyer") And Pick Everard ("the Supplier") |  |
| Contract name: | Provision of PFI Contract Expiration Surveys (“the Contract”) |  |
| Contract reference number: | CCIT22A24 |  |
| Details of Proposed Variation |  |  |
| Variation initiated by: | Buyer |  |
| Variation number: | 1 |  |
| Date variation is raised: | 03rd March 2024 |  |
| Proposed variation | To enter into the first Extension Term of one (1) Year as provided for within the Call-Off Contract with reference CCIT22A24 |  |
| Reason for the variation: | This is the first Extension Term of one (1) year as provided for within the Call-Off Contract. The IPA have a requirement for asset condition surveys to be provided during the contract term outlined below, which this Call-Off Contract variation provides for the continuation of. |  |
| An Impact Assessment shall be provided within: | 30 Days |  |
| Impact of Variation |  |  |
| Likely impact of the proposed variation: | Not Applicable |  |
| Outcome of Variation |  |  |
| Contract variation: | This Contract detailed above is varied as follows: - The first Extension Term will be entered into resulting in the Call-Off Contract being extended from 03rd March 2024 until the 2nd March 2025. |  |
| Financial variation: | Original Contract Value: | £ 250,000.00 |
|  | Additional cost due to variation: | £ 250,000.00 |
|  | New Contract value: | £ 500,000.00 |

- This Variation must be agreed and signed by both Parties to the Contract and shall only be effective from the date it is signed by Buyer

- Words and expressions in this Variation shall have the meanings given to them in the Contract.

- The Contract, including any previous Variations, shall remain effective and unaltered except as amended by this Variation.  Signed by an authorised signatory for and on behalf of the Buyer

| Signature | REDACTED TEXT under FOIA Section 40, Personal Information. |
| --- | --- |
| Date | 12/03/2024 |
| Name (in Capitals) | REDACTED TEXT under FOIA Section 40, Personal Information. |
| Address | REDACTED TEXT under FOIA Section 40, Personal Information. |

Signed by an authorised signatory to sign for and on behalf of the Supplier

| Signature | REDACTED TEXT under FOIA Section 40, Personal Information. |
| --- | --- |
| Date | 12/03/2024 |
| Name (in Capitals) | REDACTED TEXT under FOIA Section 40, Personal Information. |
| Address | REDACTED TEXT under FOIA Section 40, Personal Information. |