## Sheet1
CLARIFICATION LOG
Tender: | Archaeologicial Survey
Tender Reference:
Clarification deadline:
Published Date: | 2023-02-21
Version number: | 3
Number | Clarification | Response | Reply date
1 | Are the dates for completing the works strictly to be complied with? | The dates for undertaking the work are preferred timescale there may be some flexibility offered around the timeframe to complete the assignment. | 2023-02-13
| Is it a fair assumption that the list of the features/structures to be included in the survey is broadly the same as those listed on pp. 48-50 of the Pendennis Headland publication, to which the ITT refers? This amounts to c. 115 structures. | This is a fair assumption, however several of the assets listed are outside the ownership of FTC, eg. Pendennis Castle itself, so the list should be cross referenced against the map appendixed to the brief accompanying the ITT | 2023-02-14
| Is the intention that the condition survey gazetteer be set out broadly as it is for each feature/structure in more detail in the inventory within Appendix 1 of the same publication? In particular, is this the level of detail that is expected for each structure? | The key document here is Richard Linzey’s “Fortress Falmouth,” (2000) Linzey divides the headland into zones and it may be appropriate to adopt this approach. The zones which will form the study area are: Zone S - The West Glacis; Zone T - the Pendennis Isthmus; Zone U - the East Glacis; Zone V - Pendennis Point. The assets within each of the areas have been assigned a unique reference number, these should be used going forwards, I attach a photo of zone V. to demonstrate this. The background is already within this document and the focus of the survey needs to be on the condition of each asset, recommendations/opportunities for enhancing/preserving/maintenance & protection of the condition of the asset going forward. | 2023-02-14
| Though the budget is stated on the central contracts portal as ‘£1 to £10k’, there is no specific budget mentioned in the brief. Can I ask if £10k is the absolute ceiling, or whether the FTC are open to receiving tenders which propose fees beyond that? Given the extent of the structures to be surveyed and the additional information to be provided, such as the review of mapping, management plans and recommendations, it is unlikely that we could propose that sum and still provide the level of quality and detail which the project requires in order to be a useful tool for the CMP. | The £1-£10k is an indicative guide and any offers over this amount will be evaluated and still be considered. | 2023-02-14
| Is a separate document with questions that we fill out to demonstrate our competency against the criteria, are we meant to submit a separate document? | On this occasion we have not stipulated or included a specific response document with this quotation opportunity. Structuring a response against the headings as listed below would be appropriate way to demonstrate your necessary skills and experience and how you can apply to this contract. This can be in the form of a letter or supporting proposal and appendices, including links to your website / case studies etc. | 21.02.2023
In the event of queries please contact: