## Services
Schedule 2 - Specification
2020-04-01
Stage 4 Technical Design Audit Services
Holocaust Memorial and Learning Centre – Cost Services Reference CPD 004 120 224
Ref | Scope of Services
1 | General Services
1.1 | Carry out a technical design audit of the RIBA Stage 4 cost plan
1.2 | The audit shall highlight any missing information normally provided in a Cost Plan at RIBA Stage 4 Technical Design
1.3 | Request and attend meetings in order to complete the Stage 4 design audit review.
1.4 | Liaise through usual communication media (phone, e-mail, on-line meetings as necessary) with the Client, Project Manager, Lead Designer, Consultant Engineers and Cost Manager as necessary to complete the Stage 4 design audit review.
1.5 | Attend one interim two hour meeting at mid-point of study to review progress with client team
2 | RIBA Stage 4 - Cost Plan Review
2.1 | The Stage 4 cost plan audit shall cover all aspects of the design (including architectural (Learning Centre and Memorial), landscape architect and engineering services). {Note: the review shall not include review of the UKHM Learning Centre Content}
2.2 | Provide comment(s) on the adequacy of the cost plan for the requisite work stage
2.3 | Check area schedules and provide comments on any discrepancies to the information provided
2.4 | Suggest opportunities for cost savings / value engineering / efficiency in design
3 | Presentation of Findings
3.1 | Collate all review and findings into a full Stage 4 Cost Plan Audit Report and issue to the Client. This will identify, amongst other issues, areas of cost risk, lack of completeness, in cost estimating process, market testing, identifying potential risk issues as Red, Amber, Green in terms of risk to delivery cost and programme.
3.2 | Allow for 2 meetings at conclusion of study, one to consult design team on findings and one to present findings to client team.