## Overall Contractor Performance
OVERALL CONTRACTOR PERFORMANCE
Contractor
Contract Number
Month/Year
KPI No | PI Weighting | KPI Score | Weighted Score | Key:-
1 | 10 | 0% | 0 |  | Overall Contractor Performance greater than 85%
2 | 8 | 0% | 0
3 | 7 | 0% | 0 |  | Overall Contractor Performance between 75% and 85%
Overall Contractor Performance less than 75%
Overall Contractor Performance |  |  | #DIV/0!

## KPI 1
KPI 1 | Achieve the Required Delivery Date(s) (RDD) in respect of Planned Upkeep, Repair and Modification of Boats | [8 empty] | On or before agreed timescale
Delivered after the agreed RDD but within 105% of the duration of the task
Delivered after the agreed RDD but out with 105% of the duration of the task
No. of Occurrences |  | Multiplier | Score | RAG Status
Green | 0 | 1 | 0
Amber | 0 | 0.9375 | 0
Red | 0 | 0.9375 | 0
Total Occurrences | 0 |  | 0 | 0%
Boat No | Task Form No | Task Start Date | Required Delivery Date | Planned Workpackage length in working days | Planned Workpackage inc 5% | Actual Delivery Date | Total No of Days | Variance |  | RAG Status |  | Comments
[8 empty] | WP < 100 | WP > 100 | WP < 100 | WP > 100
Key:-
Overall Contractor Performance greater than 85%
Overall Contractor Performance between 75% and 85%
Overall Contractor Performance less than 75%
Formulas:
RAG Status = IF(([Multiplier])=(""),(""),NETWORKDAYS([Multiplier],[Score],'Network Days'!C4:C35)-1)
RAG Status = IF(([Multiplier])=(""),(""),NETWORKDAYS([Multiplier],[Score],'Network Days'!$C4:C50)-1)
Total No of Days = IF(([Actual Delivery Date])=(""),(""),NETWORKDAYS([Multiplier],[Actual Delivery Date],'Network Days'!$C4:C50)-1)
Variance = IF([RAG Status]="",(""),(IF(([RAG Status]<=100),(NETWORKDAYS([Score],[Actual Delivery Date],'Network Days'!$D4:D32)-1),"")))

## KPI 2
KPI 2 | Quality |  | No Quality Deficiency Reported i.e. no QDR's issued
Minor Quality Deficiency Reported
Major Quality Deficiency Reported
No. of Occurrences |  | Multiplier | Score | RAG Status
Green | 0 | 1 | 0
Amber | 0 | 0.9375 | 0
Red | 0 | 0.9375 | 0
Total Occurrences | 0 |  | 0 | 0%
Task Form No | Boat No | Quality Deficiency Report (No Deficiency / Minor / Major) | Comments | RAG Status
Key:-
Overall Contractor Performance greater than 85%
Overall Contractor Performance between 75% and 85%
Overall Contractor Performance less than 75%

## KPI 3
KPI 3 | Supply of Spares - Timely supply of spares |  |  |  | On or before agreed timescale
Up to 5 (five) working days late
More than 5 (five) working days late
No. of Occurrences |  | Multiplier | Score | RAG Status
Green | 0 | 1 | 0
Amber | 0 | 0.9375 | 0
Red | 0 | 0.9375 | 0
Total Occurrences | 0 |  | 0 | 0%
Task Form No | Required Delivery Date | Actual Delivery Date | Variance | RAG Status | Comments
Key:-
Overall Contractor Performance greater than 85%
Overall Contractor Performance between 75% and 85%
Overall Contractor Performance less than 75%
Formulas:
Score = IF([Required Delivery Date]=(""),(""),NETWORKDAYS([Required Delivery Date],[Multiplier],'Network Days'!$C4:C50)-1)

## Network Days
Network Days
2016-01-01
2016-03-25
2016-03-28
2016-05-02
2016-05-30
2016-08-29
2016-12-25
2016-12-26
2017-01-01
2017-04-14
2017-04-17
2017-05-01
2017-05-29
2017-08-28
2017-12-25
2018-12-26
2018-01-01
2018-03-30
2018-04-02
2018-05-07
2018-05-28
2018-08-27
2018-12-25
2018-12-26
2020-01-01
2020-04-19
2020-04-22
2020-05-06
2020-05-27
2020-08-26
2020-12-25
2020-12-26

## Weightings
Scenarios
No of Greens | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
No of Ambers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No of Reds | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total no of tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Green weighting | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Amber weighting | 85% | 78% | 72.4% | 67.92% | 64.34% | 61.47% | 59.18% | 57.34% | 55.87% | 54.7% | 53.76% | 53.01% | 52.41% | 51.92% | 51.54% | 51.23% | 50.99%
Red weighting | 75% | 60% | 48% | 38.4% | 30.72% | 24.58% | 19.66% | 15.73% | 12.58% | 10.07% | 8.053% | 6.442% | 5.154% | 4.123% | 3.299% | 2.639% | 2.111%
Weighted Average | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## Scenarios
Scenarios
No of Greens | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 3 | 20 | 5 | 5 | 20 | 10
No of Ambers | 1 | 1 | 0 | 2 | 3 | 4 | 5 | 6 | 7 | 7 | 0 | 4 | 0 | 2 | 0 | 1 | 1
No of Reds | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 1 | 0 | 0
Total no of tasks | 3 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 11 | 8 | 21 | 7 | 6 | 21 | 11
Green weighting | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Amber weighting | 72.4% | 78% | 85% | 78% | 72.4% | 67.92% | 64.34% | 61.47% | 59.18% | 55.87% | 53.76% | 57.34% | 50.4% | 59.18% | 61.47% | 50.4% | 53.76%
Red weighting | 48% | 60% | 75% | 60% | 48% | 38.4% | 30.72% | 24.58% | 19.66% | 12.58% | 8.053% | 15.73% | 0.8647% | 19.66% | 24.58% | 0.8647% | 8.053%
Weighted Average | 73.47% | 89% | 75% | 78% | 72.4% | 67.92% | 64.34% | 61.47% | 59.18% | 55.97% | 83.28% | 68.14% | 95.28% | 88.34% | 87.43% | 97.64% | 95.8%