## Sheet1
HFC Building Survey
Number | Date received | Clarification | Response
1 | 2017-06-06 | Does 3D scan need to be completed at all areas inside red line, at all levels? | No - Areas which are not included in survey scope do not need to be scanned or recorded in any way (Areas shown on SK(0)120-121 drawings in purple)
2 | 2017-06-06 | Elevations for walls AA-BB; Should we show full elevations for these? | Yes these should be complete elevations.
3 | 2017-06-06 | External sections C-C, D-D, E-E, F-F, H-H, J-J, K-K, L-L; To confirm number of internal sections required | Sections J-J, K-K, L-L, M-M are also required. However these are labelled as 'Internal Elevations' in the tender specification document. This is because there is an emphasis in particular on these sections to show detailed elevational information in the Boscawen Foyer area.
4 | 2017-06-06 | Access to elevations East and West | Page 14 states "East and West Elevations as far as can be accessed from the passageways adjoining the building as shown on SK(0)131..". HFC will set up access with neighbours once survey dates are confirmed.
5 | 2017-06-06 | Page 14 requests Boscawen Street and Back Quay Road features are included; what is the extent of this requirement i.e. 25m past the building in either direction. A drawing to identify the area required would help. | Page 15 states that elevations should be taken 5m to either side of the building (Boscawen street and Back Quay).
6 | 2017-06-06 | Page 15 contains a line which states “external outline levels of building façade in plan” unfortunately we are uncertain how to interpret this requirement and would appreciate it being clarified in any way? | All that will be required is the outer line of the footprint of the adjacent buildings (5m either side of site). Pavement levels should be shown at base of building. Also, in plan where an adjoining building sets back, the line of the setback is to be shown on the plan (all levels)
7 | 2017-06-06 | Page 15; please clarify wat is meant by “easy” lifting of carpet? | Where the carpet can be lifted without tools, the underneath should be inspected and the carpet put back in place.
8 | 2017-06-06 | Page 16; please clarify what is meant by “show internal elevations of all rooms cut through in section, including windows, doors etc.” I.e. is this detail that is on the section line only, or other (all) elevations within the room? | Only the elevational detail of the wall which the section is facing. Please see example SK(0)135 which I will send over with the rest of this response. This example drawing shows the sort of level of elevation detail we would be expecting.
9 | 2017-06-06 | External services; does the requirement to show underground service routes require the use of sonde and tracing equipment or simply interpretation of the services providers maps in relation to surface identified covers, invert levels etc? I.e. is ground penetrating radar, radio detection or CCTV surveys required to identify and/or locate sub surface utilities? | Subslab services routes are being surveyed by others using sonde and tracing technology. However, as set out in the tender, the visible services routes positions and levels are required on the dimensional survey.
10 | 2017-06-06 | Page 17; please can the schedule of building availability be provided for reference during the preparation of our tender. | Issued with this document.
11 | 2017-06-06 | Scale; the level of detail it is possible to include on hard copies of the drawings will be dependent on the scale of the reproductions. Can the scale for the production of sections, elevations and floor plans be determined to ensure that all tenderers are pricing on the same basis; or should the scale of the drawings included at the appendix be assumed? | The hard copy's should not be used as a measure of detail required - We will mostly be working with these files electronically. Level of detail required is set out in the documentation. As a rough guide you could assume working on A1 hardcopys at 1:100. We will be working with A3 and A1 drawings, ranging from 1:200 to 1:5. Where sensitive heritage areas are concerned, a higher level of detail will be required.
12 | 2017-06-06 | Are all of the tender queries and responses made publicly available i.e. all question and answers available to all tendering parties? | Yes
13 | 2017-06-06 | Are there any areas classed as a confined space within the building that will need to be surveyed? | No. (All contractors must follow appropriate health and safety procedures).
14 | 2017-06-06 | Who is responsible for arranging access to areas of the facility that are let or managed by other persons i.e. flourish; wester power distribution sub-station, city hall council offices etc; is there a single point of contact? | HFC - This will be arranged once the surveyor has been appointed.
15 | 2017-06-06 | To what extent will the premises be vacated i.e. obstructions to the survey removed by the occupants prior to scanning? | The premises will not be vacated. Note, the level of existing use varies.
16 | 2017-06-06 | Is the closing date for enquiries the 8th or 6th of June version V1.3 identified both dates; please clarify? | 6th June.
17 | 2017-06-06 | Can the dates between contract award and commencement be extended to include a reasonable mobilisation period? 3 to 4 weeks would be practicable as to be notified of contract award on the 23rd June and to commence survey work the following week would mean ensuring that no other commitments are scheduled which without a commitment to contract cannot be justified. | Please state in your tender return the mobilisation period required.
18 | 2017-06-06 | If the contract award date is delayed will the completion date be altered commensurately? | Yes.
19 | 2017-06-06 | It is necessary for us to resurvey areas shown as excluded zones in plan, in order to complete sections. | Where a section is shown cutting through an area which is excluded from the survey (shaded purple in SK(0)120-121), this area of the section can be omitted.
20 | 2017-06-06 | whether the reflected ceiling plans are needed for the whole building or just the new, additional ‘white’ areas on the plans? | RCP's are only required in the 'white' areas included in the survey. The exception to this would be the roof in the main auditorium space, above the lighting gallery. We would like to capture the trusses in particular. We have created an additional sketches to help illustrate this - Please see SK(0)137 for illustration. Note that SK(0)120 has also been updated (Rev B), and now includes the lighting gallery walkways.
21 | 2017-06-06 | Are we to enhance all of the existing floor plans, sections and elevations with our ‘new’ data, which will of course mean that we will need access to same. | You will not be required to incorporate the old data in any way with your 'new' data. The 'old' data is to help explain the scope of the survey only.
22 | 2017-06-06 | Do we need to work to OS grid and datum or if there is a local grid and datum already in place, which we would need the details for? | Yes - Work to OS grid and datum
23 | 2017-06-06 | Our understanding from the specification document is that all areas shown in purple are not to be included in the survey or shown on the floor plans and reflected ceiling plans. But are these required as part of the sections CC and HH? | Sections can simply blank out any areas which are in 'purple' areas which are excluded from scope. The exception to this is in Sections C-C and D-D. In these sections the roof truss and roof structure should be included. (Note - this is because the main internal auditorium seating is to be demolished, but the roof is to be retained. Bear this in mind to help identify the boundarys to excluded zones)
24 | 2017-06-06 | Please confirm that Elevations & Sections required are only as listed below: 4 No Elevations externally (AA, BB,CC,DD) 2 No Internal Elevations JJ & MM 2 No Sections (without elevating any background detail) CC &HH. | Sectional/Elevational Drawings Required: 4x External Elevations (AA, BB, West, East) 6x Sections (CC, DD, EE, FF, GG, HH) 4x Internal Elevations (JJ, KK, LL, MM)[These can be thought of as sections with additional elevational detail applied, one for each wall in the Boscawen Foyer]
25 | 2017-06-06 | Would you consider the possibility of capturing coloured scans only in areas of architectural interest such as the entrance lobbies as this would reduce fees and time on site. We would propose to only capture intensity levels (not RGB) in all areas of secondary use such as facilities, storage, WC’s etc. | Yes, this is the intention. We only require coloured scans of JJ, KK, LL and MM, as this area is historically important. We should essentially end up with coloured scans of each of the main Boscawen foyer walls.
26 | 2017-06-06 | Given that it is a potential BIM project do you have special Cad Standard requirements i.e. layers, file naming, fonts etc. of BFF architects? Otherwise we will use XXX standards. | This will not be a BIM project. Clarification - Project open day minutes stating that this is a BIM project are incorrect. BFF Layers, class, file naming information should be adhered to as outlined in tender information. Additional copy of BFF standard classes attached. This can be discussed fully once surveyor is appointed.
27 | 2017-06-06 | Would a structural grid be required on the Floor plans? | This is not necessary. However we will liase with the appointed surveyor to ensure our assumptions on the existing steel grid do align with observed survey.
28 | 2017-06-06 | Please note we have not allowed for removal of ceiling tiles. In order to capture the structural soffit details, key ceiling tiles will need to be removed prior to survey, else these levels will not be provided. | Following appointment we will liase with chosen contractor on removal of tiles.
29 | 2017-06-06 | Building will be surveyed as found, inaccessible areas will be indicated on the drawings. Client responsible for ensuring all rooms are clear of obstructions, to allow all details to be captured. | Noted
30 | 2017-06-06 | Do you require invert levels to internal and external manholes? Would the survey extents as shown on the attached image be sufficient? | Yes - this requirement is outlined in the survey requirements document, page 16.
31 | 2017-06-06 | It would be our preference to laser scan all external and internal areas, including the roof, as we believe this will achieve the greatest accuracy. | Noted
32 | 2017-06-06 | Additionally are we to receive answers to the questions raised at the site meeting soon as I intend to start putting our proposal together tomorrow | See minutes of site meeting
CRITICAL - TO CLARIFY THE AMOUNT OF SECTIONS & ELEVATIONS REQUIRED, PLEASE NOTE:
|  |  | Elevations: A-A, B-B, West, East, East part 2 | 5 no.
|  |  | Sections: C-C, D-D, E-E, F-F, G-G, H-H | 6 no.
|  |  | Internal Elevations: J-J, K-K, L-L, M-M | 4 no.