## Sheet1
CLARIFICATION LOG
Tender: | Professional Services Principal Design Team: (Roof Top Garden) Technical studies, design and feasibility work
Tender Reference: | 001 (05/2023)
Published Date: | 17.06.2023
Version number: | 0.7
Number | Clarification | Response | Reply date
1 | TO NOTE - Vol 2 -Supplier Response Rooftop Garden - Final replaced by Vol 2 -Supplier Response Rooftop Garden - Final_v0.2 | Please look to respond to Vol 2 -Supplier Response Rooftop Garden - Final_v0.2 | 26.05.2023
2 | Upon downloading the supporting documents you have posted online, we notice that it is missing the Contract and/or Terms and Conditions. Is this something you can send over to us? | No separate Terms and Conditions / contract is published with this tender opportunity. Instead please refer to section 2.11 – Contract / Contract Period of Volume 1 Invitation to Tender which states “Terms and Conditions - the form of contract to be the JCT Consultancy Agreement (public sector) 2016 / or RIBA concise professional services contract: architectural services and it is intended that any resultant Contract shall commence as soon after receipt of formal letter of award as may be agreed”. | 2023-06-05
3 | Please may you confirm that all surveys are to be excluded from your estimated budget of £243k? | The Council does not have a separate budget for surveys and therefore those costs should be included in the budget estimate of £243k. | 2023-06-07
4 | We have been reviewing the ITT for the St Austell Rooftop Garden project. We note that you have provided a copy of the masterplan with the project cost plan summary on page 59. Would it be possible to issue the cost breakdown for the rooftop garden element of the work, or, if this is already publicly available, please could you point us in the right direction? | The attached document "Masterplan - Provisional Working Estimate" provides indicative costs differ from the broad-brush estimates in the masterplan as the Partnership’s consultants who worked on the Masterplan were asked to refine their estimates to assist with this tendering process. It is a high-level provisional working estimate based solely on the initial conceptual designs. The estimates are only indicative at this stage and costs will of course depend largely on the detailed design of the proposed solution. The successful tenderer will be asked to provide updated cost estimates to support their recommended solution. No assurance is given at this stage as to the accuracy of the estimate contained in this document. | 2023-06-07
5 | Price Schedule: The Bid refers to the scope being up to Stage 4 – ‘shovel ready’. Stages 5 and 6 are also noted in the fee table. Are you looking for a price on these stages as well. If so, will the Lead Consultant be asked to undertake Contract Administration? | Within the Price Schedule, we would be looking for prices at stage 3, stage 4 and stage 6. We would expect the Lead Consultant would undertake contract administration. | 2023-06-15
6 | Surveys: The bid states that all surveys shall be commissioned by the team. It is likely that tenderers will return lists that vary in survey content. How will scoring of the returns be normalised, as returns may not be comparable. If a survey emerges that could not be foreseen or was difficult to foresee, is the lead consultant to be liable for its commission? Would it be possible for the bid to fix a core list of surveys required? | Overall, we would expect that for bidding and pricing purposes that the supplier would be able to price for surveys commensurate with the nature of this project based on experience from previous commissions, and as such would not look to set out a list of surveys. If genuine unforeseen works arise, being surveys or other matters, which would not reasonably be expected within the scope of the project then the Council would look to deal with these through change / variation procedures expressed in the contract. | 2023-06-15
7 | Consultants: The bid states that all consultants shall be commissioned under the Lead Consultant. It is likely that tenderers will return consultant lists that vary in content. How will scoring of the returns be normalised, as returns may not be comparable. If a consultant emerges that could not be foreseen or ordinarily required, is the lead consultant to be liable for its commission? Would it be possible for the bid to fix a core list of consultants required? | We recognise that bid submissions will vary around the structure of the bidding process. The Council would be seeking to appoint a single Lead Consultant - the Lead Consultant will be responsible for engaging and employing all of the remaining design team on a sub-contract basis. Please also reference back to the Method Statement in Volume 2 – Section 4 that highlights “The key components of support which the Team would bring would include, but not limited to: Urban / Town planning experience; Design and architectural experience; Structural and civil engineering; Surveying; Design and access statement; Marketing and branding; Hospitality; Environmental consultancy and landscape experience; Necessary financial acumen capabilities around assessment of options / funding streams and budget arrangements; Benchmarking, survey and analytical skills that support credible research that supports credible findings and recommendations; Commercial acumen to support robust consideration around funding and marketing considerations; Excellent communication and stakeholder engagement skills”. Again, if genuine unforeseen works arise, resulting in additional consultancy, which would not reasonably be expected within the scope of the project then the Council would look to deal with these through change / variation procedures expressed in the contract. | 2023-06-15
8 | Do we submit our bid direct to St Austell TC via this email address? as there is no other directive. Same for tender clarifications? | Please direct the bid and clarifications to: info@staustell-tc.gov.uk | 2023-06-15
9 | In Volume 2 - Section 2- Selection Questionnaire -is this for the lead consultant only to complete or all of the design team? | For the response to the Selection Questionnaire (Volume 2 – Section 2) we would ask that Selection Questionnaire is completed for the Lead Consultant, plus any other partner(s) in the bid with an anticipated input to the project of over 20%. Please note, in completion of the bid submission around quality questions (see Volume 2 – Section 4) we would be expecting to see the tenderer bring out the detail of the whole core team (irrespective of level of input anticipated) and their roles, experiences and capabilities, and what they would bring to support in the delivery of this project – but with a clear focus on the key members of the proposed team that would be engaged. | 2023-06-15
10 | With regard to the business planning, we would envisage and propose that a Market Appraisal from a Commercial Agent with expertise in retail and leisure would be included in our bid. This would inform a business case with occupier demand, rentals, yields and likely investment value of the proposed scheme. | We would recognise this as being a sensible approach around engagement of commercial agent as part of the core team, with insight around hospitality and leisure rather than pure retail but we would be guided by specialists. | 2023-06-15
11 | Business Plan/Operating model research: The bid asks for business plan / research into operating models for the ‘restaurant’. Tender returns are likely to vary. Again, how will scoring be normalised given the likely variation in operating models that the Bid may receive. | This would be in the form of a high level modelling and options around an operating model to help inform the design outcomes. Please also see question reference 10 response around inclusion of a commercial agent (with insight into hospitality and leisure) as part of the core team. | 2023-06-15
12 | The Tender information suggest that there is a set of terms and conditions that accompany the tender. We do not believe that this has been included in the current tender pack - can this information be circulated. | Please see response to question 2 above. | 2023-06-15
13 | Similar question to above - the tender instruction document suggest that the T&C's will be based on JCT Consultancy Agreement (PS) 2016 or RIBA Concise Professional Services Contract - can we gain confirmation on which one it will be and if there are any amendments proposed to the standard form? | The Council is agnostic to the terms as set out, either JCT Consultancy Agreement or RIBA Professional Services Contract. Please refer to Appendix 4 for summary of key contract conditions. | 2023-06-15
14 | There are no scope of services offered for the required disciplines - are we to offer as part of the return confirmation on our interpretation of the scopes of service or are will this be confirmed as part of the tender process? | Please see response to question 7 above. | 2023-06-15
15 | The tender information looks to suggest that the tender should include all required surveys to facilitate a RIBA 4 output? Can this be confirmed as this does not seem achievable until the project moves forward through the design stages. We would expected to allow to scope survey requirements and undertake procurment exercise in order to confirm value for money and these surveys to be then commissioned by the client. | Please see respone to question 6 above. | 2023-06-15
16 | Is there any further briefing that could be provided on what the Business Plan required as an output should consist of? | Please see responses to questions 10 and 11 above. | 2023-06-15
17 | Is there any indication of what construction contract would be utilised for the delivery of the project? | No - not currently. | 2023-06-15
18 | Is the 'project management' noted as a requirement also include for administration of the construction contract? | Yes - please also see response to question 5 above. | 2023-06-15
19 | Will the appointed design team be required to assist with funding applications and if so - can we gain indication on what support would be required? | The Council would lead on funding. The support of the appointed Lead Consultant would be in developing necessary plans, estimates, etc. in line with the overall commission. | 2023-06-15
20 | Assume that no requirement for collateral warranties from the appointed design team will be required. | It is not the intention to include collateral warranties with any appointed main contractor. | 2023-06-15
21 | The insurance requirement sets a minimum level - can this be used to set a cap on liability? | The Council would be prepared to cap liabilities in line with the minimum levels as set out in Volume 1 of the tender pack - on a claim by claim basis. | 2023-06-15
22 | Will ARB status suffice, rather than RIBA? | Yes | 2023-06-15
23 | Budget and delivery stages – confirmation available budget is for work up to RIBA stage 3, Stage 4 likely to include significant detailed (construction level) design and scope defined on basis of previous. | As noted in Volume 1, the maximum initial budget element for the Professional Services Principal Design Team (this tender) is £243k, with the expressed aim for this initial budget is to ideally progress to completion of RIBA Stage 4 (Technical Design). Please also note the clarification within Volume 1 around how bids will be evaluated in the event that bids exceeded at Stage 4 costs, specifically see Volume 1 section 3.36. | 2023-06-16
24 | Note regarding cashflow / payment schedules that we submit might be agreed as part of contract and how these will fit (or not) with payment terms and defined measurable outputs/outcomes of funding agreement (either monthly or quarterly in arrears with SPF projects). | The Town Council will bankroll the project and agree a payment schedule as part of the contract – this need not be affected by the timing of grant payments from the Shared Prosperity Fund (SPF) also known as Good Growth Fund in Cornwall. | 2023-06-16
25 | What is the process if we wish to visit the site? | A site visit can be arranged through the site agent depending on their commitments. If you provide details of preferred dates we will try to accommodate you – If you would like to arrange a visit please contact us at: info@staustell-tc.gov.uk | 2023-06-16
26 | Do you have any structural surveys done already? | No. | 2023-06-17
27 | You state in para 2.8 of the Volume 1 document that “ this initial budget is to ideally progress to completion of RIBA Stage 4”. The tender Brief states under ‘Required deliverable outcomes from consultants” that the appointed consultants will be required to test the feasibility of the creation of a roof top garden……… “. Are you after RIBA Stage 4 or some certainty that the scheme can be built so RIBA Stage 3+ could be more appropriate for this stage of works? | Ideally the Council is seeking to achieve RIBA stage 4 with the available initial budget. However, the Council does recognise that the achievability of this will be governed by how the market responds from this tender exercise. We would draw your attention to the response to question 23 (above) and also Volume 1 clause 3.36 in the event that credible and compliant bids not within that initial budget achieving RIBA stage 4 how the Council will look to evaluate bids recieved. | 2023-06-17
28 | Has there been any formal pre-app conversations with the Local Planning Authority yet? | Not yet but an application for advice has been submitted to Cornwall Council. | 2023-06-17
29 | Are there any ownership/ easement issues on the site or is it in full control of one party? | The site is in the control of one party. Linkages could be made to property owned by a second party. | 2023-06-17
30 | Are there any highway/ rights of access issues? | No none that the Council are aware of. | 2023-06-17
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: info@staustell-tc.gov.uk