## Timeline
Sustainable Tourism Accommodation Development Consultancy Support Programme Timeline
Stage | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01
Launch Design Guide | bar: 2021-07-01
Consultant(s) appointed | bar: 2021-08-01
Steering group meeting to finalise beneficiary eligibility criteria | bar: 2021-09-01
Businesses submit EOIs to join stage one of the programme | bar: 2021-09-01 to 2021-10-01
Shortlisting of EOIs | bar: 2021-10-01
Stage two advisory visits commence | bar: 2021-10-01 to 2022-01-01
Steering group meeting to consider stage one & two evaluation and shortlisting of beneficiaries for further stage three consultancy support | bar: 2022-01-01
Additional stage three consultancy support commences | bar: 2022-01-01 to 2022-04-01
Steering group meeting to consider stage three evaluation | bar: 2022-04-01
NFC Feasibility grants programme open for applications | bar: 2022-04-01 to 2022-05-01
NFC Feasibility grants award panel meet | bar: 2022-05-01
Feasibility studies being worked on | bar: 2022-05-01 to 2022-12-01
Final claim deadline for completion of feasibility grants | bar: 2022-12-01
Steering group meeting to consider end of programme evaluation. | bar: 2022-12-01
Programme close and bonus payments made | bar: 2022-12-01