## Timeline
Sustainable Tourism Accommodation Development Consultancy Support Programme Timeline
Stage | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01
Launch Design Guide
Consultant(s) appointed
Steering group meeting to finalise beneficiary eligibility criteria
Businesses submit EOIs to join stage one of the programme
Shortlisting of EOIs
Stage two advisory visits commence
Steering group meeting to consider stage one & two evaluation and shortlisting of beneficiaries for further stage three consultancy support
Additional stage three consultancy support commences
Steering group meeting to consider stage three evaluation
NFC Feasibility grants programme open for applications
NFC Feasibility grants award panel meet
Feasibility studies being worked on
Final claim deadline for completion of feasibility grants
Steering group meeting to consider end of programme evaluation.
Programme close and bonus payments made