## Cover
Pricing Schedule
for
Car Park Extension
at
Harbury Queen Elizabeth II Playing Fields, Constance Drive, Harbury, CV33 9JA
for
Harbury Parish Council
| Date: | 18th November 2023
| Project No | 6541
| Version No: | 1
Prepared for |  | Prepared by
Paul Quinney
Harbury Parish Council |  | Chartered Quantity Surveyor
Allen Construction Consultancy
Highlands House, Highlands Road
Shirley
Solihull
B90 4ND
| T: | 0121 765 2900
| E: | paul.quinney@allen.uk.com
| W: | www.allen.uk.com

## Tender Summary
Pricing Schedule
Client Name : |  | Harbury Parish Council |  |  |  |  | Tender Summary
Project Title : |  | Community EV Charging station at Harbury Queen Elizabeth II Playing Fields |  |  |  |  | 18th November 2023
Project Nr : |  | 6541 |  |  |  |  | 1
| Schedule of Works Summary | [5 empty] | £ p
Areas
|  | Extended car park (Area of extension) | 169.95 | m2
|  | Access apron | 8.36 | m2
|  | Extended path | 35.2 | m2
Works Cost Element
| 1 | E2 - Provision of extended carpark & access improvements
|  | 1 Site preparation works |  |  |  |  | 5000
|  | 2 Roads, paths and pavings |  |  |  |  | 35330
|  | 3 Planting |  |  |  |  | 1500
|  | 4 Fencing, railings and walls |  |  |  |  | 0
|  | 5 Site/street furniture and equipment |  |  |  |  | 7950
|  | 6 External drainage |  |  |  |  | 0
|  | 7 External services |  |  |  |  | 15860
|  | 8 Minor building works and ancillary buildings |  |  |  |  | 0
Contractors additional items
| 2 | General Preliminaries |  |  |  |  | 0
|  | Contractors Over Heads and Profit % applied to Sub-Total |  |  |  | %*
* - It is requested that the Contractors O/H&P percentage be added for purposes of variations, failure to do so may result in a non-compliant bid.
[6 empty] | Works Total | 65640
Fees
|  | Allow for confirmation of Cube test results of Concrete |  |  |  | Item | 0
[6 empty] | Fees Total | 0
| 3 | Risk
|  | Provisional Sums & Contingencies |  |  |  |  | 12500
[6 empty] | Risk Total | 12500
[5 empty] | TOTAL to Form of Tender | £ | 78140
TOTAL per Bedspaces
[5 empty] | Cost/Bed Space | £
Notes
Refer to Tender drawings and specifications
Tender drawings to take precedence contractor to price all items on tender drawings and pricing schedule
Contractors to ensure ALL Pricing Schedule items as described are priced.
Contractors are to check that all formulas within this document are calculating correctly.

## 1 Works E2 Extended Car Park
Pricing Schedule
Client Name : |  | Harbury Parish Council |  |  |  |  | Schedule of works
Project Title : |  | Community EV Charging station at Harbury Queen Elizabeth II Playing Fields |  |  |  |  | 18th November 2023
Project Nr : |  | 6541 |  |  |  | Version Nr. : | 1
Tender
E Extended Car Park (note includes ductwork provision for future EV Charging and VAWT) | [6 empty] | 4Q23
This pricing schedule has been laid out using the NRM headings to assist in contractor pricing, but has not necessarily been measured fully in accordance with NRM. Contractor to ensure all items identified on the drawings are priced and included within these items or additional items at the foot of this document.
1 Site preparation works
1 Site clearance
1.1.1 |  | Scrub and vegetation clearance | Allow for all necessary cutting back of hedges, grass and vegetation necessary to undertake full scope of works, removal of material off site. | 1 | Item | 300 | 300
1.1.2 |  | Existing signage | Allow for removing existing 2 No field access signage posts and signs (storing signs for reuse) | 1 | Item | 100 | 100
1.1.3 |  | Dog Bin | Removing and relocating existing dog bin in concrete foundations set back from widened footpath. (Provisional) | 1 | Item | 100 | 100
2 Preparatory groundworks
1.2.1 |  | Tarmac removal | Allow for all breaking up of existing tarmac areas (access drive and footpath as indicated) and sub-base to enable construction of extended grasscrete car park, removal of material off site. | 1 | Item | 2500 | 2500
1.2.2 |  | Make up/reduce levels | Allow for all necessary adjustment of existing ground levels to enable construction of extended grasscrete car park and tying into existing car park and playfield levels, removal of surplus material off site. | 1 | Item | 2000 | 2000
[6 empty] | 1 Site preparation works Sub Total | 5000
2 Roads, paths and pavings
1 Roads, paths and pavings
2.1.1 |  | Link footpath to playing field | Allow for the the supply and construction of new 2200 wide tarmacadam footpath including subase, edging and ground preparation as indicated on drawings. | 35.2 | M2 | 75 | 2640
2.1.2 |  | Connection to existing footpath | Allow to disc cut into exiting footbath to connect in new aligned link footpath; sealing joint | 1 | Item | 200 | 200
2.1.3 |  | PC Edging kerbs | Supply and install 150x50 PC edging kerbs set in concrete to form edging both sides of new extended path | 1 | Item | 2000 | 2000
2.1.4 |  | PC Half Battered kerbs | Supply and install 255x125 HB2 PC half battered road kerbs set in concrete to form edge to rear and end of new grasscrete parking parking bays only; including internal corner and dropper down to new link path. | 1 | Item | 450 | 450
2.1.5 |  | Grasscrete Car parking spaces | Supply and install 'Grasscrete', as indicated on drawings, using Grasscrete formers type GC2, 150mm deep laid on a consolidated 250mm sub-base with a 10/20mm blinding layer of sand. Steel mesh reinforcement to BS4483 reference A252, weighing 3.75kg/m2. Concrete 30MN/m2 at 28 days with air entrainment of 3%. 10mm maximum aggregate and a 150mm slump placed around formers and mesh and levelled to tops of formers. After 48 hours melt exposed tops of formers and fill with soil. Following settlement sow Grassmix No.1 at a rate of 50g/m2 and top up with fine friable topsoil, apply fertiliser as necessary. Including forming all edges, bay markings and expansion joints. Expansion joints shall be incorporated at maximum 10 x 10m centres and shall consist of 25mm wide pre-soaked softwood filler. All in accordance with manufacturers design and installation recommendations. | 176 | M2 | 150 | 26400 |  | 176.3
2.1.6 |  | Margin around existing bollards | Allow to grub up material around existing timber posts, 2No drop bollards and white posts, install approx 400mm wide x 150mm thick concrete (using GC2 grascrete formers) on 250mm stone base from back of existing road kerb to end of existing spaces around existing bollards laid to falls to level of new grasscrete | 1 | Item | 750 | 750
2.1.7 |  | Existing Block paved car park | Allow to jet wash existing block paved car park on completion | 1 | Item | 250 | 250
2 Special surfacings and pavings
2.2.1 |  | Coloured concrete | Extra over grasscrete above for “Terratone”coloured concrete GC2/Terratone, iin accordance with manufacturers recommendations (Provisional) | 1 | Item | 2640 | 2640
[6 empty] | 2 Roads, paths and pavings Sub Total | 35330
3 Planting
1 Seeding and turfing
3.1.1 |  | Making good seeding | Make good areas of playing field services disturbed to match existing | 1 | Item | 500 | 500
2 External planting
3.2.1 |  | Trees | Supply and install Semi-mature Tree | 2 | Nr | 250 | 500
3.2.2 |  | Widlife friendly planting | Prepare ground and form area of wild life friendly planting, enclose it with chesnut pale fencing - location TBD | 1 | Item | 500 | 500
[6 empty] | 3 Planting Sub Total | 1500
4 Fencing, railings and walls
|  | 1 Fencing and railings | Not applicable
|  | 2 Walls and screens | Not applicable
|  | 3 Retaining walls | Not applicable
|  | 4 Barriers and guardrails | Not applicable
[6 empty] | 4 Fencing, railings and walls Sub Total | 0
5 Site/street furniture and equipment
1 Site/street furniture and equipment
5.1.1 |  | Bollards | Supply and install 1000 high recycled suare pointed to bollards (Brown), set in concrete installed in accordance with manufacturers recommendations | 16 | Nr | 200 | 3200
5.1.2 |  | Lockable drop bollards | Supply and install 850 high round retractable/telescopic drop bollards; white; with lift assist and lockable keys (alike suited for all), set in 400 concrete and stone base all in accordance with manufacturers instructions. | 3 | Nr | 750 | 2250
5.1.3 |  | Signage | Allow to supply and install signage post setting in concrete and refixing existing signage with new security fixings. | 2 | Nr | 250 | 500
5.1.4 |  | Bat Boxes | Supply and install bat boxes - location TBD; ECO bat box https://www.nestbox.co.uk/products/eco-bat-box or equal and approved | 2 | Nr | 250 | 500
5.1.5 |  | Bird nesting boxes | Supply and install nest boxes - location TBD, ECO small bird box https://www.nestbox.co.uk/products/eco-small-bird-boxor or equal and approved | 2 | Nr | 250 | 500
5.1.6 |  | Insect boxes | Supply and install insect boxes - location TBD; Bug Hotel https://www.nestbox.co.uk/products/bug-hotel or equal and approved | 2 | Nr | 250 | 500
5.1.7 |  | Bin | Supply and install new metal refuse bin with galvanised internal holder - location TBD; https://uk.glasdon.com/litter-bins/metal-litter-bins/invicta-litter-bin or equal and approved secured to concrete base. | 2 | Nr | 250 | 500
|  | 2 Ornamental features |  | 0 | Item |  | 0
[6 empty] | 5 Site/street furniture and equipment Sub Total | 7950
6 External drainage
1 Surface water and foul water drainage
|  | SUDs requirement | Excluded | 0 | Item | 0 | 0
|  | New manholes - Storm | Excluded | 0 | Nr | 0 | 0
|  | New drain runs - Storm | Excluded | 0 | Item | 0 | 0
|  | New manholes - Foul | Excluded | 0 | Nr | 0 | 0
|  | New drain runs - Foul | Excluded | 0 | Item | 0 | 0
|  | CCTV, repair and connections | Excluded | 0 | Item | 0 | 0
|  | Existing drain removal, reconnection & diversion | Excluded | 0 | Item | 0 | 0
|  | 2 Ancillary drainage systems | Excluded | 0 | Item | 0 | 0
|  | 3 External laboratory and industrial liquid waste drainage | Excluded | 0 | Item | 0 | 0
|  | 4 Land drainage | Excluded | 0 | Item | 0 | 0
|  | 5 Testing and commissioning of external drainage installations | Not applicable | 0 | Item | 0 | 0
[6 empty] | 6 External drainage Sub Total | 0
7 External services
|  | 1 Water mains supply | Not applicable | 0 | Item | 0 | 0
|  | 2 Electricity mains supply | Not applicable | 0 | Item | 0 | 0
|  | 3 External transformation devices | Not applicable | 1 | Item | 0 | 0
|  | 4 Electricity distribution to external plant and equipment | Future EV Charging Points & VAWT - See Builders Work below | 0 | Nr | 0 | 0
|  | 5 Gas mains supply | Not applicable | 0 | Nr | 0 | 0
|  | 6 Telecommunications and other communication system | Not applicable | 0 | Nr | 0 | 0
|  | 7 External fuel storage and piped distribution systems | Not applicable | 0 | Item | 0 | 0
|  | 8 External security systems | Not applicable | 0 | Item | 0 | 0
|  | 9 Site/street lighting systems | Excluded | 0 | Item | 0 | 0
|  | 10 Irrigation systems | Not applicable | 0 | Item | 0 | 0
|  | 11 Local/district heating installations | Not applicable | 0 | Item | 0 | 0
7.12 |  | 12 Builder’s work in connection with external services | Allow for all builders work in connection with external services | 1 | Item | 1000 | 1000
7.12.1 |  | Trenches for EV Ducting | Excavating trenches for 1 Nr duct for EV Charging supply cables (cabling by others); 90/100mm diameter; assume 750mm average depth grading bottoms of excavations; earthwork support if necessary; backfilling with granular materials; compaction; disposal of surplus arising off site (Provisional) | 15.6 | M | 75 | 2640 | 15.6
7.12.2 |  | EV Ducting | Extra over; 100mm ductwork laid in trenches; including sand bed & surround; draw cord and identification tape | 15.6 | M | 25 | 2640
7.12.3 |  | EV post foundation | Extra over; Supply and install EV Blocks 300x300x450 deep (https://evblocks.com) | 3 | Nr | 450 | 1350
7.12.4 |  | EV Duct Junction boxes | Extra over; Supply and install Duct junction boxes 300x300x450 deep including using NAL STAKKAbox including heavy duty C250 cover | 1 | Nr | 450 | 450
7.12.5 |  | Trenches for VAWT ducting | Excavating trenches for 1 Nr duct for VAWT supply cables (cabling by others); 140/150mm diameter; assume 1000mm average depth grading bottoms of excavations; earthwork support if necessary; backfilling with granular materials; compaction; disposal of surplus arising off site (Provisional) | 47.6 | M | 75 | 2640
7.12.6 |  | VAWT Ducting | Extra over; 140mm ductwork laid in trenches; including sand bed & surround; draw cord and identification tape | 47.6 | M | 25 | 2640
7.12.7 |  | VAWT Duct Junction boxes | Extra over; Supply and install Duct junction boxes 450x450x450 deep using NAL STAKKAbox including heavy duty C250 cover | 3 | Nr | 500 | 1500
7.13 |  | 13 Testing and commissioning of external services | Allow for all testing & commissioning in connection with external services | 1 | Item | 1000 | 1000
[6 empty] | 7 External services Sub Total | 15860
8 Minor building works and ancillary buildings
|  | 1 Minor building works | Excluded | 0 | Item | 0 | 0
|  | 2 Ancillary buildings and structures | Excluded | 0 | Item | 0 | 0
|  | 3 Underpinning to external site boundary walls | Excluded | 0 | Item | 0 | 0
[6 empty] | 8 Minor building works and ancillary buildings Sub Total | 0
9 Contractors additional items
Contractor to include for any additional items of work identified on Tender Drawings, Specifications and Appendices but not specifically mentioned or listed above but will be required in order to complete the works as necessary. It is therefore assumed all works as shown on Tender Drawings, Specifications and Appendices are deemed included within your tender sum.
9.1 |  | Contractor to list additional items as necessary:-
9.1.1
9.1.2
9.1.3
[6 empty] | Section 1 Works Total to Tender Summary | 65640

## 2 Preliminaries
Part F - Pricing Schedule
Client Name : |  | Harbury Parish Council |  |  | Section 1 - General Preliminaries
Project Title : |  | Community EV Charging station at Harbury Queen Elizabeth II Playing Fields
Project Nr : |  | 6541 |  | Version Nr. : | 1
1 | GENERAL PRELIMINARIES (PRICING DOCUMENT)
| (Contractor to detail below all Preliminaries costs associated to deliver the works) |  |  |  | £ p
Item No
Assuming 6 week overall programme
1 | GENERALLY |  |  | Item
2 | NATURE OF THE WORK |  |  | Item
3 | WORKING HOURS (Mon-Friday 8-5pm) |  |  | Item
4 | MEETINGS AND REPORTS |  |  | Item
5 | ACCESS TO PRIVATE LAND AND PROPERTIES |  |  | Item
6 | COST CONTROL ARRANGEMENTS |  |  | Item
7 | VARIATIONS |  |  | Item
8 | PRE-CONTRACT MEETINGS |  |  | Item
9 | WORKING NEAR OCCUPIED BUILDINGS
10 | WORK WITH ASBESTOS PRODUCTS |  |  | Item
11 | HEALTH AND SAFETY - CONSTRUCTION DESIGN AND MANAGEMENT REGULATIONS (CDM) 2015 |  |  | Item
12 | PLANT, TOOLS AND VEHICLES |  |  | Item
13 | SUFFICIENCY AND AVAILABILITY OF LABOUR |  |  | Item
14 | SAFEGUARDING THE WORKS, MATERIALS AND PLANT AGAINST DAMAGE AND THEFT |  |  | Item
15 | INJURY TO PERSONS AND PROPERTY |  |  | Item
16 | INCLEMENT WEATHER |  |  | Item
17 | WINTER WORKING |  |  | Item
18 | SCAFFOLDING, STAGING, TEMPORARILY SUSPENDED ACCESS CRADLES AND PLATFORMS ETC |  |  | Item
19 | THE CONSTRUCTION (DESIGN AND MANAGEMENT) REGULATIONS (CDM) 2015 |  |  | Item
20 | WATER FOR THE WORKS |  |  | Item
21 | TEMPORARY LIGHTING, POWER AND HEATING FOR THE WORKS |  |  | Item
22 | TEMPORARY BUILDINGS FOR USE BY THE CONTRACTOR AND HIS SUBCONTRACTORS |  |  | Item
23 | TEMPORARY WORKS |  |  | Item
24 | TEMPORARY TELEPHONE |  |  | Item
25 | SAFETY, HEALTH AND WELFARE REGULATIONS |  |  | Item
26 | CONTROL OF SUBSTANCES HAZARDOUS TO HEALTH REGULATIONS 2002 |  |  | Item
27 | WORKING RULE AGREEMENT |  |  | Item
| OBLIGATIONS AND RESTRICTIONS IMPOSED BY THE EMPLOYER |  |  | Item
28 | GENERALLY |  |  | Item
29 | CONTROL OF SUBSTANCES HAZARDOUS TO HEALTH REGULATIONS 2002 |  |  | Item
30 | IDENTIFICATION OF CONTRACTORS EMPLOYEES |  |  | Item
31 | SITE MANAGER OR PERSON IN CHARGE |  |  | Item
32 | COMPLAINTS |  |  | Item
33 | SITE MEETINGS |  |  | Item
34 | PROTECTION OF PROPERTY |  |  | Item
35 | REMOVAL OF ASBESTOS |  |  | Item
36 | PROTECTION OF EXISTING TREES, SHRUBS, FENCES, RAILINGS, GATES ETC. |  |  | Item
37 | EXISTING SERVICES |  |  | Item
38 | ACCESS FOR PLANT, SCAFFOLDING AND MATERIALS |  |  | Item
39 | ACCESS FOR INSPECTION |  |  | Item
40 | PROGRAMME AND PROGRESS CHART |  |  | Item
41 | MATERIALS, GOODS AND WORKMANSHIP |  |  | Item
42 | PROTECTION |  |  | Item
43 | TESTING MATERIALS |  |  | Item
44 | WAGES BOOKS |  |  | Item
45 | CERTIFICATES |  |  | Item
46 | OVERTIME |  |  | Item
47 | HOARDINGS ETC - Heras Fencing to work area with signage until completion |  |  | Item
|  |  | C/Fwd | £ | 0
| Brought Forward |  | B/Fwd | £ | 0
48 | DISPLAY BOARDS - Allow site Board with client, funder and consultants logos |  |  | Item
49 | RUBBISH |  |  | Item
50 | MUD OR DEBRIS ON THE ROADS ETC. |  |  | Item
51 | PREVENTION OF THE SPREAD OF DUST, NOISE ETC |  |  | Item
52 | FIXING ONLY |  |  | Item
53 | TRADESMEN ENGAGED BY THE CLIENT
54 | HANDOVER OF COMPLETED PROPERTIES |  |  | Item
55 | WORKS PRIOR TO HANDOVER |  |  | Item
GENERALLY
56 | DAYWORKS |  |  | Item
57
58
59
60
61 | CONTRACTOR'S GENERAL COST ITEMS: (specify) |  |  | Item
62
63
64
65
66
|  |  | Section 2.00 Preliminaries Total To Tender Summary | £ | 0

## 3 Prov Sum
Pricing Schedule
Client Name : |  | Hastings Borough Council | [5 empty] | Section 5 Dayworks & Provisional Sums
Project Title : |  | Proposed Construction of BREEAM Certified Business Centre at Plot QX, Sidney Little Road, St Leonards-on-Sea, Hastings, TN38 9PU
Project Nr : |  | 6400 |  |  |  |  | Version Nr. : | 1
5 | DAYWORKS AND PROVISIONAL SUMS |  |  |  |  | Qty | Rate | Total
[7 empty] | £ P | £ p
5.01 | Dayworks
Labour
5.01.1 | Provisional sum: Include prime cost of labour incurred before Final Completion Date: Allow sum of £1,000 (One Thousand Pounds) for labour. | [6 empty] | 1000
5.01.2 | State daily costs (10 hours) for
|  | Foreman | 10hrs | per day | 0
|  | Plant Operator | 10hrs | per day | 0
|  | Carpenter | 10hrs | per day | 0
|  | Labourer | 10hrs | per day | 0
5.01.3 | Percentage adjustment: Add to cover incidental costs, overheads and profit: Addition on Prime Cost of labour | [5 empty] | % | 0
Materials
5.01.4 | Provisional sum: Include prime cost of materials incurred at any time during the Contract: Allow sum of £100 (One Thousand Pounds) for materials. | [6 empty] | 1000
5.01.5 | Percentage adjustment: Add to cover incidental costs, overheads and profit: Addition on Prime Cost of materials | [5 empty] | % | 0
Plant
5.01.6 | Provisional sum: Include prime cost of plant (equipment) incurred before Final Completion Date: Allow sum of £1,000 (One Thousand Pounds) for plant. | [6 empty] | 1000
5.01.7 | Percentage adjustment: Add to cover incidental costs, overheads and profit: Addition on Prime Cost of plant | [5 empty] | % | 0
5.02 | Provisional Sums
5.02.1 | Allow a provisional sum for extra over excavations to be spent or deducted as directed by the Contract Administrator, to depths not exceeding: | [5 empty] | PSUM | 1500
| i | 0.7m - 1.0m below FFL per m3 |  | Rate per m3 | 0
| ii | 1.0m - 1.2m below FFL per m3 |  | Rate per m3 | 0
| iii | 1.3m x 1.6m below FFL per m3 |  | Rate per m3 | 0
5.02.2 | Allow a provisional sum for additional replacement bollards to be spent or deducted as directed by the Contract Administrator | [5 empty] | PSUM | 1500
5.02.3 | Allow a provisional sum for Additional planting to be spent or deducted as directed by the Contract Administrator | [5 empty] | PSUM | 2500
5.02.4 | Allow a provisional sum for Replacement signage to be spent or deducted as directed by the Contract Administrator | [5 empty] | PSUM | 500
5.02.5 | Allow a provisional sum for repairs to existing block paving to be spent or deducted as directed by the Contract Administrator | [5 empty] | PSUM | 500
5.02.6 | Allow a provisional sum for additional topsoil/ground preparation to be spent or deducted as directed by the Contract Administrator | [5 empty] | PSUM | 2000
5.03 | Contingencies
5.03.1 | Allow the Contingency Sum of £1,000 (One Thousand Pounds) to be spent or deducted as directed by the Contract Administrator | [6 empty] | 1000
[6 empty] | Section 3.00 Dayworks and Provisional Sum Tender Total To Tender Summary | £ | 12500

## Sheet1
Grasscrete formers type GC2, 150mm deep laid on a consolidated 150mm sub-base with a 10/20mm blinding layer of sand. Steel mesh reinforcement to BS4483 reference A252, weighing 3.75kg/m2. Concrete 30MN/m2 at 28 days with air entrainment of 3%. 10mm maximum aggregate and a 150mm slump placed around formers and mesh and levelled to tops of formers. After 48 hours melt exposed tops of formers and fill with soil. Following settlement sow Grassmix No.1 at a rate of 50g/m2 and top up with fine friable topsoil, apply fertiliser as necessary.
(Where coloured concrete is required please suffix the GC former type reference with “Terratone” eg “GC3/Terratone”.)
Ecology Report Recommendations:
- install 2 bat boxes - location TBD
- install 2 nest boxes - location TBD
- install 2 insect boxes - location TBD
form area of wild life friendly planting, enclose it with chesnut pale fencing - location TBD
Bin
Excavating trenches for 1 Nr duct for communication cable; 100mm diameter; assume 750mm average depth grading bottoms of excavations; earthwork support if necessary; backfilling with granular materials; compaction; disposal of surplus arising off site (Provisional)
Extra over; 100mm ductwork laid in trenches; including sand bed & surround; draw cord and identification tape