## Schedule of Works
| 15/1395 The Public Hall, Liskeard (revision 2) |  |  | Dayworks |  |  | Rate
|  |  |  | Foreman |  |  | 0
|  |  |  | Tradesman |  |  | 0
| Valuation no.: | 1 |  | Groundworker |  |  | 0
| Valuation Date: | 2024-03-05 |  | Unskilled |  |  | 0
| Valuation Issue Date: | 2024-03-05 |  | Plant |  |  | Cost + 0%
|  |  |  | Materials |  |  | Cost + 0%
|  |  |  | Sub Contract |  |  | Cost + 0%
(All figures are exclusive of VAT)
(Allow to make good for all works)
| Element | Element Total | Notes | Weeks | Progress | Updated This Valuation? | Valuation
1 | Prelims | [5 empty] | 0
1.01 | Supervision | 0 |  |  | 0% |  | 0
1.02 | Fuel | 0 |  |  | 0% |  | 0
1.03 | Phone | 0 |  |  | 0% |  | 0
1.04 | Toilet | 0 |  |  | 0% |  | 0
1.05 | Small Plant / access equipment | 0 |  |  | 0% |  | 0
1.06 | Deliveries | 0 |  |  | 0% |  | 0
1.07 | Waste / Skips | 0 |  |  | 0% |  | 0
1.08 | Clean | 0 |  |  | 0% |  | 0
1.09 | Site labourer | 0 |  |  | 0% |  | 0
1.1 | Joint names insurance | 0 |  |  | 0% |  | 0
1.11 | Office overheads | 0 |  |  | 0% |  | 0
2 | Provisional Sums
2.01 | Contingencies | 1000 |  |  | 0% |  | 0
2.02 | Light fitting supply (4 @ £100 ea.) | 400 |  |  | 0% |  | 0
2.03 | Door/window ironmongery supply | 500 |  |  | 0% |  | 0
2.04 | Floor finish supply (40m2 @ £50/m2) | 2000 |  |  | 0% |  | 0
2.05 | Supply & fit blackout roller blinds with pelmet to windows, design TBA by supplier (3 @ £300 ea.) | 900 |  |  | 0% |  | 0
3 | Works
3.01 | Scaffold / access | 0 |  |  | 0% |  | 0
3.02 | Demolition (client to confirm if keeping Members' Room door for future use elsewhere) | 0 |  |  | 0% |  | 0
3.03 | Fit 4 new pendent lights in positions TBA with 2-way switches adjacent 2 entrance doors, disconnect redundant electrics, works to data by others direct to employer, emergency lighting/sign changes to regs, fit 5no. New recessed double sockets (white MK with outside rockers) & chase walls for cables with recessed conduit runs (1 on north wall west of radiator, 1 on east wall just south of new cupboard, 1 on east wall in SE corner, 2 on south wall each between windows) | 0 |  |  | 0% |  | 0
3.04 | Intruder alarm changes by Waldon Fire & Security to their design | 0 |  |  | 0% |  | 0
3.05 | Fire alarm system changes by Waldon Fire & Security to their design | 0 |  |  | 0% |  | 0
3.06 | Remove redundant cables ouside east window | 0 |  |  | 0% |  | 0
3.07 | Strip wallpaper, make good, prep, hang lining paper & decorate | 0 |  |  | 0% |  | 0
3.08 | Strip polystyrene detailing from Mayor's Parlor ceiling | 0 |  |  | 0% |  | 0
3.09 | Remove & reinstate radiators | 0 |  |  | 0% |  | 0
3.1 | BWIC with M&E | 0 |  |  | 0% |  | 0
3.11 | Replace double glazed units in 3no. Vertical sash windows with clear safety glass (6 panes) | 0 |  |  | 0% |  | 0
3.12 | Rehang existing internal door in new doorway & adjust to suit | 0 |  |  | 0% |  | 0
3.13 | New SW boxing to cable at head of door in NE corner, decorated | 0 |  |  | 0% |  | 0
3.14 | New SW cupboard to NE alcove below existing wall cupboard | 0 |  |  | 0% |  | 0
3.15 | Plasterboard/plastering | 0 |  |  | 0% |  | 0
3.16 | Fit new carpet, supply / fit premium underlay / perimeter grippers / threshold trim to match existing in building to suit | 0 |  |  | 0% |  | 0
3.17 | Decoration including lining paper to walls | 0 |  |  | 0% |  | 0
4 | Contractor Profit
4.01 | 0% | 0 |  |  | 0% |  | 0
AI 1 |  | NOTES | OMIT | ADD | Progress |  | Valuation
AI 1.01 |  |  | 0 | 0 | 0% |  | 0
AI 1.02 |  |  | 0 | 0 | 0% |  | 0
AI 2 |  | NOTES | OMIT | ADD | Progress |  | Valuation
AI 2.01 |  |  | 0 | 0 | 0% |  | 0
AI 2.02 |  |  | 0 | 0 | 0% |  | 0
Daywork Sheets |  | NOTES |  | ADD | Progress |  | Valuation
1 |  |  |  | 0 | 0% |  | 0
2 |  |  |  | 0 | 0% |  | 0
Materials On Site Not Yet Fixed |  | NOTES |  | ADD | Progress |  | Valuation
1 |  |  |  | 0 | 0% |  | 0
2 |  |  |  | 0 | 0% |  | 0
3 |  |  |  | 0 | 0% |  | 0
|  | Contract Sum | OMIT | ADD | Variation |  | Valuation
| Totals (All figures are exclusive of VAT): | 4800 | 0 | 0 | 0 |  | 0