	[image: image1.png]Ministry of Housing,
Communities &
Local Government




	
	



	Ipsos MORI 

78-81 Borough Road

London 
SE1 1FY
FAO Rachel Williams
CPD/004/109/090 (Lot 3)


	11 March 2019


Dear Contractor,
CONTRACT FOR NATIONAL EVALUATION OF THE EXPANDED TROUBLED FAMILIES PROGRAMME - LOT 3 LONGITUDINAL SURVEYS

Please find attached an amendment to the above mentioned contract. Please confirm acceptance of this amendment as soon as possible by signing and returning this document to the undersigned. 
MHCLG will accept a signed hard copy or a PDF version.
I look forward to hearing from you.

Yours faithfully

REDACTED
Ministry of Housing, Communities and Local Government
AMENDMENT TO CONTRACT

The details contained in this document form a binding amendment to the Contract referenced below between the Contractor and the Secretary of State for the Ministry of Housing, Communities and Local Government (“MHCLG”).
Contract title
:
Contract for National Evaluation of the Expanded Troubled Families Programme – Lot 3 Longitudinal Surveys
Contract reference
:
CPD/004/109/090 (Lot 3)
Purchase order no.
:
REDACTED
Contractor
:
Ipsos MORI
Amendment no.
:
6
Effective date of
: 
11 March 2019
amendment

Details of amendment
:
As below
Production of 11 local area reports for the areas involved in the longitudinal family survey.  The reports will be provided to Local Authorities in exchange for their time and efforts engaging in the research. 

Details of the tasks involved in the production of the reports are as follows:

1. Set up template for approval by MHCLG;

2. Check and prepare data;

3. Prepare charts for each of the 11 reports;

4. Write headline findings for each chart for each of the 11 reports;

5. Share reports with MHCLG and amend as per feedback;

6. Share reports with Local Authorities and answer any questions.
7. To quality assure the data and reports.
A breakdown of the costs for this work are set out in the table below.
	Ipsos Team member
	Role
	Day rate
	Time
	Cost 
(exc. VAT)

	REDACTED
	Task 7
	£850
	0.5
	£425 

	REDACTED
	Task 7
	£750
	0.5
	£375 

	REDACTED
	Tasks 2 and 6
	£550
	1.5
	£825 

	REDACTED
	All Tasks
	£450
	5
	£2,250 

	Total
	
	 
	7.5
	£3,875 


Contract value prior to
:
£855,812.50 (excluding VAT)
this amendment
Maximum value of this
:
£3,875.00 (excluding VAT) 
amendment 
Revised value
:
£859,687.50 (excluding VAT)

for the Contract
Terms and conditions
:
All other terms and conditions remain the same for this Contract.
	FOR AND ON BEHALF OF THE SECRETARY OF STATE FOR HOUSING, COMMUNITIES AND LOCAL GOVERNMENT
	FOR AND ON BEHALF OF THE CONTRACTOR

	Name:
	Name:

	Title
	Title:

	Signed:
	Signed:

	Date:
	Date:


MHCLG Amendment

CPD/004/109/090 (Lot 3)

[image: image1.png]