Changes in red made on 14th July 2017

Assessment and accreditation process for child and family social workers: Development, implementation and delivery of assessment infrastructure.

The contract will seek contractor(s) to set up an operational system for the assessment and accreditation of child and family social workers in England.  They will need to create a clear framework and delivery structure to ensure assessment rollout for approximately 1,200 social workers between January 2018 and January 2020. A range of elements will need to be delivered including:

1.	Assessment centres within the volunteer local authority areas;

2.	Recruitment and training of assessors and observers;

3.	Recruitment and training of actors for simulated observation;

4.	Preparing and expanding a pre-existing digital platform to be ready for phased roll out.

5.	Design and implementation of a system for result feedback to employers and individuals including a data base for securely storing results;

6.	Design and implementation of a system for dealing with retakes, concerns, queries and appeals processes.

7.          Work alongside an independent researcher partner to understand and action change requirements to the delivery programme over the contract period.

Please note that this list is not exhausted.

The contract will support the continued social work reform programme agreed by Ministers to achieve the ambition for all child and family social workers, supervisors and practice leaders to be assessed by 2020.

The Department for Education is establishing a rigorous assessment system based on the knowledge and skills statements (https://www.gov.uk/government/publications/knowledge-and-skills-statements-for-child-and-family-social-work) developed for child and family frontline social workers and practice supervisors.

The four-stage assessment and accreditation system will consist of:

- Stage 1: direct practice observation by the employer - in the workplace over a period of time leading to the employer endorsement

- Stage 2: an online assessment of knowledge

- Stage 3: an observed interactive practice simulation in a controlled environment with independent examiners

- Stage 4: a written assessment linked to the simulated observation.

The content of the assessments for child and family social workers and practice supervisors for stages 2, 3 and 4 above is currently in development under a separate contract. This contractor will be expected to work with the successful bidder(s) for the assessment delivery infrastructure to ensure there is a smooth transition between development of the assessment process and its implementation.

The department will be running two information days on the invitation to tender, Manchester 7 August and London 8 August. If you are interested in attending one of these events, please email NAAS.DELIVERYTENDER@education.gov.uk