# Annex A

| Title of Project | Understanding the effects of land management scenarios on reef resilience in Montserrat |
| --- | --- |
| Date and Time for Return of Bids | Monday 13th September @ 16:00 hours |
| Contract Reference Number | C21-0481-1578 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO JAMES HUTCHINSON, BRYONY MEAKINS OR DORA IANTOSCA VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the individuals below, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for Technical Information relating to this Project Specification | James Hutchinson Email: james.hutchinson@jncc.gov.uk Tel: +44 (0)1 1733 866940 OR Bryony Meakins Joint Nature Conservation Committee Email: bryony.meakins@JNCC.gov.uk Tel: +44 (0)1733 866950 |
| Contact for Queries Regarding the Procurement Procedure | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk or contractqueries@jncc.gov.uk Telephone: +44 (0)1733 866894 |
| Proposed Start Date | Week beginning 20th September 2021 |
| Proposed End Date | Friday, 28th January 2022 |

Title of Project

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	3

5.	Project Objectives: Detailed Tasks	3

6.	Potential Follow-On Work	3

7.	Outputs	4

8.	Dissemination	4

9.	Timescale	4

10.	Health and Safety	4

11.	Product Specification	4

12.	Project Management	5

13.	Instructions for Bid Submission	5

14.	Evaluation Criteria	6

15.	Payment	7

16.	Additional Requirements	7

17.	References	7

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to  protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

JNCC is providing technical assistance to the Overseas Territory of Montserrat.  This project aims to support the Government of Montserrat to;

- Explore the impacts of different future scenarios of land use and environmental management in Montserrat on marine habitats and improve understanding of the natural capital linkages and potential ‘trade-offs’/synergies to support decision making.

This project aims to build on previous projects and experience gained elsewhere in the Caribbean and South Atlantic Territories, to provide Montserrat with a tool to support terrestrial spatial planning and nature conservation gains, to gain a better understanding of natural capital linkages and inform better decision making around land-use management.

## Project Background

The ‘Emerald Isle of the Caribbean’, Montserrat is a highly biodiverse, volcanic & mountainous island of 103km2, located between the islands of Nevis and Guadeloupe, 43 km south-west from Antigua (Bettencourt & Imminga-Berends, 2015).  Montserrat’s ecosystems provide an important source of income through the exploitation of its unique biodiversity to promote tourism as well as supporting the livelihoods of Montserrat’s population.  Ecosystems provide multiple benefits such as the provision of fresh water, maintaining soil fertility and a variety of food resources.

The Soufriere volcano has been active since 1995 causing extensive damage to biodiversity and ecosystems and has caused social and economic disruption, with the migration of 2/3 of the population (OCTA, 2015).  Infrastructure was destroyed, the thriving tourism industry was severely reduced and agriculture sector was devastated.  Hurricanes also pose a serious risk and are expected to become more frequent and intense in the future because of climate change.  Montserratians are working to overcome the crisis and move on to redevelop infrastructure, economy, and industry that supports and encourages a growing and more independent population.

In 2016 JNCC started the ‘Natural Capital in the Caribbean and South Atlantic Overseas Territories’ project (CSSF-funded projects).  Natural capital in a number of the UK’s Caribbean and South Atlantic OTs was assessed, supported by training and capacity building to monitor environmental change and integrate environmental evidence into economic policy making and infrastructure planning.

In 2017, JNCC commissioned a Data Management project for the Caribbean island of Montserrat as part of a territory-to-territory partnership between the Government of Montserrat and the Falklands Islands Government. This project designed and built a data management system and process as a tool to Develop a sound evidence base for Montserrat:  A tool for environmental management, spatial and economic planning, and natural capital assessments.  A Data Gateway for Montserrat was built to enable Montserrat to enhance data management capacity (discovery, access, manage, analyse & use of data).

Following a similar assessment carried out in St Helena in 2018/19:  South Atlantic Natural Capital Assessment; Modelling St Helena’s Natural Capital, the 2020 project ‘Developing a Decision Support Tool to Inform Land Management Scenarios in Montserrat‘ explored different future development scenarios and the impacts, synergies and trade-offs associated with different land management in Montserrat.

This project will build upon and use learning from the 2020 project and experience gained elsewhere in the Caribbean and South Atlantic Territories, to demonstrate the use of the tools, identify areas for the use of nature-based solutions to support disaster and environmental resilience in Montserrat. The project will be informed by two projects that will run in parallel with this this.  The first extends the model finished in 20/21 to a user interface in the contract ‘pilot demonstration of the use of the spatial planning and land-use decision support tools to support environmental resilience in Montserrat’ project and the second will provide Montserrat with high-resolution catchment scale hydrological model, to link-to or underpin the existing systems model.

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are:

- Through consultation, design a decision support tool that explores the effects of land use management on the marine environment that is tailored to meet the needs of the Government of Montserrat.

- Integrate knowledge from existing spatial data available for the island, and previously modelled scenarios to produce spatial outputs to visualise risks and benefits under different land management scenarios.

- Complete a trade-off case-study example of how elements of land management could be changed to realise benefits for coral reef resilience in the marine environment.

Please note:

- Stakeholder engagement is a key component of this project, both to gather initial information under objective A and iteratively throughout the project. Given the travel constraints and on-island meeting requirements, tenderers are expected to outline how they will engage and consult with stakeholders.

- These projects are:

  - Implementation of a pilot study in the use of the spatial planning and land-use decision support too.

  - Developing an inland flood/ hydrological system and indicators to monitor and inform land management in Montserrat.

Tenderers are encouraged to use on-island partners where possible.  JNCC will facilitate on-island introductions to the successful tenderer if/as necessary.

Train key Government of Montserrat personnel in the use, application and interpretation of the BBN.

## Project Objectives: Detailed Tasks

- Set up a Steering Group comprising, Government of Montserrat key personnel (e.g. Department of Environment, Department of Agriculture and Fisheries, Department of Physical Planning, GIS, etc), JNCC and contractor.

  - First Steering group meeting to be held within week of contract confirmation.

  - Meetings to be held (via remote systems) as agreed by the Steering Group

- Knowledge and data gathering

  - Agree priority management scenarios and ecosystem services to explore through Project Steering Group

  - Identify key pathways to the marine environment and the associated land use practises;

- Data collection through stakeholder engagement;

- Collate sensitivity of marine ecosystem elements to land- based activities through a literature review and linking to existing JNCC projects;

- Develop spatial modelling approach to assessing land use scenarios

  - Identify ocean flow model to map outflows to the marine environment

  - Integrate hydrological and sediment load outputs from inland models with ocean flow model and assess the impact on the marine environment

  - Visualise spatial layers of risks and benefits under land use scenarios

- Integrate the marine elements into the land-based models developed in the concurrent projects to visualise management scenarios.

  - Conceptual model and spatial layer visualisation consultation with GoM staff and stakeholders;

  - Assess and incorporate stakeholder feedback into final model;

  - Assess selected ecosystem services and scenarios, to allow trade-offs in ecosystem service delivery to be explored;

  - Synthesise results into a final technical report, to include a non-technical summary.

  - Provide recommendations for next steps.

  - Training.

- Train key Government of Montserrat personnel in the upload and use of the BBNs

  - Deliver training to key GoM personnel on how to operate and interpret the BBNs by end of January 2022.

- Communicate key project outcomes with wider stakeholders, in conjunction with the Government of Montserrat.

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2021/22 or 2022/2023 (please indicate year) as follows:

- Expand the BBN to include further land management scenarios.

- Refine the model, using updated information on the sensitivity of the marine environment to land-based pressures.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Outputs

Any products or outputs submitted to JNCC [for publication] should adhere to JNCC’s house-style and should be produced in an accessible format (see product specification for more information).

- A spatial model with quantitative or expert-judgement-derived qualitative relationships between nodes and node state data linked to spatial data layers from Montserrat’s GIS.

- Set of spatial layers to show estimates of risks/benefits of land-use changes

- A technical report, with non-technical summary, and recommendations for next steps.

- Data and modelled outputs delivered to Government of Montserrat in format and to standard compatible to Montserrat.

- Remote-training event (s) for:

  - Technical leads in use and update of the model and how to convey outputs to decision-makers and end users in model analysis, and model update as new data becomes available.

  - Training to decision makers to understand the implications of modelled outputs

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style (to be provided) and be produced using a JNCC template (to be provided), unless otherwise stated.  All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

(Note for author if research project/contract: see EQA Policy Appendix 4 (Communicating Evidence Quality). Ensure that data management and storage requirements are stipulated taking into account relevant policy for data access. See https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/

## Dissemination

The products/outputs produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to staff within JNCC, Defra and the Government of Montserrat.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (UK) | W/c 20th September 2021 |
| Draft model | October 2021 |
| Spatial model integrated into GIS platform | November 2021 |
| Training delivered | January 2021 |
| Technical report and modelled outputs delivered | January 2021 |

## Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

James Hutchinson

Email:  james.hutchinson@jncc.gov.uk

Tel: +44 (0)1 1733 866940

Bryony Meakins

Joint Nature Conservation Committee

Email: bryony.meakins@JNCC.gov.uk

Tel:     01733 866811

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed (note for author if research project/contract: see EQA Policy Appendix 1 (Bias, Conflicting Evidence and Uncertainty) and EQU Policy Appendix 3 (Quality Assurance of Expert Knowledge and Opinion):

Details of the bidder’s own internal Quality Management System;

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project;

Availability of the Project Team for a virtual start-up meeting;

Overall quote for the contract to include:

  - Day rates for all members of the Project Team;

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments; and

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 14.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC staff and staff members from the Government of Montserrat. Unless otherwise stated in your bid submission, bids will be forwarded to these agencies for evaluation purposes only.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal particularly work programme and deliverables | 10 |  |
|  | Understanding of, and relevance to, the requirements (in particular, the adequacy of outputs and understanding of working with spatial decision-making models, hydrological models and working in / with Governments in the Overseas Territories | 10 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Realism and measurability of outputs | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Total | 50 |  |
| 2. Details of Contractor (20% of the total for the three assessment categories) |  |  |  |
|  | Expertise, experience, and balance of team | 9 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors if any | 6 |  |
|  | Sub Total | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation what does presentation mean here in relation to cost? | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 8 |  |
|  | Sub Total | 30 |  |
| Total Score |  | 100 |  |

## Payment

Unless a payment schedule is stated in your submission and agreed by JNCC project manager. Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

    - On satisfactory completion of model, expected to be November 2021

    - On satisfactory completion of the model, report and recommendations delivered to JNCC and Government of Montserrat, expected to be end of January 2022.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## References

McVittie, A., Hutchison, J. Marengo, I. and Smith, N. (2019) South Atlantic Natural Capital Assessment: Modelling St Helena’s Natural Capital.  A Supplementary Report for the JNCC CSSF-funded project https://hub.jncc.gov.uk/assets/bcb4e6a3-02dc-44a6-88d1-f59be6c242a1

McVittie, A., Gibson-Poole, S., Botero, H. and Hamilton, A. (2021) Developing a decision support tool to inform land management scenarios in Montserrat, Final Report to JNCC C20-0425-1516.  Available upon request from JNCC

JNCC CSSF-funded ‘Natural Capital in the Caribbean and South Atlantic Overseas Territories’ projects

St Helena Natural Capital Modelling (2019) https://hub.jncc.gov.uk/assets/bcb4e6a3-02dc-44a6-88d1-f59be6c242a1

Developing a Decision Support Tool to Inform Land Management Scenarios in Montserrat (2020) available on request from JNCC