## Sheet1
KEY MILESTONE REFERENCE | Response Accommodation Action | [6 empty] | Response Accommodation Completion Latest Date
|  | Breakdown of Response Accommodation Action | Critical | Response Accommodation - Person Responsible | Start Date | End Date | Milestone Stage
IM1 – Workforce 1 | Identify relevant staff, if not already checked, have them vetted & DBS checked. Sign the anti-racism declaration and any other documentation to the required level in accordance with Probation Instruction 2014/55; Probation Instruction 2014/03; required to fulfil the contract. | Review DBS check records and identify staff who require DBS checks | Yes | Claire Hart |  |  | Done | 2021-10-29
|  | Establish level of DBS check required | Yes | Claire Hart |  |  | Done
|  | Obtain documents required to submit DBS checks | Yes | Claire Hart |  |  | Done
|  | Submit DBS check and confirm result satisfies requirement. | Yes | Claire Hart | 2021-11-11
|  | All staff to sign anti-racism declaration. | Yes | Claire Hart | 2021-10-08 | 2021-10-15
|  | Perform vetting in accordance with Probation Instruction 2014/55; Probation Instruction 2014/03;to fulfil the contract. Existing and new staff and sub-contractors. | Yes | Claire Hart | 2021-10-11
|  | Store documents with protective marking in accordance with Data Protection Act. | Yes | Glen Freeman | 2021-10-15 | 2021-10-15
IM2 – Workforce 2 | Check staff levels are adequate to fullfil the contract | Review changes to existing processes. | Yes | Claire Hart |  |  | Done | 20-10-21
|  | Review staffing levels based upon any process changes | Yes | Claire Hart |  |  | Done | 2021-10-29
| Check if additional staff training is required against the Framework Agreement | Review staff current competency and skill levels | Yes | Claire Hart |  |  | Done | 2021-10-29
| Carry out training if required | Deliver training to all staff in accordance with all processes to current procedures for emergency accommodation and in accordance with the framework agreement. | Yes | Claire Hart | 2021-10-05 | 2021-10-28 |  | 2021-10-29
IM3 – ICT1 | Check that the IT equipment is suitable for purpose & has an adequate software program to record all data for the contract | Audit computing and telecommunicating equipment and software build | Yes | Glen Freeman | 2021-10-06 | 2021-10-15 |  | 22-10-21
|  | Replace and upgrade if necessary to meet requirements | Yes | Glen Freeman | 2021-10-06 |  |  | 2021-10-29
| Check Reporting capabilities of Software to ensure that requirements are fully met |  | Yes | Glen Freeman |  |  | Done | DONE
| Check staff training records for use of relevant software | Identify any staff that require any training and implement | Yes | Claire Hart/Glen Freeman |  |  | Done | DONE
IM4- ICT2 | Inspection/approval of systems by customer |  | Yes |  |  |  |  | WC 25/10/21
| Record all user details & if vetting has been initiated/completed |  | Yes |  |  |  |  | WC 25/10/21
| Agree Service Management arrangements with customer |  | Yes | Claire Hart/Glen Freeman |  |  |  | WC 25/10/21
|  | Complete Cyber Essentials questionnaire. | Yes | Glen Freeman | 2021-10-06
|  | Ensure than we are compliant | Yes | Glen Freeman | 2021-10-06
|  | Send certificate to MoJ | Yes | Glen Freeman
|  | Commence Cyber Essentials Plus certification | No | Glen Freeman | 2021-10-18 | 2021-10-18
| Supply a copy of Information Security Management Plan to the customer for approval |  | Yes | Glen Freeman | 2021-10-28 | 2021-10-28 |  | 2021-10-29
IM5 – Estates 1 | Sourcing of accommodation to commence immediately in order to be ready for the Call Off Contract Commencement date. Supply evidence that accommodation providers have signed a Service Agreement Contract to supply MoJ contract via Response Accommodation | Sourcing is already underway. The signed service agreement documents are available on request and on an ongoing basis as additional property providers are recruited. This is in addition to our already onboarded providers. | Yes | Claire Hart |  |  | Done | 2021-10-29
Performance Monitoring Report | Prepare reports as required |  |  | Claire Hart/Glen Freeman | When required | When required |  | January & April 2022
Charges | Prepare reports as required |  |  | Claire Hart/Glen Freeman | When required | When required |  | Ad-hoc as required
Equalities report | Prepare reports as required |  |  | Claire Hart/Glen Freeman | When required | When required |  | Ad-hoc as required
Annual Slavery and trafficking report | April 2022 - At the end of the CallOff Contract as only 6 months duration |  |  | Claire Hart/Glen Freeman | 2022-04-01 | 2022-04-01 |  | Annually
Workforce and staffing | Prepare reports as required |  |  | Claire Hart/Glen Freeman | When required | When required |  | Ad-hoc as required
Note on C7: @claire@responseaccommodation.com Are directors or staff to sign this? -Glen Freeman