## Sheet1
CLARIFICATION LOG
Tender: | Provision of 60-65 kW Solar Panel System and Battery at TR20 8PL
Tender Reference: | Ref: GGHRDI-002(2)
Published Date: | 2023-11-21
Version number: | 0.3
Number | Clarification | Response | Reply date
1 | I am writing to request a more comprehensive architectural site plan for the new shed project | Please see https://planning.cornwall.gov.uk/online-applications/simpleSearchResults.do?action=firstPage for the planning documents. | 2023-11-27
2 | Please can you confirm the roof covering that we shall be quoting for? | The roof will be fibre cement. | 2023-11-29
3 | Where is your meter location on site? | Please see attached plan. | 2023-11-29
4 | Please can you clarify a) Inverter/ Charger Peak capacity (kW) b) Battery Storage Capacity (kWh) We’re currently assuming 40kW peak charge & 40kWH energy storage unless clarified | 40kwH of usable battery storage is required as there will be equipment that require start up loads. | 2023-11-30
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: jackie@jackiegeorge.co.uk