## Sheet1
UHT SOC Support Specification Cost Template
Please complete the SOC Support Specification cost template
Workstream | Key activities required to be completed by Business Case Advisor | Named advisor with responsibility to deliver | Grade of advisor (ie. Director) | Hourly rate (£) | Number of hours allocated | Total cost (£)
PMO / SOC co-ordination | Overall management of Group SOC development, co-ordinating all required inputs for a SOC across the Trust/Group and other external advisors |  |  |  |  | 0
| Navigate SOC inputs through internal governance structures, including development of papers, summary of actions from governance sessions |  |  |  |  | 0
Clinical Strategy Development | Subject Matter Expertise to guide the development of the Group Clinical Strategy and support key decision making in agreeing the Group Clinical Model. |  |  |  |  | 0
| Critique the Group Clinical Strategy against NHSE expectations to maximise the overall case for support from NHSE. |  |  |  |  | 0
| Articulate the Group Clinical Model to inform estate options development |  |  |  |  | 0
Demand and capacity modelling | Develop a service-level demand and capacity bed model to model the current state, unmitigated future state and mitigated future state scenarios. This should cover bedded activity and make suitable assumptions for non-bedded activity. |  |  |  |  | 0
Strategic narrative | Conduct qualitative and quantitative analysis to support the development of a case for change for developing infrastructure across the Tees Group. |  |  |  |  | 0
Options appraisal | Run a HMT compliant appraisal to identify and test options to redevelop the Tees Group Infrastructure. This will include but isn’t necessarily limited to: |  |  |  |  | 0
| Developing Programme Critical Success Factors |  |  |  |  | 0
| Developing a longlist and shortlist of options – these could consider various items such as sites, services and programme phasing |  |  |  |  | 0
| Developing a robust evidence base to agree a Preferred Way Forward with the Group. |  |  |  |  | 0
Benefits modelling | Modelling of opportunities identified in the current state analysis into cash releasing, non-cash releasing and societal benefits for all shortlisted options |  |  |  |  | 0
Economic modelling | Development of CIA model and supporting inputs |  |  |  |  | 0
| Sensitivity and switching analysis, as per NHSE guidance |  |  |  |  | 0
Financial modelling | Develop a financial model with an agreed forecast BAU position and modelling of affordability impacts of Preferred Way Forward |  |  |  |  | 0
| Development of incremental financial statements (SOCI, SOCF, SOFP) |  |  |  |  | 0
| Test and analyse different funding flows to articulate the impact on scheme affordability |  |  |  |  | 0
| Capture and craft the financial tactics and narrative, particularly around the breakeven position for the Preferred Way Forward |  |  |  |  | 0
Delivery planning | Develop a high-level plan which covers the transition of services to the new group infrastructure |  |  |  |  | 0
| Write up of approach to other components of a Management Case as per NHSE requirements change management, governance, benefits realisation etc |  |  |  |  | 0
Authorship | Drafting and developing the five case SOC document |  |  |  |  | 0
| Maintaining alignment with best practice and regulatory requirements (including NHSE requirements and HM Treasury requirements); |  |  |  |  | 0
Totals |  |  |  |  | 0 | 0
Please note that Architectural support and OB Form costing are by others. Bidders are required to allow time for co-ordination with Architectural advisors and OB Form Cost Advisors.