**Appendix D- Project Timetable**

# Project Timetable

1. Table 1 below sets out the main tasks required to produce an assessment of sites in Lambeth suitable for Self Build and custom housebuilding, The study will form part of the evidence base for Lambeth’s forthcoming Site Allocations DPD (SA DPD). It will therefore need to be completed before the Regulation 18 stage of the SA DPD which is due to begin in January 2021.

Table 1- Indicative project timescales

|  |  |  |  |
| --- | --- | --- | --- |
| **Stage** | **Component** | **By whom** | **Indicative timescale** |
| Preparation | Inception meeting  | Appointed consultants and council officers | w/b 5th October 2020 |
| Provide Long list of sites | Council Officers | w/b 5th October 2020 |
| Site assessment | Consultants to review long list of sites | Appointed consultant | w/b 12th October 2020 |
| Consultants to produce short list of sites | Appointed consultant | By 23rd October |
| Detailed site assessment  | Appointed consultant | By 6th November |
| Respond to queues/information requests | Council Officers | Throughout October-November 2020 |
| Draft Report | Draft Final report | Appointed consultant | By 13h November 2020 |
| Review Draft Final Report | Council Officers | By 20th November 2020 |
| Final Report | Final Report  | Appointed consultant | By 4th December 2020 |
| Report presented to council members for comment (if required) | Council Officers | 14th December 2020 |
| Final report signed off by the Council | Council Officers | 11th January 2021 |