Tender Specification: Groundworks to proposed new play area

Tender reference: COS CMP-02

RAF Museum, Cosford

Purpose of the product

To prepare the identified area for the installation of a new play area and picnic area and prepare site compound for the duration of the works, including the duration of the play area/equipment installation.

COVID-19

Due to the current situation regarding COVID-19, the museum is now closed until 1 May, at least. This will be reviewed and monitored in line with Government advice. Tenderers will be notified of any changes.

Constraints

- The site will be open to the public throughout construction

  - 8:00am - 5:30pm working hours

  - 10:00am - 1:00pm peak time for visitors

  - 8:00am - 10:00am Ideal time for deliveries

- The site will be visible to the public

- The site is near to a live airfield and a Foreign Object Debris (FOD) prevention programme needs to be in place throughout the build.

Responsibilities

The appointed individual or company will at all times ensure:

- Compliance with the Health & Safety at Work Act (including risk assessments, method statements, and relevant certification) and be able to show proof if required

- Compliance with the Museum’s Safeguarding Policy and Procedures

- The company will be deemed the Principal Contractor for the playground design and construction

- Compliance with site induction processes and rules

- Provision of required insurance details to comply with the induction process.

- Compliance with all Government recommendations related to COVID-19

The appointed individual or company will also:

- Provide all equipment necessary to carry out the agreed contract

- Show actions to reduce impact on the environment.

- Take into consideration site operations when planning and delivering set tasks

- Liaise daily and provide a weekly briefing of outcomes to the site liaison(s)

Location

The project will be delivered at the RAF Museum in Cosford, West Midlands.

Key dates

Phase 1 – Initial Basework to be completed by 3 July 2020 subject to Government restrictions

- Relocation of picnic area

- Excavation of play area

- Excavation and installation of concrete barriers

- Ground levelling works

Phase 2 – Kompan installation of play equipment 6 July 2020 – 31 July 2020 subject to Government restrictions.

- Fence line and welfare facilities to be retained

Phase 3 – Remedial Works and clearing of site compound 3 August 2020 – 7 August 2020 subject to Government restrictions

- Localised ground levelling works including access to play area gates

- Remove site compound and fencing

- Seeding where required

- Relay block paving

Site information

The RAF Museum is open to the public from 10am – 5pm seven days a week (summer hours), 10am – 4pm (winter hours)

Site access is 8am – 6pm unless a four week’s notice period is provided

All site deliveries must be within site access times avoiding 10am-5pm and 10am-4pm respectively.