Statement of Requirements CONTRACT NO. : PF/3010/2018

(SoRs)

Gender Baselining for the Energy sector in Mexico

Mexico Prosperity Fund Programme 2018-2019

Contents

SUMMARY OF REQUIREMENT	2

INTRODUCTION	2

OBJECTIVE	2

METHODOLOGY	3

OUTPUTS / DELIVERABLES	3

EXPECTED TASKS	4

PROCESS AND TIMEFRAME	5

REPORTING STRUCTURE, LOGISTICS AND OTHER ARRANGEMENTS	7

SKILLS AND COMPETENCES	6

TENDERS/ BIDS PACKAGE	7

ASSESSMENT	8

BUDGET	9

DUTY OF CARE	9

SUMMARY OF REQUIREMENT

- The Foreign and Commonwealth Office (FCO), seeks to appoint one or more Service Supplier(s) (“the Supplier”) for the implementation of the (FY 18-19) Cross Whitehall Prosperity Fund project in Mexico entitled “Gender baselining for the energy sector in Mexico”. The Service Supplier(s) will conduct a two study that will provide baseline information for the delivery of the years 3-5 Energy Strand of the Mexico Prosperity Fund programme.

INTRODUCTION

- In 2015, the UK government’s Strategic Defence and Security Review announced a £1.3billion cross-government Prosperity Fund (PF) to run over five years (2016/17 to 2020/21). Its primary purpose is to promote the economic reform and development needed for growth in partner countries, in accordance with Official Development Assistance (ODA) rules, the International Development Act (2002) and the Gender Equality Act (2014). It will contribute towards meeting the new Sustainable Development Goals. The Fund’s secondary objective is to open up opportunities for which business, including UK businesses, can compete. The UK government is looking to identify and support programmes that meet both the Fund’s primary and secondary objectives.

## The proposed purpose of our Energy programme is to encourage sustainable growth and international investment in the Mexican energy sector, so that the sector further drives national economic growth and development. The programme aims to contribute to the following outcomes:

- Larger pipeline of certified male and female specialists to meet industry demand and a local workforce that is resilient to economic shocks;

- Incorporation of market ready local male and female-owned SMEs in the supply chain of MNCs in the energy sector; and

- Increased levels of technical proficiency amongst regulators and male and female officials that uphold adherence to international standards in the energy sector.

- Please see Annex 1 for additional context of the Prosperity Fund and the Energy sector in Mexico.

## OBJECTIVE

- The British Embassy in Mexico City (“the Authority”) wishes to secure the services of experts to conduct a gender baselining study to provide key information for the delivery of the Energy Strand of the Mexico Prosperity Fund programme. This study aims to provide both a quantitative and qualitative analysis of gender equality in a specific area of the energy sector in Mexico in order to determine potential area of work for the Energy strand of the Mexico Prosperity Fund programme. It also aims to increase awareness and visibility of social inclusion issues in the sector and to promote the work of national and international organisations in tackling the issue. The main objective of this study is:

## Map the current participation of women in the energy sector in the states of Tabasco, Nuevo Leon, Campeche, Veracruz, Jalisco and Sonora, including the identification of barriers to entry and the challenges faced by women, with data disaggregated by level of seniority and sub-sector (Oil & Gas, Electricity, Renewables and Energy Efficiency).

## The service will help to address the lack of gender equality in the energy sector, which has been identified as a key barrier to growth and will thus support the creation of new market opportunities.

## In delivering this project, the Supplier must consult relevant actors and institutions. Some of these actors and institutions include, but are not limited to: SENER (Ministry of Energy); CNH (National Hydrocarbon Commission); CRE (Energy Regulatory Commission); ASEA (National Agency for Safety, Energy and Environment); CENACE (National Energy Control Centre); CONUEE(National Commission for the Efficient Use of Energy); SEMAR (Mexican Navy); STPS (Ministry of Labour and Social Welfare); SEP (Ministry of Education); INMUJERES (National Institute of Women); state governments; and other donors working in this field.

- The Supplier must maintain a focus on data and information relevant to the narrowing of the gender gap in the Mexican energy sector.

## METHODOLOGY

- Interested parties are asked to tender an outline methodology of how they would deliver the above mentioned services, both on a theoretical and practical basis. That may include, but is not limited to: desk and field research, stakeholder consultations in Mexico and UK, draft reports, presentations, etc. The methodology should be accompanied by a detailed budget for the cost of proposed activities and the CVs of the team members that would conduct the work. UK organisations may wish to consider including local experts in their proposed teams.

## The Supplier will be expected to complement and align with existing and past studies or programmes in Mexico relevant to the topic.

## OUTPUTS / DELIVERABLES

## This project will deliver the following outputs:

## One written report mapping the current participation of women in the energy sector in the states of Tabasco, Nuevo Leon, Campeche, Veracruz, Jalisco and Sonora including:

        - Identification of barriers to women taking up employment in the energy sector and challenges to those currently working in the sector in the states mentioned above;

        - Proposal of potential solutions to identified barriers and challenges; and

## Data disaggregated by level of seniority and sub-sector (Oil and Gas, Electricity, Renewables and Energy Efficiency)

  - One presentation of the report findings to relevant stakeholders, including, but not limited to, representatives from Mexican government, the Authority, Mexican and UK private sector and the Partner for the Mexico Prosperity Fund Energy Strand, where applicable. The presentation should be held in Mexico and should include:

    - Presentation of the key findings,

    - A panel discussion with experts,

    - Simultaneous translation as required.

## All written reports and presentations shall be delivered in both English and Spanish.

- The Supplier will be expected to attend fortnightly progress meetings with the Programme Officer in the British Embassy in Mexico, however, suppliers are expected to raise any issues at their earliest opportunity.

## EXPECTED TASKS

## At a minimum, the successful Supplier is expected to carry out the following tasks for the delivery of this project:

Tasks for output 1:

  - Desk research to gather required information.

  - Consultation with international and national actors and institutions (see paragraph 7).

  - Identification of barriers to women taking up employment in the energy sector in Tabasco, Nuevo Leon, Campeche, Veracruz, Jalisco and Sonora.

  - Identification of challenges to women currently employed in energy in Tabasco, Nuevo Leon, Campeche, Veracruz, Jalisco and Sonora.

  - Proposal of potential solutions to barriers and challenges identified.

  - Coordination with international donors (eg. GIZ – Hoja de Ruta para la Transición Energética)’.

  - Delivery of Outline report to Authority by 30 November 2018.

  - Delivery of draft report to Authority by 15 February 2019.

  - Delivery of final report

Tasks for Output 2:

  - Evaluation and suggestion of a suitable expert(s) to deliver the presentation suggestion of potential subject matter experts or stakeholders for panel discussion, for final selection by the Authority.

  - Design of work plan (including a communication strategy) and organisation of presentation in close consultation with the Authority.

  - Suggestion of list of participants and attendees to be approved by the Authority.

  - Suggestion of venue, catering, and any other services necessary for the delivery of the presentations (eg. Translation, sound, video, projector, etc) for final approval by the Authority.

  - Invitation, follow up and confirmation of attendance of speakers and participants.

  - Invitation, follow up and confirmation of attendees.

  - Final delivery of the presentation, with agreed input from the Authority.

## PROCESS AND TIMEFRAME

Key dates

| ITT to prospective Organisations |  | Tuesday 10th October 2018 |
| --- | --- | --- |
| Last day of questions from bidders on the ITT |  | Monday 22nd October 2018 at 12:00 BST |
| ITT response |  | Monday 5th November 2018 |
| Contract Award |  | w/c 12 November 2018 |
| Output 1 | Milestone 1: Delivery of Outline Report | 14 December 2018 |
| Output 1 | Milestone 2: Delivery of Draft Report | 15 February 2019 |
| Output 1 | Milestone 3: Delivery of Final Report | 15 March 2019 |
| Output 2 | Milestone 4: Delivery of presentation | 15 March 2019 |
| Subject to previous agreement between the Embassy and the supplier, dates for delivering outputs might change. |  |  |

- A project kick-off workshop will be held after signing the contract with the Authority which will be used to establish a shared understanding of the project goals and methodology and clarify key knowledge gaps. This should result in updated work-plan within one week of this meeting being held. The approval of this updated work plan by the Authority will provide the basis for the commencement of the activities agreed in said work plan and their subsequent payment.

## MONITORING, REPORTING, EVALUATION AND LEARNING (MREL)

- The Authority will require successful suppliers to engage constructively with contractor(s) appointed to deliver the Cross Whitehall Prosperity Fund Monitoring, Reporting, Evaluation and Learning (MREL) contract to ensure data flows and evaluations are captured effectively.

## SKILLS AND COMPETENCES

## The Supplier(s) will have to demonstrate knowledge or capability in:

## Strong management and reporting skills, knowledge and experience of handling ODA funds, high levels of customer engagement, responsiveness, accountability, service delivery and delivery of value for money, as well as effective mechanisms for all aspects of management (including both international and local staff) including dealing with poor performance;

## Ability to provide operational support services overseas including local procurement of accommodation, material and services; experience of recruiting and managing local staff (including interpreters) and ensuring that they, and any related equipment is safely operated, maintained and accounted for; and the ability to demonstrate appropriate cultural awareness, sensitivity and a partnership approach, adapting concepts and materials to local needs and audiences;

## Mainstreaming social inclusion throughout the project cycle – i.e. to recognise opportunities to address issues such as gender inequality and supporting women’s economic empowerment, or at a very minimum ensuring that social inequalities are not exacerbated;

## A multidisciplinary approach to ensure wider perspectives are taken into account while carrying out the analysis and to determine further business opportunities, including as a minimum, a sector specialist, a sector-specific social development expert and a political economist;

## Ability to collaborate effectively with UK and overseas governments and local partners in support of the Sustainable Development Goals;

## Ability to work in English and Spanish;

## The energy sector in Mexico and the current economic and political environment;

## Gender studies, gender issues and baselining in labour markets and workforce;

## Applying and integrating gender and social analysis and advice across all of the above to comply with the Gender Equality Act and support good development practice;

## Conducting research, analysing data, developing innovative policy proposals and publishing comprehensive reports combined with very good communication and presentation skills;

## Working with the Authority and/or other bilateral and multilateral organisations as well as government, civil society and private sector interlocutors;

## Existing, or where not existing, the ability to develop, active partnerships with stakeholders in order to successfully carry out the proposed programme; and

## Supporting collaborative partnerships to encourage innovation, capacity-building, and technology and knowledge transfer.

## REPORTING STRUCTURE, LOGISTICS AND OTHER ARRANGEMENTS

## The Supplier(s) will assign a member of staff who will report to the Authority’s Programme Officer and lead the day to day delivery of the project. The Supplier(s) will also appoint a member of staff to liaise with the Authority’s Programme Manager for any contract management issues.

## The Supplier will work independently in setting up the meetings with key stakeholders, arranging transport, agenda, programmes, etc. However, the Authority reserves the right to attend all meetings and events relevant to this project, subject to the Authority’s staff availability. The Supplier must therefore inform the Authority of all events and meetings relevant to this project in a timely manner. Where appropriate, the Authority’s may assist in accessing government agencies or other key senior stakeholders if this should prove necessary.

## TENDERS/ BIDS PACKAGE

## Tenders/bids should include:

- A cover letter introducing the Supplier and how the skills and competencies described above are met, with concrete examples.

- A 6-8 page outline of the proposed review process including:

  - Proposed outline methodology

  - Management arrangements set out in an organogram with clear reporting lines, outline of responsibilities within the team and detail of how much time each team member will provide to the programme.

  - Timeline / Project plan for the delivery of the project

- A one-page budget covering all major costs (See ATT5 Schedule of Prices and Rates):

- Researcher fees.

- Reimbursable costs envisaged

- A 1-page CV for each team member

## ASSESSMENT

## The tender process will be conducted in a manner that ensures tenders are evaluated fairly to ascertain the Most Economically Advantageous Tender (MEAT) from the point of view of the purchasing Authority.

Evaluation Criteria for selection will be based on quality, technical and commercial supports as follow:

- Methodology and Project Management

- Expertise

- Risk Management

- Project team / Resource Plan

- Value for money

- Cost competitiveness in achieving the volume and quality of activities and outputs that will deliver the best results and outcomes anticipated, including activity costs and administrative fees. The successful bidder undertakes to make all reasonable efforts to ensure that all goods and Services purchased in support of this Contract are purchased at the best possible market price, in line with the Authority’s requirements.

For detailed information in this section see Attachment 2 Information Required from Tenderers

## BUDGET

## The maximum budget for the service, covered under these terms of reference, will be no more than £24,900

## The supplier will propose the overall budget for this work which must be inclusive of all applicable taxes, overheads and logistical costs including, but not limited to, travel, venue, catering, translation etc. Bidders are expected to show VfM and not reach the budget ceiling if costs can be lower. Payment will be made in arrears and in two parts:

## 30% upon successful achievement of Milestone 1; and

## 70% upon successful achievement of Milestone 4.

## Acceptance criteria for the successful delivery of outputs and achievement of milestones will be agreed during the kick-off meeting.

## DUTY OF CARE

## The Supplier is responsible for the safety and well-being of their Personnel and Third Parties affected by their activities under this Contract, including appropriate security arrangements. They will also be responsible for the provision of suitable security arrangements for their domestic and business property.

## The Supplier is responsible for ensuring appropriate safety and security briefings for all of their Personnel working under this Contract and ensuring that their Personnel register and receive briefing as outlined above. Travel advice is also available on the FCO website and the implementing agency must ensure they (and their Personnel) are up to date with the latest position.

## Service Suppliers must develop their Tender on the basis of being fully responsible for Duty of Care. They must confirm in their Tender that:

## They fully accept responsibility for Security and Duty of Care.

## They understand the potential risks and have the knowledge and experience to develop an effective risk plan.

## They have the capability to manage their Duty of Care responsibilities throughout the life of the contract.

## Acceptance of responsibility must be supported with evidence of capability (no more than two pages and the FCO reserves the right to clarify any aspect of this evidence).

## In providing evidence Suppliers should consider the following questions:

## Have you completed an initial assessment of potential risks that demonstrates your knowledge and understanding, and are you satisfied that you understand the risk management implications (not solely relying on information provided by the FCO)?

## Have you prepared an outline plan that you consider appropriate to manage these risks at this stage (or will you do so if you are awarded the contract) and are you confident/comfortable that you can implement this effectively?

## Have you ensured or will you ensure that your staff are appropriately trained (including specialist training where required) before they are deployed and will you ensure that on-going training is provided where necessary?

## Have you an appropriate mechanism in place to monitor risk on a live / on-going basis (or will you put one in place if you are awarded the contract)?

## Have you ensured or will you ensure that your staff are provided with and have access to suitable equipment and will you ensure that this is reviewed and provided on an on-going basis?

## Have you appropriate systems in place to manage an emergency / incident if one arises?

## Acceptance of responsibility must be supported with evidence of capability (no more than two pages and the FCO reserves the right to clarify any aspect of this evidence).

## In providing evidence Suppliers should consider the following questions:

## Have you completed an initial assessment of potential risks that demonstrates your knowledge and understanding, and are you satisfied that you understand the risk management implications (not solely relying on information provided by the FCO)?

## Have you prepared an outline plan that you consider appropriate to manage these risks at this stage (or will you do so if you are awarded the contract) and are you confident/comfortable that you can implement this effectively?

## Have you ensured or will you ensure that your staff are appropriately trained (including specialist training where required) before they are deployed and will you ensure that on-going training is provided where necessary?

## Have you an appropriate mechanism in place to monitor risk on a live / on-going basis (or will you put one in place if you are awarded the contract)?

## Have you ensured or will you ensure that your staff are provided with and have access to suitable equipment and will you ensure that this is reviewed and provided on an on-going basis?

## Have you appropriate systems in place to manage an emergency / incident if one arises?

ANNEX 1

Prosperity Fund

- The Prosperity Fund supports high impact programmes across high opportunity countries, regions and sectors. The Fund focuses on ODA eligible countries where the development challenges remain significant, and which at the same time are important for global and UK prosperity. This is based on economic analysis and is kept under review.

## The Mexico programme is being developed to support the overall environment for economic development and inclusive growth – e.g. policy development and strategy, strengthening the environment for business, anti-corruption, trade and regulatory reform. It also has to meaningfully consider the impact on reducing gender inequality and how to engage and harness the potential for women’s economic empowerment. As a minimum the programme must ensure it does no harm and does not worsen gender discrimination. Through targeting niche interventions, the programme aims to complement the work of the Mexican government and of other donors operating in the country in the above sectors.

- The Prosperity Fund programme in Mexico is focused on overcoming identified constraints to economic development where the UK has a comparative advantage. Sectors include Energy, Future Cities, Financial Services and Anticorruption and Rule of Law.

Gender and Energy

- Our capacity building work will be approached from a gender-sensitive angle and will look to increase female representation within the energy sector workforce. Other projects in Latin-America have demonstrated success by training women as technicians for small scale PV projects, facilitating their taking part in non-traditional productive activities and thus increasing their household income. Our programme will support the training of women in these non-traditional sectors to empower them to pursue economic opportunities in this growing and lucrative sector. We see this as an opening for women in a sector in which they have historically been absent and who can therefore lead the path to gender equality in the energy sector. A country’s competitiveness largely depends on the skills, education and productivity of its workforce.  Women represent half of this potential talent and therefore, through the energy programme, we intend to help Mexico capitalise on this talent base striving for gender equality as part of the wider objective to strengthen the energy sector in Mexico. The operation and maintenance of energy technologies has traditionally been a male dominated sector, however, studies have shown that when women are trained in the operation and maintenance of energy technologies, the equipment is likely to be in a better state than when only serviced by men.

- An open market that promotes fair competition is necessary to attract the entry of new players which will increase production, boost economic growth. Mexicans that are equipped with the adequate knowledge and skills will be better placed to take advantage of the new jobs over foreign labour, thus increasing their income and access to basic services. The acquisition of transferable skills will not only make them more attractive to international companies but will also increase their resilience against economic shocks or changes in industry direction (in the renewables, low carbon sectors). Negative social and environmental impacts directly affect local communities and their quality of life. Energy projects that consider social and environmental impacts will set higher standards of living for local communities, helping to reduce poverty levels.

- Support in the implementation of regulation and policy will reduce energy prices, increase oil and gas production, improve regulatory practice, increase access to sustainable energy and encourage the adoption of energy planning strategies. The resulting reduction in energy prices from successful implementation of the reform will boost industrial productivity. An increase in oil and gas production will generate higher oil revenues which can be directed to development programmes (e.g. education and investigation). Increased access to affordable energy services will reduce the number of households that live in energy poverty and lower levels of energy poverty will positively impact on national poverty levels. Reduction in energy prices should also benefit MSMEs who are particularly affected by high energy prices – this will also benefit large numbers of women as many MSMEs are owned and run by women in Mexico. Our programme will not only support the growth of renewable energy, but will also incentivise energy efficiency policies that will help these SMEs to become more productive and profitable. Energy efficiency measures will help reduce energy costs thus liberating income for productive activities such as expansion or diversification. According to the OECD and other international organizations such as the International Energy Agency, following an increase in income women are more likely to make sustainable energy decisions for their households.

“Guia sobre genero y energía”, Latin American Energy Organization (OLADE), 2015, http://www.energia.org/cms/wp-content/uploads/2015/04/08.-Guia-sobre-genero-y-energia.pdf

“Guia sobre genero y energía”, Latin American Energy Organization (OLADE), 2015, http://www.energia.org/cms/wp-content/uploads/2015/04/08.-Guia-sobre-genero-y-energia.pdf

“Guía sobre genero y energía”, Latin American Energy Organization (OLADE), 2015, http://www.energia.org/cms/wp-content/uploads/2015/04/08.-Guia-sobre-genero-y-energia.pdf