## Sheet1
1 WREN ST, BURNLEY, BB12 6QG
Please note that the numbers in the left hand column relate to the specification where applicable. The specification should be used for guidance purposes, any similar or equal alternative will be considered. Any variation from the specification should be discussed with the technical officer on site unless otherwise stated in the schedule of works.
Contractors are advised to visit the site prior to submitting their price. Visits to be arranged with the Technical Officer
Contractors are required to supply a break-down of their price on the following sheet. Prices will not be accepted without a break-down.
Contractors are required to arrange for water mains to be connected with the necessary utility companies.
Please note that penalty clauses are now in place to prevent the contact running over the allocated time.
The properties are to be scaffolded front and back with suitably spaced lifts, fully boarded with necessary handrails, toe boards and access points. Where scaffolding is deemed to be unsafe or inappropriate for the required use, work will be stopped until the scaffolding is made safe at the expense of the main contractor.
Means of escape windows are to be fitted as shown on the drawings.
Contractors are advise to allow for thorough cleaning of the property on completion. If a suitable standard of cleaning is not achieved, an independent cleaning contractor will be appointed by the client at the main contractors expense
Contactors are advised that the project will be carried out under a JCT MINOR WORKS contract 2007 and as such liquidated damages are in place.
Item Number | Description | Estimated Cost
| ROOF | £
Check the slate the roof to the front and rear elevations, replace or re-fit any slipped or missing slates as necessary. If any issues of concern are detected consult with the Technical Officer.
Remove all pointing from the ridge tiles and re-bed and repoint.
Check the chimney and repair, replace and seal with a suitable sealant as necessary.
Recap chimney and fit cowl.
1.1.6 | Hack out and repoint the chimney.
1.1.4 | Build up fire stop wall in the loft where / if necessary.
1.1.5 | Replace the gutter to the rear using a PVC equivalent with a matching profile. Allow for additional fixing brackets where necessary. Fit a rain water pipe.
FRONT ELEVATION
2.1.2 | Patch point where necessary to match existing, using a 1:1:6 (cement, lime, sand) mix. To be carried out using scaffolding if necessary.
2.1.3 | Apply a minimum of 2 coats of silicone water seal to the wall. Ensure all windows / doors etc. are protected and suitably cleaned after completion.
The jambs, lintle and brickwork over the first floor window to the master bedroom (to the right side as you look at the property) appear to have moved; take out and reset stone surrounds to window and tie to inner leaf, rebuild stone above head.
2.1.5 | Replace the windows using UPVC frames with a 'Grey' effect outside, white inside. Allow for window linings. Fit escape windows to the first floor with suitable restrictors.
2.1.6.1 | Fit a new Composite door & casing with multi-point locking with 'Grey' effect outside, white inside (allow for linings). Style to be agreed with Technical Officer.
GABLE & REAR ELEVATION
2.1.2 | Patch point where necessary to match existing, using a 1:1:6 (cement, lime, sand) mix. To be carried out using scaffolding if necessary.
2.1.3 | Apply a minimum of 2 coats of silicone water seal to the wall. Ensure all windows / doors etc. are protected and suitably cleaned after completion.
2.1.5 | Replace the windows using UPVC frames with a 'Grey' effect outside, white inside. Allow for window linings. Fit escape windows to the first floor with suitable restrictors.
2.1.6.1 | Fit a new Composite door (with glazing in the top half) & casing with multi-point locking with 'Grey' effect finish to match windows, allow for linings. (Rock door or similar)
2.1.7 | Renew all soil / waste pipes to the property using black UPVC pipes. Allow for all necessary clips / fittings, i.e. rodding eyes etc.
REAR YARD
Remove / clear all rubbish, debris and vegetation and cart away.
Check if the water main to the property has been replaced and report back to the Technical Officer.
Check drains are to building standards and not blocked; clear if necessary and ensure water drains freely.
3.1.2 / 3.1.3 | Where the steps are to the back street, cut- througe the concrete floor (across to the party wall) and dig out and step down to a more suitable level in relation to the back door step and drain. Renew the yard drain if necessary and renew the yard surface using concrete flags. Be mindful of the DPC.
Power wash the remaining concrete yard floor.
Retain the existing timber fence on top of the wall; repair as necessary.
3.1.5 | Knock off any loose render and re-render the yard walls, both inside the yard and on the back street; allow for all necessary angle / stop beads and bell-cast moulds.
3.1.6 | Stone paint the yard wall render with at least 2 coats of masonary paint.
3.1.7 | Fit a good quality new yard gate (level with yard wall / fence height) and paint / stain / treat.
GENERAL INTERNAL WORKS
4.0.0 | REMOVAL / DISPOSAL
4.0.1 | Ceilings throughout the property.
Plaster from all walls throughout the property.
4.0.2 | Redundant plumbing throughout the property.
4.0.3 | Redundant electrics throughout the property.
4.0.4 | Previous insulation material
4.1.1 | DPC
Provide a DPC to all ground floor walls (ALLOW FOR WATERPROOF RENDER / TANKING UP TO 1200MM BEFORE DRY LINING).
4.1.2 | Provide a full new electrical installation to the property. Allow for a minimum of 3 double sockets in each room, extractor fans to the kitchens and bathroom, hard wired heat and smoke detectors where shown on the drawings. Allow for 1 security light with PIR sensor at the rear and separate switch within the property. All necessary certification to be provided on completion.
On completion fit LED light bulbs to all rooms.
4.1.3 | Supply and fit a basic hard wired alarm system consisting of a minimum of key pad control, 2 X PIR's, door sensors to the front and rear doors and bell box to the external wall.
4.1.4 | Provide a new hot and cold water supply to the kitchen & bathroom.
4.1.4 | Provide a new heating system allowing for 1 radiator to each room (possibly 2 in the lounge or dining area if necessary because of the open stairs and 2 external walls) and room thermostat (see spec for boiler; should have a minimum 5 year guarantee.)
4.1.8 | Render all walls with a scratch coat render prior to dry lining. Allow for waterproofing / salt resisting additives.
4.2.3 | All walls and ceilings are to be skimmed to a smooth finish.
4.2.7 / 4.2.8 | Replace the skirting's, architraves and plinth blocks throughout the property in wood.
4.2.9 | Fit new doors throughout the property complete with door furniture.
4.3.0 | Provide door stops to all doors opening against internal walls.
4.3.7 | Decorate all walls and ceilings using brilliant white matt emulsion.
Woodwork to be finished in white gloss.
ENTRANCE PORCH
4.1.8 / 4.1.9.4 / 4.2.3 | Dry-line the walls and skim to a smooth finish. Allow for the replacement / alteration of the door linings as necessary.
4.2.1 / 4.2.3 | Over board and skim ceiling and skim to smooth finish.
4.2.7 / 4.2.8 | Replace all skirting and architraves in wood.
4.2.9 | Fit a new internal door and casing.
GROUND FLOOR DINING ROOM & LOUNGE
Re-configure layout as per drawings (move the wall between the lounge and kitchen).
Change beam as per drawing.
4.1.8 / 4.1.9.4 / 4.2.3 | Dry-line the walls using insulated plasterboard (Thermaline Super 50mm) to the external walls and regular 12.5mm plasterboard to the internal walls. Skim to a smooth finish. Allow for the replacement / alteration of the window linings and sill boards as necessary.
4.2.1 / 4.2.3 | Counter batten and board the ceiling and skim to smooth finish
Change the bottom of the stairs, as per the drawings to create a little more space.
4.1.7 | Remove the existing fire surround and hearth. Fit a small vent to the fireplace opening, sufficient for suitable ventilation.
4.3.8 | Remove the existing meter cupboard (if necessary) and construct a new meter cupboard with suitable catches and door handles.
4.2.4 | Possibly a solid floor (laminate down) but if not replace the floorboards where necessary.
4.2.7 / 4.2.8 | Replace all skirting and architraves (in wood).
4.2.9 | Fit new internal doors and casings.
4.3.0 | Fit a door stop.
KITCHEN
4.1.8 / 4.1.9.4 / 4.2.3 | Dry-line the walls using insulated plasterboard (Thermaline Super 50mm) to the external walls and regular 12.5mm plasterboard to the internal walls. Skim to a smooth finish. Allow for the replacement / alteration of the window linings and sill boards as necessary.
4.2.1 / 4.2.3 | Renew the ceiling, counter batten, plasterboard and skim to a smooth finish. Ensure insulation is installed above.
4.3.4 | Fit new kitchen units as shown on the drawing (discuss with Technical Officer). Units to be 'Greenwich Gloss Dove Grey with brushed steel handles and white or wood effect worktop'.
Allow for built in electric cooker and gas hob.
4.3.5 | Provide a minimum of 3 rows (300mm) of tiles to the rear of all work surfaces and behind the cooker position tile the area from the worktop to the extractor hood, seal tiles to worktop. Ensure all walls are sealed with 'Poly-bond' prior to applying adhesive. Allow for white brick effect tiles.
Install plumbing for washing machine.
Fit an extractor fan as shown on the drawings (ducting through the wall).
4.2.7 / 4.2.8 | Replace all skirting and architraves (In wood).
4.2.5 | Lay a self levelling LATEX floor screed (if necessary) to a smooth level finish in preparation for vinyl floor covering.
STAIRS & FIRST FLOOR LANDING
Change the steps at the bottom of the stairs as per drawings.
As per the drawings, raise the height of the bulkhead by 150mm to reduce the risk of hitting your head on it.
4.1.8 / 4.1.9.4 / 4.2.3 | Dry-line the walls using insulated plasterboard (Thermaline Super 50mm) if possible to the external walls and soundblock boards to the party walls. Skim to a smooth finish.
4.3.1 | Handrails / balustrade covering the full flight of the stairs.
LOFT HATCH / ACCESS
4.3.2 / 4.3.3 | Renew & relocate the loft hatch to a suitable location. Install a minimum of 270mm of mineral wool insulation to the loft space.
FIRST FLOOR
FRONT BEDROOM (Largest)
4.1.8 / 4.1.9.4 / 4.2.3 | Dry-line the walls using insulated plasterboard, Thermaline Super 50mm to the external walls and regular 12.5mm plasterboard to the internal walls. Skim to a smooth finish. Allow for the replacement / alteration of the window linings and sill boards as necessary.
4.2.1 / 4.2.3 | Counter batten and board the ceiling and skim to smooth finish.
4.2.4 | Replace the floorboards where / if necessary.
Check the condition of the floor joists and boards and if any issues report the findings to the council Technical Officer.
4.2.9 | Fit a new internal door and casings.
4.2.7 / 4.2.8 | Replace all skirting and architraves.
4.3.0 | Fit door stop if necessary.
FRONT BEDROOM (Smallest)
Move the wall between the bedroom and bathroom as per the drawings.
4.1.8 / 4.1.9.4 / 4.2.3 | Dry-line the walls using insulated plasterboard, Thermaline Super 50mm to the external walls, soundblock boards to the party walls and regular 12.5mm plasterboard to the internal walls. Allow for installing sound insulation quilt between the bedroom and bathroom studs. Skim to a smooth finish. Allow for the replacement / alteration of the window linings and sill boards as necessary.
4.2.1 / 4.2.3 | Counter batten and board the ceiling and skim to smooth finish.
4.2.4 | Replace the floorboards where / if necessary.
Check the condition of the floor joists and boards and if any issues report the findings to the council Technical Officer.
4.2.9 | Fit a new internal door and casings.
4.2.7 / 4.2.8 | Replace all skirting and architraves.
4.3.0 | Fit door stop if necessary.
REAR BEDROOM
4.1.8 / 4.1.9.4 / 4.2.3 | Dry-line the walls using insulated plasterboard ( Thermaline Super 50mm ) to the external walls and regular 12.5mm plasterboard to the internal walls. Skim to a smooth finish. Allow for the replacement / alteration of the window linings and sill boards as necessary.
4.2.1 / 4.2.3 | Counter batten and board the ceiling and skim to smooth finish.
4.2.4 | Replace the floorboards where / if necessary.
Check the condition of the floor joists and boards and if any issues report the findings to the council Technical Officer.
4.2.9 | Fit a new internal door (Tongue & Groove style) and casings.
4.2.7 / 4.2.8 | Replace all skirting and architraves.
4.3.0 | Fit door stop if necessary.
BATHROOM
Move the wall between the bedroom and bathroom as per the drawings.
4.1.8 / 4.1.9.4 / 4.2.3 | Dry-line the walls using insulated plasterboard Thermaline Super 50mm to the external walls, soundbloc boards to the party-walls and regular 12.5mm plasterboard to the internal walls. Skim to a smooth finish.
Plasterboard the partition between the bathroom, bedroom and landing. Allow for installing sound insulation quilt between studs.
4.2.1 / 4.2.3 | Counter batten and board the ceiling and skim to smooth finish.
4.2.4 | Replace the floorboards where / if necessary
4.1.4.1 | Install a new bathroom suite as shown on the drawings.
4.1.4.2 | Install a thermostatic mixer shower over the bath.
4.1.5 | Fit a hinged glass shower screen to the bath / wall ensuring a suitable seal along the edge of the bath.
4.3.6 | Provide approx. 12 sq. m of tiling (from bath to ceiling level & tiled splashback to the sink)
4.2.6 | Cover the existing floor with 6mm plywood in preparation for vinyl floor covering.
4.2.9 | Fit a new internal door and casing.
4.2.7 / 4.2.8 | Replace all skirting and architraves.
4.3.0 | Fit door stop if necessary.
Fit a extractor fan as shown on the drawings.(ducting through the wall /roof).
COMPLETION
Ensure all floorboards are securely fixed after being lifted.
Thoroughly clean the property before final handover.
Provide a completion pack containing the correct documentation for Gas / Electric / DPC and Window installations.
Return all keys from sub-contractors.