## Summary
5 Frances St, Truro TR1 3DN
Phil : 07932 093 530 Email : phil@chsurveyors.com
RESOURCE PROJECT, KIMBERLEY LODGE, FALMOUTH
BQ COLLECTION
Summary Page
1 | Preliminaries - Please extend from Preliminaries document
2 | Schedule of Works Pricing Document:
1a. Substructures
2a Frame
2c. Roof
2e. External Walls
2f Windows and External Doors
2g. Internal Walls
2h Internal Doors
3a. Wall Finishes
3b. Floor Finishes
3c. Ceiling Finishes
4a. Fixtures and Fittings
5a Sanitary Installation
5b. Electrical Installation
5c. Mechanical Installation
6a. Site Works
7. Works to existing building
SUB-TOTAL
Overheads & Profit (%)
SUB-TOTAL
| Contingency | 40000 | 40000
TOTAL

## 1a Substructures
Ref |  | Quantity | Unit | Rate | £
D GROUNDWORKS
D20: EXCAVATING AND FILLING
| Excavating; including all earthwork support; including all working space allowances |  |  |  |  | Retaining wall
From reduced levels after demolitions
A | maximum depth not exceeding 0.25m | 18 | m³
B | maximum depth not exceeding 1.00m | 12 | m³
C | E.O Excavation in rock (Approximate) | 3 | m³
Trenches; width not exceeding 0.60m; including all earthwork support; including
D | maximum depth not exceeding 2.00m | 13 | m³
E | E.O Excavation in rock (Approximate) | 2 | m³
Disposal
Excavated material
F | on site; to spoil heaps not exceeding 200m distance | 2 | m³
G | off-site | 41 | m³
H | off-site; (Approximate) | 5 | m³
Filling to excavations
Average thickness n.e. 0.25m
I | selected excavated material | 2 | m³
J | type 1 material; as Architect's Specification | 35 | m³
| Page Nr 1A/1 | Page Total
Ref |  | Quantity | Unit | Rate | £
Surface treatments
Compacting
H | filling; blinding with sand | 139 | m²
J | bottoms of excavations | 139 | m²
Disposal
Surface water
K | generally | 1 | it
Ground water
J | generally | 1 | it
E IN-SITU CONCRETE/LARGE PRECAST CONCRETE
E10 : MIXING/ CASTING/ CURING IN-SITU CONCRETE
Plain in-situ concrete
Fillings
A | to cavity; 200 wide | 15 | m³
Foundations
C | generally in trenches | 7 | m³
Reinforced in-situ concrete
Slabs
E | thickness 150 - 450; to slopes or falls exceeding 15 degrees | 16 | m³
| Page Nr 1A/2 | Page Total
Ref |  | Quantity | Unit | Rate | £
E20 : FORMWORK FOR IN-SITU CONCRETE
Formwork with basic finish at the discretion of the contractor
Sides of foundations
F | plain vertical; height 250 - 500mm | 146 | m
E30 : REINFORCEMENT FOR IN-SITU CONCRETE
Reinforcement; plain round steel, welded; BS 4483
Fabric
A | A393 mesh | 95 | m²
E40 : DESIGNED JOINTS AND DETAILS FOR IN-SITU CONCRETE
Formed Joint
Junction
B | 600mm long H16 dowel with 50/50 embedment as Structural Engineer Drawing 23505/010 | 4 | m
Base Plate
C | 80 x 80 x 6.3 SHS with an 8mm fillet welded 300 x 300 x 10 thick base plate; bolted through 20mm non-shrinkable structural grout with 4nr grade 8.8 M16 threaded rods resin fixed with RAWL R-KEM II or similar approved; as Engineer Drawing 23505/010 | 1 | nr
| Page Nr 1A/3 | Page Total
Ref |  | Quantity | Unit | Rate | £
E41 : WORKED FINISHES/ CUTTING TO IN-SITU CONCRETE
Finishes to in-situ concrete
Power floating
F | width exceeding 300 | 110 | m²
F MASONRY
F10 : BRICK/ BLOCK WALLING
Dense concrete blockwork; 7N trench block as Engineers details
Walls
B | 100 thick | 30 | m²
B | 215 thick | 7 | m²
C | 300 thick | 6 | m²
C | 440 thick | 9 | m²
F30 : ACCESSORIES/ SUNDRY ITEMS FOR BRICK/ BLOCK/ STONE WALLING
Forming cavities
In hollow walls
F | 150 wide | 15 | m²
Dpc
Hyload cavity tray; as Architect's Specification
G | horizontal; exceeding 225 wide | 18 | m²
| Page Nr 1A/4 | Page Total
Ref |  | Quantity | Unit | Rate | £
Weepholes
Weepholes; as Architect's Specification
A | through 100mm blockwork | 79 | nr
Holes through walls
For services
B | 250 x 250 hole through 300 thick cavity wall, including lintols | 5 | nr
J WATERPROOFING
J20 MASTIC ASPHALT TANKING/DAMP PROOF MEMBRANES
Geocomposite Gas Venting Layer
Visqueen Gas Resistant DPC; as Architect's Specification
C | exceeding 300 wide; horizontal; to blinded hardcore | 139 | m²
| Page Nr 1A/5 | Page Total
£
COLLECTION
Page Nr 1A/1
Page Nr 1A/2
Page Nr 1A/3
Page Nr 1A/4
Page Nr 1A/5
TOTAL TO SUMMARY

## 2a Frame
Ref |  | Quantity | Unit | Rate | £
E CONCRETE
E05 INSITU CONCRETE
Grouting with cement mortar; as Architect's Specification
Stanchion bases
A | 25 mm thick | 1 | nr
E42 ACCESSORIES CAST INTO INSITU CONCRETE
Foundation bolt boxes
Temporary plywood; for group of 4 nr bolts
B | 75 x 75 x 150 mm; (Approximate) | 1 | nr
Foundation bolts and nuts
Black hexagon
C | 20 mm diameter x 180 mm long; (Approximate) | 4 | nr
G STRUCTURAL/CARCASSING METAL/TIMBER
G10 STRUCTURAL STEEL FRAMING
Framing, fabrication; weldable steel; BS EN 10025: 1993 Grade S355JR; hot rolled structural steel sections; welded fabrication; as Engineer's Drawings and Specification
Columns
D | weight not exceeding 40 kg/m | 0.91451 | t
Beams
E | weight not exceeding 40 kg/m | 0.11123 | t
Page Total
Ref |  | Quantity | Unit | Rate | £
A | Fittings | 0.153 | t
Framing erection
B | Permanent erection on site | 1.18 | t
Surface preparation
At works
C | blast cleaning | 34 | m2
D | touch up primer and one coat of two pack epoxy zinc phosphate primer | 34 | m2
On site
E | intumescent paint fire protection (60) minutes; spray applied; as Architect's Specification | 34 | m2
G12 ISOLATED STRUCTURAL METAL MEMBERS
Fabricated weldable steel; hot rolled sections; welded and bolted fabrication; galvanised coated shop and site bolts; Contractor designed steelwork connections; as Engineer's Drawings and Specification
Beams
F | weight not exceeding 40 kg/m | 0.34161 | t
G | Fittings | 0.051 | t
Framing erection
H | Permanent erection on site | 0.39 | t
Page Total
Ref |  | Quantity | Unit | Rate | £
Surface preparation
At works
A | blast cleaning | 10 | m2
B | touch up primer and one coat of two pack epoxy zinc phosphate primer | 10 | m2
On site
C | intumescent paint fire protection (60) minutes; spray applied; as Architect's Specification | 10 | m2
F31 PRECAST CONCRETE SILLS / LINTELS / COPINGS / FEATURES
Precast concrete units; prestressed concrete lintels; building into existing masonry; bedding in cement/lime/sand mortar (1:3-4); as Engineers Drawings and Specification
Lintels
D | 100 x 215 x 1200 long | 4 | nr
Mass concrete units; GEN3 mass concrete padstone [cast in-situ] in existing masonry; as Engineers Drawings and Specification
Padstones
E | 300 x 200 x 200 | 7 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
G20 CARPENTRY / TIMBER FRAMING / FIRST FIXING
Sawn softwood; strength class C246; pressure impregnated with preservative
Framed supports; as Engineer's Drawing and Specification
2 no 50 x 175 C24 timbers bolted together
A | including all fixings; within existing building | 10 | m
M SURFACE FINISHES
M60 PAINTING/CLEAR FINISHING
Touch up primer; one undercoat and two finishing coats of gloss paint; on iron or steel surfaces; as Architect's Specification
Structural steelwork
B | over 300 mm girth (Approximate) | 10 | m2
Page Total
COLLECTION
Page Nr 2A/1
Page Nr 2A/2
Page Nr 2A/3
Page Nr 2A/4
TOTAL TO SUMMARY

## 2c Roof
Ref |  | Quantity | Unit | Rate | £
H CLADDING / COVERING
H20 RIGID SHEET CLADDING
H31 METAL PROFILED / FLAT SHEET CLADDING / COVERING
Warm Flat Roof (PIR); single ply low pitch 15 degrees; as Architect and Manufacturer Specification
Roof coverings
A | full composite system | 61 | m²
Extra over for
B | verge detail and soffit | 24 | m
C | raking cutting | 24 | m
D | ridge detail | 13 | m
E | eaves detail including ventilated filler block | 13 | m
Warm Flat Roof (PIR); single ply flat roof; as Architect and Manufacturer Specification
Roof coverings
F | full composite system | 92 | m²
Extra over for
G | abutment to masonry | 36 | m
H | edge detail including all formed gutters | 51 | m
I | abutment to 750 x 750 rooflights | 3 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
R DISPOSAL SYSTEMS
R10 RAINWATER PIPEWORK / GUTTERS
Pipework; as Architect Specification
Pipes
A | fixing to masonry | 16 | m
B | Extra for offsets; as drawing | 10 | Nr
C | Extra for connectins to gullies | 6 | Nr
Gutters; as Architect Specification
Gutters
D | fixing to timber | 14 | m
E | Ends | 4 | Nr
G | Outlets | 2 | Nr
Page Total
£
COLLECTION
Page Nr 2C/1
Page Nr 2C/2
TOTAL TO SUMMARY

## 2e External Walls
Ref |  | Quantity | Unit | Rate | £
E IN SITU CONCRETE / LARGE PRECAST CONCRETE
E10 MIXING / CASTING / CURING IN-SITU CONCRETE
Plain concrete; as Engineer's Specification
Filling hollow walls
A | not exceeding 150 thick | 4 | m3
Grouting; as Engineer's Specification
Column bases
B | 150 to 450 thick | 1 | m3
F MASONRY
F10 BRICK / BLOCK WALLING
Dense concrete blockwork (7.2N/mm2); cement/sand mortar (1:3-4); as Architect's Specification
Walls
C | 100mm thick | 314 | m²
D | Extra over for flush pointed and fair faced one side | 163 | m²
F30 ACCESSORIES SUNDRY ITEMS FOR BRICK/BLOCK
Forming cavities
Forming cavities in hollow walls
E | 200 wide; stainless steel wall ties; 900 centres horizontally; 450 centres vertically; 150 thick insulation; plastic insulation retaining discs; as Architect's Drawings and Specification | 180 | m²
Page Total
Ref |  | Quantity | Unit | Rate | £
Damp proof courses; minimum 100 laps; bedding in cement/sand mortar (1:3-4); as Architects Specification
On surfaces
A | over 225 wide; vertical | 71 | m²
B | over 225 wide; horizontal | 64 | m²
Proprietary items; Cavity tray; bedding in cement/sand mortar (1:3-4); as Architects Specification
On surfaces
C | over 225 wide; horizontal | 38 | m²
Proprietary items; Furfix wall starter; as Architects Specification
On surfaces
D | vertical; to existing stonework | 10 | m
Proprietary items; weep ventilators; building into 100 thick blockwork; as Architects Specification
Weep ventilators
E | generally | 74 | nr
Proprietary items; combined DPC and insulated cavity closers; as Architects Specification
On surfaces
F | 45 wide; horizontal | 150 | m
Page Total
Ref |  | Quantity | Unit | Rate | £
Proprietary items; stainless steel frame ties, including isopads; fixed to steelwork; as Architects Specification
Frame ties
A | fixing to steel | 14 | nr
Proprietary items; galvanised lateral restraint straps; holed for fixings; as Architects Specification
Straps; fixing to masonry
B | 30 x 5 x 1500; bent x 1 | 86 | nr
F31 PRECAST CONCRETE SILLS / LINTELS / COPINGS / FEATURES
Precast concrete units; prestressed concrete lintels; building into blockwork; bedding in cement/lime/sand mortar (1:3-4); as Structural Engineer Specification
Lintels
C | 100 x 65 x 900 long | 6 | nr
D | 100 x 65 x 1200 long | 8 | nr
E | 100 x 65 x 1500 long | 7 | nr
Precast concrete units; bedding and pointing); as Structural Engineer Specification
Padstones
F | 400 x 100 x 215 | 7 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
H CLADDING / COVERING
H21 TIMBER WEATHERBOARDING - EXTERNALLY
Natural Larch Shingle; 200 x 300 shingles; on and including 25 x 50mm horizontal battens at 200centres, Tyvek breather membrane, 25 x 50mm verical battens at 600 centres fixed to masonry; as Architects specification
Walls
A | over 300mm wide; to blockwork | 186 | m²
Finished angles
B | 90 degrees external; matching shingles | 15 | m
C | 90 degrees internal; matching shingles | 6 | m
D | irregular angle external; matching shingles | 3 | m
E | irregular angle internal; matching shingles | 6 | m
Finished junctions
F | vertical to masonry or stonewrok; matching shingles | 11 | m
G | vertical to windows or doors; matching shingles | 124 | m
H | horizontal to windows or doors; matching shingles | 74 | m
I | horizontal at bellcast; matching shingles | 42 | m
J | horizontal at eaves; matching shingles | 45 | m
Page Total
£
COLLECTION
Page Nr 2E/1
Page Nr 2E/2
Page Nr 2E/3
Page Nr 2E/4
TOTAL TO SUMMARY

## 2f Windows and Extl Doors
Ref |  | Quantity | Unit | Rate | £
L WINDOWS / DOORS / STAIRS
L10 WINDOWS / ROOFLIGHTS / SCREENS / LOUVRES
Timber Windows; Rationel Aura; triple glazed units; complete with all ironmongery; pressure impregnated with preservative; factory finished; complete with all necessary flashings, blanking plates, insulation, birdguards, insect mesh, trickle vents, mastic bedding and pointing, etc.; as drawing 0141.a/451,0141.a/452 and Architects Specification
Timber windows; external
A | 800 x 1250 overall; ref W 3-1n | 1 | nr
B | 1120 x 2150 overall; ref W 3-2n | 1 | nr
C | 1000 x 1250 overall; ref W 3-3n | 1 | nr
D | 500 x 500 overall; ref W 3-4n | 1 | nr
E | 500 x 1550 overall; ref W 3-5n | 1 | nr
F | 900 x 1250 overall; ref W 3-6n | 1 | nr
G | 500 x 1550 overall; ref W 3-7n | 1 | nr
H | 5600 x 650 overall; ref W 3-11n | 1 | nr
I | 2500 x 650 overall; ref W 3-12n | 1 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
Timber Windows; Rationel Forma; double glazed units; complete with all ironmongery; pressure impregnated with preservative; factory finished; complete with all necessary flashings, blanking plates, insulation, birdguards, insect mesh, trickle vents, mastic bedding and pointing, etc.; as drawing 0141.a/451,0141.a/452 and Architects Specification
Timber windows; external
A | 1240 x 1100 overall; ref W 1-1n, W 1-2n | 2 | nr
B | 1240 x 1180 overall; ref W 1-3n, W 1-5n | 2 | nr
C | 750 x 520 overall; ref W 1-4n | 1 | nr
D | 1230 x 1180 overall; ref W 1-6n | 1 | nr
Timber windows; internal
E | 750 x 1200 overall; ref Wi 3-1n, Wi 3-2n, Wi 3-3n, Wi 3-4n, Wi 3-6n | 5 | nr
F | 1250 x 1200 overall; ref Wi 3-5n | 1 | nr
Timber Rooflights; Rationel Aura; double glazed units; complete with all ironmongery; pressure impregnated with preservative; factory finished; complete with all necessary flashings, blanking plates, insulation, birdguards, insect mesh, trickle vents, mastic bedding and pointing, etc.; as drawing 0141.a/451,0141.a/452 and Architects Specification
Timber rooflights
G | 600 x 750 overall; ref RL 4-1n | 1 | nr
H | 600 x 750 overall; ref RL 4-2n | 1 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
Timber Rooflights; Rationel Aura; triple glazed units; complete with all ironmongery; pressure impregnated with preservative; factory finished; complete with all necessary flashings, blanking plates, insulation, birdguards, insect mesh, trickle vents, mastic bedding and pointing, etc.; as drawing 0141.a/451,0141.a/452 and Architects Specification
A | 750 x 750 overall; ref RL 3-1n, RL 3-2n, RL 3-3n | 3 | nr
B | 600 x 750 overall; ref RL 4-1n, RL 4-2n | 2 | nr
Timber Rooflights; Rationel Forma; double glazed units; complete with all ironmongery; pressure impregnated with preservative; factory finished; complete with all necessary flashings, blanking plates, insulation, birdguards, insect mesh, trickle vents, mastic bedding and pointing, etc.; as drawing 0141.a/451,0141.a/452 and Architects Specification
Timber rooflights
C | 800 x 1400 overall; ref RL 1-1n | 1 | nr
L20 DOORS / SHUTTERS / HATCHES
Timber external door and frame sets; "Rationel Forma"; door and frame units; double glazed units; complete with all ironmongery and glazing; pressure impregnated with preservative; factory finished; complete with all necessary flashings, blanking plates, insulation, birdguards, insect mesh, trickle vents, mastic bedding and pointing, etc.; as drawing 0141.a/451,0141.a/452 and Architects Specification
Door and frame
D | 960 x 1970 overall; ref D 1-1n | 1 | nr
E | 1020 x 2090 overall; ref D 1-2n | 1 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
Timber external door and frame sets; "Rationel Forma"; door and frame units; triple glazed units; complete with all ironmongery and glazing; pressure impregnated with preservative; factory finished; complete with all necessary flashings, blanking plates, insulation, birdguards, insect mesh, trickle vents, mastic bedding and pointing, etc.; as drawing 0141.a/451,0141.a/452 and Architects Specification
Door and frame
A | 1090 x 2150 overall; ref D 3-1n | 1 | nr
B | 1020 x 2090 overall; ref D 3-2n | 1 | nr
C | 1020 x 2090 overall; ref D 3-3n | 1 | nr
Steel external door and frame sets; door and frame units; complete with all ironmongery; factory finished; complete with all necessary flashings, blanking plates, insulation, birdguards, insect mesh, trickle vents, mastic bedding and pointing, etc.; as drawing 0141.a/451,0141.a/452 and Architects Specification
Door and frame
D | 1440 x 2150 overall; ref D 4-5n | 1 | nr
Bedding and Pointing frames
Pointing metal frames with polysulphide sealant; Adshead Ratcliffe Arbokol AG1 one-part polysulphide sealant; Spec L10.810
E | both sides | 142 | m
Page Total
Ref |  | Quantity | Unit | Rate | £
M SURFACE FINISHES
M60 PAINTING/CLEAR FINISHING
One coat primer; on wood surfaces; as Architect Specification
General surfaces; prior to fixing
A | not exceeding 300mm girth | 107 | m
B | over 300mm girth | 56 | m2
One coat primer; one undercoat and two finishing coats of eggshell paint; on wood surfaces; as Architect Specification
General surfaces
C | not exceeding 300mm girth | 107 | m
D | over 300mm girth | 28 | m2
P BUILDING FABRIC SUNDRIES
P20 UNFRAMED ISOLATED TRIMS/SKIRTINGS/SUNDRY ITEMS
Composite item; as Architect Drawing 0141.a/547
External door threshold detail
E | 1050 wide; including sill, threshold, aco drain, damp proofing; including bedding, pointing, plugging, screwing; pellating, etc. | 4 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
Medium density fibre board; moisture resistant; as Specification
Skirtings, picture rails architraves and the like
A | 18 x 69; pencil rounded x 1; plugging; screwing; pellating | 107 | m
Window boards, nosings, bed moulds and the like; rebated and rounded
B | 25 X 350mm | 70 | m
Page Total
COLLECTION
Page Nr 2F/1
Page Nr 2F/2
Page Nr 2F/3
Page Nr 2F/4
Page Nr 2F/5
Page Nr 2F/6
TOTAL TO SUMMARY

## 2g Internal Walls
Ref |  | Quantity | Unit | Rate | £
E IN SITU CONCRETE / LARGE PRECAST CONCRETE
E10 MIXING / CASTING / CURING IN-SITU CONCRETE
Plain concrete; as Engineer's Specification
Filling hollow walls
A | not exceeding 150 thick | 3 | m3
F MASONRY
F10 BRICK / BLOCK WALLING
Dense concrete blockwork (7.2N/mm2); cement/sand mortar (1:3-4); as Architect's Specification
Walls
B | 100mm thick | 160 | m²
C | Extra over for flush pointed and fair faced one side | 92 | m²
D | Extra over for flush pointed and fair faced both sides | 68 | m²
F30 ACCESSORIES SUNDRY ITEMS FOR BRICK/BLOCK
Forming cavities
Forming cavities in hollow walls
E | 200 wide; stainless steel wall ties; 900 centres horizontally; 450 centres vertically; 150 thick insulation; plastic insulation retaining discs; as Architect's Drawings and Specification | 92 | m²
Page Total
Ref |  | Quantity | Unit | Rate | £
Proprietary items; Furfix wall starter; as Architects Specification
On surfaces
A | vertical; to existing stonework | 8 | m
Proprietary items; galvanised lateral restraint straps; holed for fixings; as Architects Specification
Straps; fixing to masonry
B | 30 x 5 x 1500; bent x 1 | 38 | nr
F31 PRECAST CONCRETE SILLS / LINTELS / COPINGS / FEATURES
Precast concrete units; prestressed concrete lintels; building into blockwork; bedding in cement/lime/sand mortar (1:3-4); as Structural Engineer Specification
Lintels
C | 100 x 65 x 1200 long | 7 | nr
D | 100 x 65 x 1500 long | 8 | nr
Precast concrete units; bedding and pointing; as Structural Engineer Specification
Padstones
E | 440 x 100 x 251 | 3 | nr
Page Total
G STRUCTURAL / CARCASSING METAL / TIMBER
G20 CARPENTRY / TIMBER FRAMING / FIRST FIXING
'Sawn softwood; strength class C24; pressure impregnated with preservative; as Engineer Specification
2nr 47 x 200mm C24 timbers bolted together to form lintel
A | 2100 long | 1 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
COLLECTION
Page Nr 2E/1
Page Nr 2E/2
Page Nr 2E/3
TOTAL TO SUMMARY

## 2h Internal Doors
Ref |  | Quantity | Unit | Rate | £
L WINDOWS / DOORS / STAIRS
L20 DOORS / SHUTTERS / HATCHES
Timber internal door and frame sets; "Eclisse"; single fire-rated pocket door system door and frame units; complete with all ironmongery and glazing; pressure impregnated with preservative; factory finished; as drawing 0141.a/451,0141.a/452 and Architects Specification
Door and frame
A | 1050 x 2090 overall; ref Di 1-1n | 1 | nr
Timber internal door and frame sets; "Classic"; single pocket door system door and frame units; complete with all ironmongery and glazing; pressure impregnated with preservative; factory finished; as drawing 0141.a/451,0141.a/452 and Architects Specification
Door and frame
B | 1040 x 2090 overall; ref Di 3-5n | 1 | nr
Timber internal door and frame sets; "Rationel"; door and frame units; complete with all glazing and glazing beads, etc; pressure impregnated with preservative; factory finished; as drawing 0141.a/451,0141.a/452 and Architects Specification
Door and frame
C | 1020 x 2090 overall; ref Di 1-2n | 1 | nr
D | 1020 x 2090 overall; ref Di 3-1n | 1 | nr
E | 1020 x 2090 overall; ref Di 3-2n | 1 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
A | 1020 x 2090 overall; ref Di 3-3n | 1 | nr
B | 1020 x 2090 overall; ref Di 3-4n | 1 | nr
C | 1020 x 2090 overall; ref Di 3-6n | 1 | nr
D | 1020 x 2090 overall; ref Di 3-7n | 1 | nr
E | 1020 x 2090 overall; ref Di 3-8n | 1 | nr
F | 1020 x 2090 overall; ref Di 3-9n | 1 | nr
G | 1020 x 2090 overall; ref Di 3-10n | 1 | nr
H | 1020 x 2090 overall; ref Di 3-11n | 1 | nr
I | 1020 x 2090 overall; ref Di 3-12n | 1 | nr
J | 1020 x 2090 overall; ref Di 3-13n | 1 | nr
K | 620 x 1190 overall; ref Di 3-14n | 1 | nr
L | 950 x 2040 overall; ref Dt 4-1, Dt 4-2, Dt 4-3, Dt 4-4 | 4 | nr
M SURFACE FINISHES
M60 PAINTING/CLEAR FINISHING
One coat primer; on wood surfaces; as Architect Specification
General surfaces; prior to fixing
M | not exceeding 300mm girth | 218 | m
Page Total
Ref |  | Quantity | Unit | Rate | £
One coat primer; one undercoat and two finishing coats of gloss paint; on wood surfaces; as Architect Specification
General surfaces
A | not exceeding 300mm girth | 218 | m
P BUILDING FABRIC SUNDRIES
P20 UNFRAMED ISOLATED TRIMS / SKIRTINGS / SUNDRY ITEMS
Medium density fibre board; moisture resistant; as Architect Drawing 0141.a/482 and Architect and Manufacturer Specification
Skirtings, picture rails architraves and the like
B | 18 x 69; pencil rounded x 1; plugging; screwing; pellating | 202 | m
B | 67 x 21; plugging; screwing; pellating | 16 | m
P BUILDING FABRIC SUNDRIES
P21 DOORS / WINDOW IRONMONGERY
Ironmongery; as Architect's Specification
Ball bearing hinge
C | 102 x 76 | 23 | pairs
Overhead door closers
D | GEZE TS40000S | 15 | nr
Flush bolts
E | 150 x 19 | 30 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
Door lock
A | lock, key and escutcheon plates; 110 x 19; stainless steel | 3 | nr
B | bathroom turn and release set with hex key overide; stainless steel | 2 | nr
Door latches
C | heavy duty tubular latch; 78mm case; 57mm backset; stainless steel | 15 | nr
Lever handles
D | door handle on rose; 19mm; stainless steel | 30 | nr
Kicking plates
E | 900 x 150 x 1.2; with 8 screw holes; stainless steel | 30 | nr
Name plate; 200 x 150 x 1.2; stainless steel
F | unisex disabled WC symbol; 200 x 150 x 1.2; stainless steel | 2 | nr
G | "Vocal Booth"; 200 x 150 x 1.2; stainless steel | 1 | nr
H | "Recording Room"; 200 x 150 x 1.2; stainless steel | 1 | nr
I | "Recording Control Room"; 200 x 150 x 1.2; stainless steel | 1 | nr
J | Kitchen"; 200 x 150 x 1.2; stainless steel | 1 | nr
K | "Server Room"; 200 x 150 x 1.2; stainless steel | 1 | nr
L | "Radio Control Room"; 200 x 150 x 1.2; stainless steel | 1 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
A | "Radio Studio One"; 200 x 150 x 1.2; stainless steel | 1 | nr
B | "Radio Studio Two"; 200 x 150 x 1.2; stainless steel | 1 | nr
C | "Fire Door Keep Shut"; 75 diameter; stainless steel | 1 | nr
Page Total
£
COLLECTION
Page Nr 2H/1
Page Nr 2H/2
Page Nr 2H/3
Page Nr 2H/4
Page Nr 2H/5
TOTAL TO SUMMARY

## 3a Wall Finishes
Ref |  | Quantity | Unit | Rate | £
M SURFACE FINISHES
M20 PLASTERED / RENDERED / ROUGHCAST COATINGS
Plaster skim; as Architect Specification
Walls
A | over 300 wide; to plasterboard | 16 | m²
M40 STONE / CONCRETE / QUARRY / CERAMIC TILING / MOSAIC
Ceramic Tiling; "H & R Johnson Prismatics Range"; 150 x 150 x 6.5 ceramic wall tiling; fixed square pattern; fixing and grouting with '"Bal-flex" adhesive and "Balgrout" grout; as Architect Specification
Walls
B | over 300 wide; to masonry | 2 | m²
Painting blockwork; Spec M60.113
General surfaces
C | over 300 girth | 402 | m²
Page Total
COLLECTION
Page Nr 3A/1
TOTAL TO SUMMARY

## 3b Floor Finishes
Ref |  | Quantity | Unit | Rate | £
M SURFACE FINISHES
M10 CEMENT: SAND / CONCRETE SCREEDS / TOPPINGS
Screed; 1:4 cement: sand
Floors
A | 70 average thick; to falls and cross falls not exceeding 15 degrees from horizontal | 116 | m²
M40 STONE / CONCRETE / QUARRY / CERAMIC TILING / MOSAIC
Ceramic tiling; high slip resistance; checkered victorian tiles; as Architect Specification
Floors
B | 97 x 97 x 7mm; level or to falls not exceeding 15 degrees from horizontal | 7 | m²
C | Extra for half tile skirting | 12 | m
D | Extra for internal angles to skirting | 8 | nr
E | Extra for external angles to skirting | 4 | nr
F | Extra for ends/ abutments on skirting | 8 | nr
G | Extra for external angles to skirting | 4 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
M42 WOODBLOCK / COMPOSITION BLOCK / MOSAIC PARQUET FLOORING
Engineered wood floor; Oakley Products Decka Plank New Hampshire; as Manufacturer and Architect Specification
Floors
A | 14mm thick; 1900 x 190 boards; including oiled finish; generally | 31 | m²
M50 RUBBER / PLASTICS / CORK / LINO / CARPET TILING / SHEETING
Marmoleum; Forbo Marmoleum Concrete Pine Forest 3750; as Architect Specification
Floors
B | over 300 wide; level or to falls; including latex levelling screed | 9 | m²
Marmoleum; Forbo Marmoleum Concrete Orange Shimmer 3712; as Architect Specification
Floors
C | over 300 wide; level or to falls; including latex levelling screed | 23 | m²
Skirtings
D | 100 high; coved to masonry | 8 | m
Marmoleum; Forbo Marmoleum Concrete Green Shimmer 3736; as Architect Specification
Floors
E | over 300 wide; level or to falls; including latex levelling screed | 28 | m²
Page Total
Ref |  | Quantity | Unit | Rate | £
Carpet tiles; Forbo Tessera Layout and Outline; as Architect Specification
Floors
A | over 300 wide; level or to falls; including latex levelling screed | 51 | m²
Entrance mat; Aluflex JR Brush; UV-Resistant; as Architect and Manufacturer Specification
Floors
B | 1050 x 600; level or to falls; including natural aluminium matwell frame, wire rope, lock, etc. | 2 | nr
P BUILDING FABRIC SUNDRIES
P20 UNFRAMED ISOLATED TRIMS / SKIRTINGS / SUNDRY ITEMS
Aluminium; flooring transition T bar; Schluter RENO-T-AE; as Architect and manufacturer specification
Skirtings, picture rails, architraves and the like
C | 25mm; plugging; screwing; pellating | 1 | m
Hardwood; Beech threshold; standard flat door threshold; as Architect and manufacturer specification
Skirtings, picture rails, architraves and the like
D | 44 deep x 900 wide x 12mm thick; plugging; screwing; pellating | 12 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
Softwood; Redwood pine skirting; Victoria Emporium; Torus moulding; as Architect and manufacturer specification
Skirtings, picture rails, architraves and the like
A | 117 x 21; plugging; screwing; pellating | 22 | m
MDF; bullnose skirting; as Architect specification
Skirtings, picture rails, architraves and the like
B | 96 x 15; plugging; screwing; pellating | 102 | m
Page Total
£
COLLECTION
Page Nr 3B/1
Page Nr 3B/2
Page Nr 3B/3
Page Nr 3B/4
TOTAL TO SUMMARY

## Floor Finishes (SS) (hidden)
Ref |  | Quantity | Unit | Rate | £
M SURFACE FINISHES
M10 CEMENT: SAND / CONCRETE SCREEDS / TOPPINGS
Cement - Sand
Floors
A | 70 average thick; to falls and cross falls not exceeding 15 degrees from horizontal | 110 | m²
Latex screeds; Spec M50.460
Floors
D | generally; level or to falls not exceeding 15 degrees from horizontal |  | m²
Pumaflow floor finish; two coats of Pumaprime SF; Pumaflow, 2mm thick; all in accordance wih manufacturers instructions
Floors
E | generally; level or to falls not exceeding 15 degrees from horizontal |  | m²
M40 STONE / CONCRETE / QUARRY / CERAMIC TILING / MOSAIC
Ceramic tiling; Spec M40.110A
Floors
F | 450 x 450 x 8mm; level or to falls not exceeding 15 degrees from horizontal |  | m²
G | Extra for 100mm high sit on skirting with rounded profile top |  | m
H | Extra for angle/transition strips to matwells carpet tiles and timber flooring |  | m
J | Extra for movement joints |  | m
| Revision 1 (11/1/08) | Page Total
Ref |  | Quantity | Unit | Rate | £
Ceramic Tiling; M40.110B
Floors
A | 300 x 300 x 8mm; level or to falls not exceeding 15 degrees from horizontal |  | m²
B | Extra for movement points |  | m
C | Extra for 450 x 100m skirting tiles to match floor tiles |  | m
Ceramic Tiling; Spec M40.110C
Floors
D | 150 x 150 x 8mm; to falls and cross falls not exceeding 15 degrees from horizontal |  | m²
E | Extra over for 250 x 125 x 25mm Ivory Drain ceramic floor tile ref DA/4200/IVORY |  | m²
F | Extra for 450 x 150m skirting tiles to match floor tiles |  | m
G | 150 x 150 x 8mm; level or to falls not exceeding 15 degrees from horizontal |  | m²
H | Extra for movement joints |  | m
Ceramic tiling; Spec M40.110D
Floors
J | 600 x 600 x 8mm; level or to falls not exceeding 15 degrees from horizontal; alternating colour flag tiles; laid to circle 2.65m radius |  | m²
K | Extra for aluminium reducing strip; 2.65 radius |  | m
| Revision 1 (11/1/08) | Page Total
Ref |  | Quantity | Unit | Rate | £
Accessories; Spec M40
Floors
A | 10mm wide dark grey mastic joint at junction of floor tiling and walls or columns etc. (Approximate) |  | m
M42 WOODBLOCK / COMPOSITION BLOCK / MOSAIC PARQUET FLOORING
Laminate Boards; Spec M42.110A
Floors
B | 195mm wide Pergo beech flooring; ref PUQ 37 190 Beach plank; generally |  | m²
M50 RUBBER / PLASTICS / CORK / LINO / CARPET TILING / SHEETING
Carpet tiling; Spec M50.130A
Floors
C | over 300 wide; level or to falls; to latex levelling screed |  | m²
D | over 300 wide; level or to falls; to latex levelling screed; in staircase areas |  | m²
E | treads |  | m
F | risers; Plain; 170 high |  | m
Page Total
Ref |  | Quantity | Unit | Rate | £
Plastics Sheeting; Spec M50.150A
Floors
A | over 300 wide; level or to falls; to latex levelling screed |  | m²
Skirtings
B | 100 high; coved to plaster |  | m
C | Extra over for taper at door edges |  | nr
Accessories; Spec M50.130A
Trims
D | gradus clip top trim ref: TT37/AFT17 |  | m
Aluminium; Spec M50.740
Cover strips
E | type Gradus; carpet to carpet |  | m
F | type Gradus; vinyl to ceramic tile |  | m
G | type Gradus; carpet to ceramic |  | m
H | type Gradus; carpet to Pergo timber flooring |  | m
J | type Gradus; paint to ceramic tiling |  | m
K | type Gradus; ceramic to Pergo timber |  | m
L | type Gradus; vinyl to carpet |  | m
M | type Gradus; carpet to paint |  | m
Page Total
Ref |  | Quantity | Unit | Rate | £
Accessories; Spec M50.750
Nosings to stairs
A | generally |  | m
M60 PAINTING / CLEAR FINISHING
Painting Concrete; Spec M60.115A
Floors
B | over 300 girth |  | m²
N FURNITURE / EQUIPMENT
N10 GENERAL FIXTURES / FURNISHINGS / EQUIPMENT
Matwell Frames; Spec N10.290
Floors
C | 1000 x 1000 mm |  | nr
D | Extra for curved radius approx 100mm |  | nr
E | 1500 x 2350 mm |  | nr
F | 3700 x 1900mm; semicircular to SEAT revolving doors |  | nr
Matting; Spec N10.300A
Floors
G | to concrete |  | m²
Matting; Spec N10.300B
Floors
H | to concrete |  | m²
Page Total
Ref |  | Quantity | Unit | Rate | £
P BUILDING FABRIC SUNDRIES
P20 UNFRAMED ISOLATED TRIMS / SKIRTINGS / SUNDRY ITEMS
Beech; Spec M50.770A
Skirtings, picture rails, architraves and the like
A | 100 x 19; plugging; screwing; pellating |  | m
B | 100 x 19; plugging; screwing; pellating; in staircase areas |  | m
Page Total
£
COLLECTION
Page Nr 3B/1
Page Nr 3B/2
Page Nr 3B/3
Page Nr 3B/4
Page Nr 3B/5
Page Nr 3B/6
TOTAL TO SUMMARY

## 3c Ceiling Finishes
Ref |  | Quantity | Unit | Rate | £
K LININGS/SHEATHING/DRY PARTITIONING
K10 PLASTERBOARD DRY LININGS / PARTITIONS / CEILINGS
Plasterboard lining; Acoustic plasterboard; filling 'and taping joints and filling screw holes for direct decoration (decoration measured separately); plasterboard sealer; including continuous intumescent acoustic sealant to all junctions, abutments etc.; as Architect Specification
Linings to ceilings, 45mm thick overall comprising 3nr 15mm plasterboard layers
A | over 300mm wide | 46 | m²
Linings to ceilings, 15mm thick overall comprising 1nr 15mm plasterboard layer
B | over 300mm wide | 69 | m²
M SURFACE FINISHES
M20 PLASTERED / RENDERED / ROUGHCAST COATINGS
Plaster; one coat skim, 3 thick; as Architect Specification
Ceilings
C | over 300 wide; to plasterboard | 113 | m2
M60 PAINTING / CLEAR FINISHING
Painting Plaster; as Architects Specification
General surfaces
D | over 300 girth | 113 | m²
Page Total
Ref |  | Quantity | Unit | Rate | £
P BUILDING FABRIC SUNDRIES
P10 SUNDRY INSULATION/PROOFING WORK/FIRE STOPS
Fire Stops
Between ceiling and underside of roof
A | 50mm Rockwool mineral fibre with metal mesh support; vertical; to be sealed about all penetrations (Approximate Quantity) | 113 | m²
Page Total
Ref |  | Quantity | Unit | Rate | £
COLLECTION
Page Nr 3C/1
Page Nr 3C/2
TOTAL TO SUMMARY

## 4 Fittings
Ref |  | Quantity | Unit | Rate | £
N FURNITURE/EQUIPMENT
N10/N11 GENERAL FIXTURES/KITCHEN FITTINGS
Kitchen in extension
Provisional Sum
A | Please include the defined provisional sum of £2,200 for the supply and installation of kitchen units to the extension | 1 | item | 2200 | 2200
B | Please include the defined provisional sum of £4,200 for the supply and installation of kitchen units to the café kitchen | 1 | item | 4200 | 4200
C | Please include the defined provisional sum of £1,200 for boxing in connection with the fittings | 1 | item | 1200 | 1200
General Fixtures and Fittings
Mirrors; as Architect Drawing 0141.a/486 and Specification
D | fixing to masonry walls in accordance with manufacturers instructions | 2 | nr
Soap dispenser; ; as Architect Drawing 0141.a/486 and Specification
E | fixing to masonry walls in accordance with manufacturers instructions | 2 | nr
Paper towel dispenser; as Architect Drawing 0141.a/486 and Specification
F | fixing to masonry walls in accordance with manufacturers instructions | 2 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
Warm Air Hand Driers; as Architect Drawing 0141.a/486 and Specification
A | fixing to masonry walls in accordance with manufacturers instructions | 2 | nr
Coat hooks; as Architect Drawing 0141.a/486 and Specification
B | fixing to masonry walls in accordance with manufacturers instructions | 8 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
COLLECTION
Page Nr 4/1
Page Nr 4/2
TOTAL TO SUMMARY

## 5a Sanitary
Ref |  | Quantity | Unit | Rate | £
N: FURNITURE/ EQUIPMENT
N13 SANITARY APPLIANCES/ FITTINGS
Proprietary Sanitary Package; as Architect Drawing 0141.a/486 and Architect and Manufacturer Specification
Doc M Contour 21+
A | fixing to masonry; including all sealant | 2 | nr
R DISPOSAL SYSTEMS
R11 FOUL DRAINAGE ABOVE GROUND
Plastics Pipework; Spec R11
Pipes
B | 35 nominal size; bracketed off walls; plugging; screwing; to masonry | 10 | m
C | connections to bossed or trapped fittings | 4 | nr
D | fittings with one end | 2 | nr
E | fittings with two ends | 2 | nr
F | fittings with three end | 1 | nr
Pipes
G | 40 nominal size; bracketed off walls; plugging; screwing; to masonry | 20 | m
H | connections to bossed or trapped fittings | 4 | nr
I | fittings with one end | 2 | nr
Page Total
COLLECTION
Page Nr 4/1
TOTAL TO SUMMARY

## 5b Electrical
Ref |  | Quantity | Unit | Rate | £
SERVICES INSTALLATION
ELECTRICAL INSTALLATION
Preambles
Allow for all Electrical Installation works as shown on the Tender drawings, specification and where indicated on the Architect drawings
A | generally |  | it
Include in the tender price for any amendments issued during the tender period
B | generally |  | it
Complete all tender summaries, appendices etc. as required in accordance with the Electrical Specification and return with the Form of Tender
C | generally |  | it
Works to be carried out by qualified installer
D | generally |  | it
Electrical Installation Tender Summary
Include here for all works, including all builders work in connection, shown on Electrical Installation drawings and Specification or apparent as being necessary from all tender drawings and specification provided
E | generally |  | it
Tender breakdown
F | provide a breakdown of the Electrical Installation cost in accordance with the M & E tender summary included in the Design Specification document |  | it
TOTAL TO SUMMARY

## 5c Mechanical
Ref |  | Quantity | Unit | Rate | £
SERVICES INSTALLATION
MECHANICAL INSTALLATION
Preambles
Allow for all Mechanical Installation works as shown on the Tender drawings, specification and where indicated on the Architect drawings
A | generally | 1 | it
Include in the tender price for any amendments issued during the tender period
B | generally | 1 | it
Complete all tender summaries, appendices etc. as required in accordance with the Mechanical Specification and return with the Form of Tender
C | generally |  | it
Works to be carried out by qualified installer
D | generally |  | it
Mechanical Installation Tender Summary
Include here for all works, including all builders work in connection, shown on Mechanical Installation drawings and Specification or apparent as being necessary from all tender drawings and specification provided
E | generally |  | it
Tender breakdown
F | provide a breakdown of the Mechanical Installation cost in accordance with the M & E tender summary included in the Specification document |  | it
TOTAL TO SUMMARY

## 6a Site Works
Ref |  | Quantity | Unit | Rate | £
D GROUNDWORKS
D20 EXCAVATING AND FILLING
Excavating
To reduced levels
A | maximum depth not exceeding 1.00m; (Approximate) | 31 | m³
Disposal
Surface water
B | generally |  | it
Ground water
C | generally |  | it
Excavated material
D | off site; (Approximate) | 15 | m³
Filling; selected excavated material
Filling
E | average thickness not exceeding 0.25m | 16 | m³
Filling; imported type 1 granular fill material
Filling
F | average thickness not exceeding 0.25m | 15 | m³
Surface treatments
Compacting bottoms of excavations
G | bottoms of excavations | 125 | m²
Page Total
Ref |  | Quantity | Unit | Rate | £
A | filling | 61 | m²
B | filling; blinding with sand | 61 | m²
Geotextile sheet; Tensar SS30 or similar approved; Spec D20.550
Geotextile sheet
C | generally | 125 | m²
Q PAVING / PLANTING / FENCING / SITE FURNITURE
Q10 KERBS / EDGINGS / CHANNELS / PAVING ACCESSORIES
Precast concrete
Edgings
D | 50 x 150 edging; including 100mm concrete beds and haunching one side (Approximate) | 55 | m
Q25 SLAB / BLOCK / SETT / COBBLE / PAVINGS
Impermeable paving
Pavings
E | level or to falls; on and including 30mm bedding sand | 74 | m²
Q28 TOPSOIL AND GROWING MEDIA
Preparation; subsoil surface preparation for planted bed
Preparation
F | generally; (Approximate) | 15 | m²
Page Total
Ref |  | Quantity | Unit | Rate | £
Topsoil; Imported topsoil
Filling
G | average thickness not exceeding 0.25m; (Approximate) | 4 | m³
Provisional Sums
Gates
H | Include the Provisional Sum of £1,500 for timber fence and gate |  | it | 1500 | 1500
Bin store
I | Include the Provisional Sum of £2,500 for bin store |  | it | 2500 | 2500
Dranage
J | Include the Provisional Sum of £22,500 for drainage |  | it | 22500 | 22500
External Services
K | Include the Provisional Sum of £2,500 for external services |  | it | 2500 | 2500
Page Total
Ref |  | Quantity | Unit | Rate | £
COLLECTION
Page Nr 6A/1
Page Nr 6A/2
Page Nr 6A/3
TOTAL TO SUMMARY

## DEMS AND ALTS
Ref |  | Quantity | Unit | Rate | £
DEMOLITIONS AND ALTERATIONS
| Demolition Works; Architect's Drawings 0141.a/411, /416, and /417; submit all relevant notices; design and provide temporary works and protect the retained structures; dispose of all arisings off site |  |  |  |  | Clean exiting lodge walls throughout; undertake spot repairs; prepare for new finish
Paint exiisting walls in lodge
Remove single storey rear extension of Lodge; soft strip prior to demolition; disconnect, make safe and protect services installations above and below ground; remove all construction aboove and below ground including grub-up foundations
A | overall footprint 40m2 | 1 | item
B | E.O Set aside carefully roof coverings, including verges, ridges, rainwater goods, etc. for re-use on Lodge roof; set aside and store; clean off for re-use | 1 | item
Remove single storey outbuilding; soft strip prior to demolition; disconnect, make safe and protect services installations above and below ground; remove all construction aboove and below ground including grub-up foundations; including attached walls;
C | overall footprint 21m2 | 1 | item
Alterations to existing retained buildings; Architect's Drawings 0141.a/411, /416, and /417; submit all relevant notices; design and provide temporary works and protect the retained structures; dispose of all arisings off site
Break out slab within existing Lodge; dispose of all arisings off-site; compact and prepare ground for new slab
D | approximately 250 thick with 250 sub-base | 42 | m2
Page Total
Ref |  | Quantity | Unit | Rate | £
Remove and carefully set aside roof coverings from Lodge, including verges, ridges, rainwater goods, etc. for re-use; set aside and store; clean off for re-use
A | generally | 68 | m2
Remove rotten roof timbers and dispose of off-site; replace with new scarfed in as necessary
B | 47 x 200 (Approximate quantity) | 16 | m
C | 47 x 50 (Approximate quantity) | 40 | m
Remove the chimney internally on the ground floor up to underside of the roof; seal off flues; piece in treated sawn softwood rafters; make good roof coverings
D | 2435 x 950 overall on plan | 1 | item
Form opening in 540 thick external masonry walls; form square revelas, head and reduce by 250mm at floor to allow new slab and floor finish; make good
E | 1600mm wide x 2900mm high | 1 | item
Remove external door; prepare openings to receive new door
F | generally | 1 | item
Remove windows; prepare openings to receive new windows
G | generally | 5 | nr
Page Total
Ref |  | Quantity | Unit | Rate | £
Demolish internal masonry walls; including finishes, fittings, attachments, etc.
A | 100mm thick | 21 | m²
Remove internal doors; including all linings, architraves, etc. prepare square opening for new
B | generally | 1 | nr
Remove internal doors; including all linings, architraves, etc.
C | generally | 3 | nr
Remove ceiling
D | generally | 42 | m2
New works to Lodge roof; where stated as refix this is to be from salvaged materials
Roof
E | refix existing slates | 185 | m2
F | new 50 x 50 batten | 632 | m
G | new slates (Approximate quantity) | 185 | m2
H | refix existing gutter; including all angles, junctions, etc | 39 | m
I | new gutter; including all angles, junctions, etc (Approximate quantity) | 39 | m
J | refix existing downpipe; including all angles, junctions, etc | 3 | m
Page Total
Ref |  | Quantity | Unit | Rate | £
A | new downpipe; including all angles, junctions, etc (Approximate quantity) | 3 | m
B | refix hip slates | 23 | m
C | refix hip slates (Approximate) | 23 | m
D | refix ridge slates | 8 | m
E | refix ridge slates (Approximate) | 8 | m
F | valley | 11 | m
G | new fascia to match existing | 34 | m
H | new soffit to match existing | 35 | m
I | new verge to match existing | 4 | m
J | re-render chimney | 1 | item
K | new stepped flashing to chimney | 2 | m
L | apron flashing to chimney | 1 | m
M | counter flashing to chimney | 2 | m
Reinforced in-situ concrete
New concrete floor in Lodge; 100mm thick fibre reinforced concrete slab; 1600 gauge DPM and radon membrane; 75mm PIR insulation taped; radon sump; 50mm sand blinding on compacted ground
N | as Architect Specification 1 | 42 | m2
Page Total
Ref |  | Quantity | Unit | Rate | £
E40 : DESIGNED JOINTS FOR IN-SITU CONCRETE
Formed Joint
Expansion Joint
A | 16 closed cell polythene foam compressible filler secured with mastic | 36 | m
M60 PAINTING / CLEAR FINISHING
Painting existing plaster; prepare in accordance with BS 6150, Section 6; including clean off existing surfaces; Smooth surface irregularities; fill joints, cracks, holes and other depressions with stoppers/fillers ; abrade to a smooth finish
General surfaces
B | over 300 girth | 92 | m²
Page Total
£
COLLECTION
Page Nr 7A/1
Page Nr 7A/2
Page Nr 7A/3
Page Nr 7A/4
TOTAL TO SUMMARY