## Sheet1
Highways Agency Confirmation of Task Order Redactions made under FOIA 2000 exemptions sec 40: personal info and sec 43: commercial.
Supplier: | AECOM | Fee Request for this CTO |  | Redatecd
Project Title: | Package 3: A14 J34 - J38, M11 J10 Traffic Data Collection
Contract Ref. | 114/2/1391/1 | CPA No.: | Redatecd | BPA No.: | Redatecd
PIN Description: | Recoverable External | Sub Pin: | Redatecd | PIN No.: | Redatecd
HA Reference: | Redatecd | Start and End Date : |  | 16/09/2015 - 27/11/2015
Task Overview and Expected Outcomes
The A14 runs from M1 Junction 19 (just east of Rugby) South East to Felixstowe. This package covers Junctions 34 to 38 which are located around the edge of Cambridge. This section of the A14 experiences high levels of congestion and reduced journey times for vehicles using the route. This package also includes M11 Junction 10 which located near Duxford, to the south of Cambridge. The assessment is broken down into several phases. The intention of this first phase is to build individual junction models which replicate the current situation. A second phase (not covered in this proposal) will utilise these models and test with various future scenarios which consider expected traffic growth on the network and committed development to understand how the junction will operate in the future. This will allow for problems to be identified and understood at each junction and solutions to then be developed as part of the third phase (not covered in this proposal). The fourth phase (not covered in this proposal) will test the proposed solutions using the junction models to determine which is the most suitable to resolve the issues. This proposal focuses on Phase 1 only. It will incorporate the following: • Data collection of all junctions • Junction modelling of the existing scenario
Task Objectives and Milestones
The objective of this task is to collect existing traffic flows and patterns at these junctions and use this information to build junction models using ARCADY, PICADY and LINSIG. Which modelling software used will vary depending on the junction’s design.
Expected Project Outcomes
AECOM will prepare a technical note discussing our findings from modelling the junctions and our recommendations for the next phases and further assessment.
Project Risk and Management
The proposal assumes 1 day of traffic, queue and saturation flow surveys to inform the junction model assessment. The ability to complete the junction models is dependent upon the successful completion of the related traffic surveys. In the event of poor weather or an incident, data collected may not be representative of a typical scenario. The camera coverage to collect queue data is limited as there not enough suitable camera fixing points in the area. Although the camera coverage is reasonably extensive however there are areas of the carriageway which will not be covered. It is possible that not all of the queue will be captured. The programme is dependent in part upon the timely provision of information from third parties. AECOM cannot be held responsible for the timely provision of information that is outside of AECOM’s control.
HA Project Sponsor | Sign: |  | Print Name: |  | Date:
Management Approver: | Sign: |  | Print Name: |  | Date:
Contractual Approval: | Sign: |  | Print Name: |  | Date: